## Welcome!
Welcome to Statistical PERT® Beta Edition
Statistical PERT® (SPERT®) is a freely licensed, probabilistic, estimation technique. Use Statistical PERT | All models are wrong, but some are useful.
to estimate uncertainties that have bell-shaped risk properties, like: task duration, work effort, | George E. P. Box, British statistician (1919-2013)
revenue, expenses, agile story points, project portfolios, event attendance, and more.
Statistical PERT® Beta Edition uses Excel's two beta distribution functions, BETA.DIST and | Facts are stubborn things, but statistics are pliable.
BETA.INV to model uncertainty. To easily model mild-to-moderately skewed uncertainties, | Mark Twain, American humorist (1835-1910)
try Statistical PERT® Normal Edition which uses Excel's two normal distribution functions
NORMAL.DIST and NORMAL.INV.
This example workbook is intended to help you quickly get started. You can also download
a Quick Start guide for Statistical PERT® Beta Edition. The Quick Start guide explains the
essential things you need to know to use the Statistical PERT® Beta Edition spreadsheet.
All Statistical PERT downloads share the same three steps for making a probablistic estimate:
1) Create a 3-point estimate (minimum, most likely, maximum)
2) Render a subjective judgment about the most likely outcome
3) Select any probabilistic planning estimate, or make a risk-based forecast
If you have any questions, suggestions, or comments, I'd love to hear from you! | New with Version 3 -- Monte Carlo simulation of a single, random variable!
Contact me!
Version 3.0.s – © 2015-2020, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Subscribe to the SPERT® newsletter for monthly tips, free webinars, and new release notifications
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice, | New with Version 3 -- SPERT Scheduler for plan-driven projects
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
Plus:
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY; | - Enhanced! Model three scenarios side-by-side on the Agile Forecast worksheet
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE. | - Other minor improvements, too!
See the GNU General Public License for more details (https://www.gnu.org/licenses/).

## README for Version 3
Statistical PERT® (SPERT®) Beta Edition README for Version 3
Statistical PERT® Beta Edition Version 3 introduces a real Monte Carlo simulation worksheet that
will sample a single, random variable for 10,000 trials using an Excel data table (see the SPERT® Beta
MC Simulation tab). That is the only SPERT worksheet that uses Monte Carlo simulation to construct
probabilistic estimates using Excel's beta distribution functions, BETA.DIST and BETA.INV.
Because SPERT now includes a data table to support Monte Carlo simulation, this SPERT workbook
may not have the same, speedy performance as it did in Version 2 and earlier versions. If you find that
this workbook's calculations are sluggish, check the Excel setting for "Calculation Options" under the
Formulas tab on the Excel Ribbon and select the option, "Automatic Except for Data Tables." This will
avoid SPERT performing a 10,000 trial simulation everytime you interact with any data entry cells
on any worksheet. If you want to use the Monte Carlo simulation, press F9 to execute a simulation
of 10,000 trials (this is only meaningful with the SPERT® Beta MC Simulation worksheet).
You may also delete the SPERT® Beta MC Simulation worksheet if you don't want to use Monte Carlo
simulation, or if you want to reduce the file size of this SPERT spreadsheet file.
Version 3.0.s – © 2015-2020, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Subscribe to the SPERT® newsletter for monthly tips, free webinars, and new release notifications
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).
TL;DR
On the Excel Ribbon, look for the "Calculation" group under the "Formulas" menu selection. Then, click the "Calculation Options" button and select "Automatic Except for Data Tables" to increase the speed and calculation performance of all SPERT worksheets.
Or, simply delete the SPERT® Beta MC Simulation worksheet from this Excel workbook.

## SPERT® Beta for Beginners
Statistical PERT® (SPERT®) Beta Edition for Beginners
First, enter a three-point estimate for any uncertainty
| Minimum | Most Likely | Maximum
| 60 | 120 | 240 | Use SPERT to estimate task duration, work effort, agile story points, cost, revenue, event attendance, etc. | [12 empty] | Variance
1021.953
|  |  | Validate your bell-shaped uncertainty | 1 |  |  | A green checkmark means you have correctly entered minimum, most likely and maximum point-estimates
Examine SPERT's Skew Analysis | [6 empty] | Skew Analysis |  |  | This analysis helps SPERT choose an implied bell-shaped curve for your uncertainty
Slight skew
[7 empty] | Render a subjective judgment about HOW LIKELY |  |  | Most Likely Confidence
[7 empty] | the Most Likely outcome really is |  |  | Medium Confidence | This choice influences the implied bell-shaped curve for the uncertainty you are estimating
© 2015-2020, William W. Davis, MSPM, PMP
This beta distribution graph shows the bell-shaped curve for your uncertainty | [10 empty] | Curve | The bell-shaped curve will change depending on your 3-point estimate and your subjective judgment about the Most Likely outcome (above) |  |  | The bell-shaped curve will change depending on your 3-point estimate and your subjective judgment about the Most Likely outcome (above)
[12 empty] | Note: If your 3-point estimate indicates skewing, SPERT Beta Edition fits your uncertainty into a beta-distributed, bell-shaped curve |  |  | Note: If your 3-point estimate indicates skewing, SPERT Beta Edition fits your uncertainty into a beta-distributed, bell-shaped curve
[5 empty] | Range % | R/L Skew |  | X | Midpoint |  |  | Y | Alpha | Beta | Mean | SPERT SD
[5 empty] | 33.3333 | R |  | 3 | 150 |  | This is the Mean (average) and SPERT Standard Deviation for your uncertainty | 6 | 2.5 | 4 | 129.228 | 31.968 |  | You don't have to know this or do anything with this, but SPERT shows these approximate values for your information only
[16 empty] | Show probabilities from either the left-side area or right-side area |  | Show Left-Side Area |  | Read the red text below to see how this choice affects the SPERT estimates
[18 empty] | Planning Estimate | SPERT Probability | Note: This is a cumulative probability, so the SPERT Probability is the likelihood that
the Planning Estimate will be EQUAL TO or GREATER THAN the uncertainty's true outcome*
[16 empty] | Enter a Planning Estimate and see its likelihood of occurrence under SPERT Probability |  | 150 | 73.61% | * This is true if you choose Show Left-Side Area in the dropdown control above. If you choose Show Right-Side Area,
you'll see the SPERT Probability that your Planning Estimate will be EXCEEDED by the uncertainty's true outcome.
Show the likelihood that the SPERT estimates will be EQUAL TO or GREATER THAN an uncertainty
[19 empty] | Here, you'll see several SPERT estimates with different probabilities of occurrence | SPERT Probabilistic Estimates using the BETA distribution
[19 empty] | You can change these cumulative probability choices (enter values between 1% and 99%) → | 5% | 95% | 10% | 20% | 30% | 40% | 50% | 60% | 70% | 80% | 90% | 99%
[19 empty] | Find a SPERT Probablistic Estimate that best matches your risk propensity → | 80.6675 | 185.5319 | 88.3784 | 99.7938 | 109.3262 | 118.2031 | 126.9838 | 136.0975 | 146.0522 | 157.7256 | 173.4327 | 205.0138
Choose whether to show currency formatting
Do not show currency formatting
That's it! Now try using the (3-Point entry) worksheet!
Or, use the (1-Point entry) worksheet, where two heuristics automatically calculate the Minimum and Maximum point-estimates
| -50% | << Heuristics >> | 100%
| Minimum | Most Likely | Maximum
| 60 | 120 | 240
Try selecting a different dropdown percentage by clicking above the Minimum and Maximum cell headings,
and see the value changes for the minimum and maximum point-estimates in the green-shaded cells.
The rest of the (1-Point entry) worksheet works exactly the same way as the (3-Point entry) worksheet.
Version 3.0.s – © 2015-2020, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Subscribe to the SPERT® newsletter for monthly tips, free webinars, and new release notifications
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).
| X-axis increments | 1.8 | This, along with the grayed-out table below, is only used to create a Sparkline
| 60 | 2.6257e-09
| 61.8 | 0.00019457
| 63.6 | 0.00053381
| 65.4 | 0.00095095
| 67.2 | 0.0014193
| 69 | 0.0019221
| 70.8 | 0.0024478
| 72.6 | 0.0029871
| 74.4 | 0.0035331
| 76.2 | 0.0040799
| 78 | 0.0046226
| 79.8 | 0.0051573
| 81.6 | 0.0056804
| 83.4 | 0.0061892
| 85.2 | 0.0066811
| 87 | 0.0071541
| 88.8 | 0.0076064
| 90.6 | 0.0080365
| 92.4 | 0.0084433
| 94.2 | 0.0088256
| 96 | 0.0091828
| 97.8 | 0.0095141
| 99.6 | 0.0098192
| 101.4 | 0.010098
| 103.2 | 0.010349
| 105 | 0.010574
| 106.8 | 0.010772
| 108.6 | 0.010944
| 110.4 | 0.011089
| 112.2 | 0.011208
| 114 | 0.011301
| 115.8 | 0.01137
| 117.6 | 0.011413
| 119.4 | 0.011433
| 121.2 | 0.011429
| 123 | 0.011403
| 124.8 | 0.011354
| 126.6 | 0.011285
| 128.4 | 0.011195
| 130.2 | 0.011085
| 132 | 0.010957
| 133.8 | 0.010812
| 135.6 | 0.010649
| 137.4 | 0.010471
| 139.2 | 0.010278
| 141 | 0.010071
| 142.8 | 0.0098509
| 144.6 | 0.0096191
| 146.4 | 0.0093763
| 148.2 | 0.0091236
| 150 | 0.0088619
| 151.8 | 0.0085922
| 153.6 | 0.0083155
| 155.4 | 0.0080328
| 157.2 | 0.007745
| 159 | 0.0074532
| 160.8 | 0.0071581
| 162.6 | 0.0068608
| 164.4 | 0.0065622
| 166.2 | 0.0062631
| 168 | 0.0059644
| 169.8 | 0.0056669
| 171.6 | 0.0053715
| 173.4 | 0.005079
| 175.2 | 0.00479
| 177 | 0.0045054
| 178.8 | 0.0042258
| 180.6 | 0.003952
| 182.4 | 0.0036845
| 184.2 | 0.0034239
| 186 | 0.0031708
| 187.8 | 0.0029258
| 189.6 | 0.0026893
| 191.4 | 0.0024617
| 193.2 | 0.0022435
| 195 | 0.002035
| 196.8 | 0.0018366
| 198.6 | 0.0016485
| 200.4 | 0.0014709
| 202.2 | 0.0013039
| 204 | 0.0011478
| 205.8 | 0.0010026
| 207.6 | 0.00086836
| 209.4 | 0.00074494
| 211.2 | 0.00063232
| 213 | 0.00053035
| 214.8 | 0.00043882
| 216.6 | 0.00035749
| 218.4 | 0.00028604
| 220.2 | 0.00022409
| 222 | 0.00017121
| 223.8 | 0.0001269
| 225.6 | 9.0596e-05
| 227.4 | 6.1685e-05
| 229.2 | 3.9473e-05
| 231 | 2.3209e-05
| 232.8 | 1.2071e-05
| 234.6 | 5.1723e-06
| 236.4 | 1.5563e-06
| 238.2 | 1.9752e-07
| 240 | 3.4383e-17
↑ Rows 61 through 163 are hidden; they are used to create the bell-curve Sparkline
Note on B4: The Minimum point-estimate represents the smallest value that is feasible, but highly improbable.
Note on C4: The Most Likely point-estimate represents the value you believe will most likely occur for each uncertainty, although many other possible outcomes exist between the Minimum and Maximum point-estimates.
Note on D4: The Maximum point-estimate represents the largest value that is feasible, but highly improbable
Note on N12: The shape of the bell-curve is heavily influenced by how confident you believe the Most Likely outcome will occur relative to other, possible outcomes between the Minimum and Maximum point-estimates. When you are more confident in the Most Likely outcome, the bell-curve grows taller, and there is a shrinking likelihood of other occurrences near the Minimum and Maximum point-estimates. Conversely, when you are less confident in the Most Likely outcome, the bell-curve grows flatter, and there is a rising likelihood of other occurrences near the Minimum and Maximum point-estimates. (You can add to, remove, or modify the dropdown control options using the VLookups worksheet).
Note on O15: William Davis: SPERT builds an implied, bell-shaped curve to represent the risk characteristics for your uncertainty. The flatter, wider the bell-curve curve is, the more uncertain the outcomes are over the feasible region. If the bell-curve's vertical rise is steep, though, your uncertainty has much less volatility near the most likely outcome. If the bell-curve is both centered and symmetrical, it fits a normal distribution. The beta distribution can also show skewed bell-curves, dependent on your 3-point estimate and how likely the most likely outcome really is.
Note on V23: You may optionally enter a planning estimate for each uncertainty you enter, and see its cumulative probability result in the 'SPERT Probability' column. The cumulative probability is the likelihood your planning estimate will be EQUAL TO or GREATER THAN the uncertainty you are estimating. Choosing a larger planning estimate will increase the cumulative probability, and choosing a smaller planning estimate will decrease the cumulative probability.
Note on W23: The SPERT Probability shows the cumulative probability of each Planning Estimate you entered in column R. If you select 'Show Left-Side Area' in cell R1, this column shows the likelihood that your Planning Estimate will be EQUAL TO or GREATER THAN the uncertainty you are estimating. If you select 'Show Right-Side Area' in cell R1, this column shows the likelihood that the uncertainty will EXCEED your Planning Estimate in column R.
Note on B40: Use a simple heuristic to quickly create MINIMUM point-estimates. Do this by selecting a percentage in cell B2. Minimum point-estimates are automatically created for you by taking the Most Likely point-estimate in column C and reducing it by the percentage value specified in cell B2. If you want, overwrite any cell formula in column B to manually enter a non-calculated, minimum value for a particular three-point estimate. (If you need to modify the dropdown choices in cell B2, you can do that in the Vlookups worksheet).
Note on C40: The Most Likely point-estimate represents the value you believe will most likely occur for each uncertainty, although many other possible outcomes exist between the Minimum and Maximum point-estimates.
Note on D40: Use a simple heuristic to quickly create MAXIMUM point-estimates. Do this by selecting a percentage in cell D2. Maximum point-estimates are automatically created for you by taking the Most Likely point-estimate in column C and increasing it by the percentage value specified in cell D2. If you want, overwrite any cell formula in column D to manually enter a non-calculated, maximum value for a particular three-point estimate. (If you need to modify the dropdown choices in cell D2, you can do that in the Vlookups worksheet).

## SPERT® Beta (1-Point entry)
| Statistical PERT® (SPERT®) Beta Edition 1-Point Entry | [16 empty] | Show Left-Side Area |  | Show the likelihood that the SPERT estimates will be EQUAL TO or GREATER THAN an uncertainty
| -50% | << Heuristics >> | 100% | [14 empty] | Planning Estimate | SPERT Probability | SPERT Probabilistic Estimates using the BETA distribution | [11 empty] | This section is only to build Line Sparklines to show the bell-shaped curve for each row, and the summary bell-curve chart.
ID | Minimum | Most Likely | Maximum |  | Range % | R/L Skew | Skew Analysis | X | Midpoint | Most Likely Confidence | Y | Alpha | Beta | Curve | Mean | SPERT SD | Variance |  |  | 5% | 95% | 10% | 20% | 30% | 40% | 50% | 60% | 70% | 80% | 90% | 99% | x-axis increments (magenta in blue cells shows the increment, the next 101 columns are the x-axis values for the Line Sparkline column and summary bell-curve chart) | [101 empty] | These are the y-axis values with which the bell-shaped curve is built (used only for the Line SparkLine column) | [100 empty] | ← Columns AH through IB are hidden; they are used to create Sparklines and the bell-curve bar chart
1 | 60 | 120 | 240 | 1 | 33.3333 | R | Slight skew | 3 | 150 | Near Certainty | 1 | 13 | 25 |  | 121.578 | 13.68 | 187.1424 | 150 | 97.65% | 99.9436 | 144.9375 | 104.2664 | 109.7826 | 113.9344 | 117.5855 | 121.0755 | 124.6317 | 128.4997 | 133.0949 | 139.5564 | 155.0347 | 1.8 | 60 | 61.8 | 63.6 | 65.4 | 67.2 | 69 | 70.8 | 72.6 | 74.4 | 76.2 | 78 | 79.8 | 81.6 | 83.4 | 85.2 | 87 | 88.8 | 90.6 | 92.4 | 94.2 | 96 | 97.8 | 99.6 | 101.4 | 103.2 | 105 | 106.8 | 108.6 | 110.4 | 112.2 | 114 | 115.8 | 117.6 | 119.4 | 121.2 | 123 | 124.8 | 126.6 | 128.4 | 130.2 | 132 | 133.8 | 135.6 | 137.4 | 139.2 | 141 | 142.8 | 144.6 | 146.4 | 148.2 | 150 | 151.8 | 153.6 | 155.4 | 157.2 | 159 | 160.8 | 162.6 | 164.4 | 166.2 | 168 | 169.8 | 171.6 | 173.4 | 175.2 | 177 | 178.8 | 180.6 | 182.4 | 184.2 | 186 | 187.8 | 189.6 | 191.4 | 193.2 | 195 | 196.8 | 198.6 | 200.4 | 202.2 | 204 | 205.8 | 207.6 | 209.4 | 211.2 | 213 | 214.8 | 216.6 | 218.4 | 220.2 | 222 | 223.8 | 225.6 | 227.4 | 229.2 | 231 | 232.8 | 234.6 | 236.4 | 238.2 | 239.999 | 0 | 2.0215e-16 | 6.4894e-13 | 6.5826e-11 | 1.6205e-09 | 1.8341e-08 | 1.2685e-07 | 6.2401e-07 | 2.3901e-06 | 7.5566e-06 | 2.0523e-05 | 4.926e-05 | 0.0001067 | 0.00021194 | 0.00039077 | 0.00067542 | 0.001103 | 0.0017127 | 0.0025423 | 0.0036233 | 0.0049767 | 0.0066085 | 0.0085068 | 0.01064 | 0.012956 | 0.015388 | 0.017851 | 0.020255 | 0.022506 | 0.024513 | 0.026196 | 0.027488 | 0.028342 | 0.028733 | 0.028657 | 0.028129 | 0.027188 | 0.025883 | 0.024279 | 0.022445 | 0.020454 | 0.018377 | 0.016281 | 0.014225 | 0.012257 | 0.010415 | 0.008729 | 0.0072147 | 0.0058803 | 0.0047256 | 0.0037441 | 0.0029239 | 0.0022504 | 0.0017064 | 0.0012745 | 0.00093729 | 0.00067849 | 0.00048324 | 0.00033849 | 0.00023306 | 0.00015764 | 0.0001047 | 6.8223e-05 | 4.3586e-05 | 2.728e-05 | 1.6711e-05 | 1.001e-05 | 5.8567e-06 | 3.3429e-06 | 1.8591e-06 | 1.0058e-06 | 5.2854e-07 | 2.6928e-07 | 1.3275e-07 | 6.3178e-08 | 2.8955e-08 | 1.2743e-08 | 5.3676e-09 | 2.1563e-09 | 8.2264e-10 | 2.9663e-10 | 1.0054e-10 | 3.1822e-11 | 9.3354e-12 | 2.5157e-12 | 6.1608e-13 | 1.3536e-13 | 2.626e-14 | 4.4113e-15 | 6.2593e-16 | 7.2666e-17 | 6.6182e-18 | 4.4672e-19 | 2.0633e-20 | 5.8021e-22 | 8.2868e-24 | 4.4373e-26 | 5.0419e-29 | 3.3873e-33 | 2.2806e-40 | 1.9224e-118
2 | 60 | 120 | 240 | 1 | 33.3333 | R | Slight skew | 3 | 150 | Extremely High Confidence | 2 | 8 | 15 |  | 122.604 | 17.496 | 306.11 | 150 | 93.31% | 95.2013 | 152.7822 | 100.47 | 107.3498 | 112.6172 | 117.2973 | 121.8021 | 126.4146 | 131.4471 | 137.4326 | 145.8314 | 165.6311 | 1.8 | 60 | 61.8 | 63.6 | 65.4 | 67.2 | 69 | 70.8 | 72.6 | 74.4 | 76.2 | 78 | 79.8 | 81.6 | 83.4 | 85.2 | 87 | 88.8 | 90.6 | 92.4 | 94.2 | 96 | 97.8 | 99.6 | 101.4 | 103.2 | 105 | 106.8 | 108.6 | 110.4 | 112.2 | 114 | 115.8 | 117.6 | 119.4 | 121.2 | 123 | 124.8 | 126.6 | 128.4 | 130.2 | 132 | 133.8 | 135.6 | 137.4 | 139.2 | 141 | 142.8 | 144.6 | 146.4 | 148.2 | 150 | 151.8 | 153.6 | 155.4 | 157.2 | 159 | 160.8 | 162.6 | 164.4 | 166.2 | 168 | 169.8 | 171.6 | 173.4 | 175.2 | 177 | 178.8 | 180.6 | 182.4 | 184.2 | 186 | 187.8 | 189.6 | 191.4 | 193.2 | 195 | 196.8 | 198.6 | 200.4 | 202.2 | 204 | 205.8 | 207.6 | 209.4 | 211.2 | 213 | 214.8 | 216.6 | 218.4 | 220.2 | 222 | 223.8 | 225.6 | 227.4 | 229.2 | 231 | 232.8 | 234.6 | 236.4 | 238.2 | 239.999 | 0 | 1.2347e-10 | 1.371e-08 | 2.0291e-07 | 1.3148e-06 | 5.4147e-06 | 1.673e-05 | 4.2374e-05 | 9.275e-05 | 0.00018152 | 0.00032512 | 0.00054183 | 0.00085051 | 0.0012692 | 0.0018136 | 0.0024955 | 0.003322 | 0.0042943 | 0.005407 | 0.0066485 | 0.0080006 | 0.0094399 | 0.010938 | 0.012463 | 0.013981 | 0.015456 | 0.016854 | 0.018144 | 0.019294 | 0.02028 | 0.02108 | 0.021681 | 0.022071 | 0.022248 | 0.022214 | 0.021974 | 0.021542 | 0.020933 | 0.020166 | 0.019263 | 0.018247 | 0.017142 | 0.015973 | 0.014763 | 0.013535 | 0.012309 | 0.011104 | 0.0099358 | 0.0088184 | 0.0077627 | 0.0067768 | 0.0058667 | 0.0050357 | 0.0042851 | 0.0036143 | 0.0030211 | 0.0025021 | 0.0020528 | 0.0016678 | 0.0013415 | 0.001068 | 0.00084114 | 0.00065519 | 0.0005045 | 0.00038384 | 0.0002884 | 0.00021388 | 0.00015645 | 0.0001128 | 8.0106e-05 | 5.5981e-05 | 3.8462e-05 | 2.5953e-05 | 1.7179e-05 | 1.114e-05 | 7.0671e-06 | 4.3783e-06 | 2.6441e-06 | 1.5532e-06 | 8.8535e-07 | 4.8832e-07 | 2.5978e-07 | 1.3279e-07 | 6.4936e-08 | 3.022e-08 | 1.33e-08 | 5.4946e-09 | 2.111e-09 | 7.4571e-10 | 2.3872e-10 | 6.7976e-11 | 1.6801e-11 | 3.4868e-12 | 5.7997e-13 | 7.2222e-14 | 6.0576e-15 | 2.8668e-16 | 5.4923e-18 | 2.0214e-20 | 1.3247e-24 | 3.7916e-70
3 | 60 | 120 | 240 | 1 | 33.3333 | R | Slight skew | 3 | 150 | Very High Confidence | 3 | 5.5 | 10 |  | 123.864 | 21.204 | 449.6096 | 150 | 88.18% | 90.9719 | 160.7221 | 97.0364 | 105.1641 | 111.5052 | 117.2005 | 122.7207 | 128.3976 | 134.6044 | 141.9829 | 152.2843 | 175.9831 | 1.8 | 60 | 61.8 | 63.6 | 65.4 | 67.2 | 69 | 70.8 | 72.6 | 74.4 | 76.2 | 78 | 79.8 | 81.6 | 83.4 | 85.2 | 87 | 88.8 | 90.6 | 92.4 | 94.2 | 96 | 97.8 | 99.6 | 101.4 | 103.2 | 105 | 106.8 | 108.6 | 110.4 | 112.2 | 114 | 115.8 | 117.6 | 119.4 | 121.2 | 123 | 124.8 | 126.6 | 128.4 | 130.2 | 132 | 133.8 | 135.6 | 137.4 | 139.2 | 141 | 142.8 | 144.6 | 146.4 | 148.2 | 150 | 151.8 | 153.6 | 155.4 | 157.2 | 159 | 160.8 | 162.6 | 164.4 | 166.2 | 168 | 169.8 | 171.6 | 173.4 | 175.2 | 177 | 178.8 | 180.6 | 182.4 | 184.2 | 186 | 187.8 | 189.6 | 191.4 | 193.2 | 195 | 196.8 | 198.6 | 200.4 | 202.2 | 204 | 205.8 | 207.6 | 209.4 | 211.2 | 213 | 214.8 | 216.6 | 218.4 | 220.2 | 222 | 223.8 | 225.6 | 227.4 | 229.2 | 231 | 232.8 | 234.6 | 236.4 | 238.2 | 239.999 | 0 | 8.9466e-08 | 1.8476e-06 | 1.0446e-05 | 3.4726e-05 | 8.6262e-05 | 0.00017815 | 0.00032377 | 0.00053572 | 0.00082491 | 0.0011998 | 0.0016662 | 0.0022264 | 0.0028798 | 0.0036225 | 0.0044476 | 0.0053456 | 0.0063047 | 0.0073113 | 0.0083503 | 0.0094056 | 0.010461 | 0.0115 | 0.012506 | 0.013465 | 0.014362 | 0.015185 | 0.015922 | 0.016563 | 0.017102 | 0.017534 | 0.017853 | 0.018059 | 0.018152 | 0.018134 | 0.018008 | 0.01778 | 0.017455 | 0.017041 | 0.016546 | 0.01598 | 0.015351 | 0.01467 | 0.013945 | 0.013188 | 0.012407 | 0.011612 | 0.010811 | 0.010013 | 0.0092248 | 0.0084535 | 0.007705 | 0.0069844 | 0.006296 | 0.0056433 | 0.0050291 | 0.0044552 | 0.0039228 | 0.0034325 | 0.0029842 | 0.0025773 | 0.0022106 | 0.0018826 | 0.0015914 | 0.001335 | 0.0011109 | 0.00091665 | 0.00074973 | 0.00060755 | 0.00048755 | 0.00038724 | 0.00030422 | 0.00023624 | 0.0001812 | 0.00013717 | 0.00010237 | 7.525e-05 | 5.4413e-05 | 3.8652e-05 | 2.693e-05 | 1.837e-05 | 1.2244e-05 | 7.9535e-06 | 5.0215e-06 | 3.071e-06 | 1.812e-06 | 1.0265e-06 | 5.5497e-07 | 2.8428e-07 | 1.3669e-07 | 6.0959e-08 | 2.4821e-08 | 9.0323e-09 | 2.851e-09 | 7.471e-10 | 1.5186e-10 | 2.1365e-11 | 1.6808e-12 | 4.5786e-14 | 9.3606e-17 | 4.9372e-46
4 | 60 | 120 | 240 | 1 | 33.3333 | R | Slight skew | 3 | 150 | High Confidence | 4 | 4 | 7 |  | 125.448 | 25.002 | 625.1 | 150 | 82.81% | 87.0051 | 169.1924 | 93.7612 | 103.0994 | 110.5442 | 117.3113 | 123.918 | 130.7391 | 138.2049 | 147.0583 | 159.3115 | 186.519 | 1.8 | 60 | 61.8 | 63.6 | 65.4 | 67.2 | 69 | 70.8 | 72.6 | 74.4 | 76.2 | 78 | 79.8 | 81.6 | 83.4 | 85.2 | 87 | 88.8 | 90.6 | 92.4 | 94.2 | 96 | 97.8 | 99.6 | 101.4 | 103.2 | 105 | 106.8 | 108.6 | 110.4 | 112.2 | 114 | 115.8 | 117.6 | 119.4 | 121.2 | 123 | 124.8 | 126.6 | 128.4 | 130.2 | 132 | 133.8 | 135.6 | 137.4 | 139.2 | 141 | 142.8 | 144.6 | 146.4 | 148.2 | 150 | 151.8 | 153.6 | 155.4 | 157.2 | 159 | 160.8 | 162.6 | 164.4 | 166.2 | 168 | 169.8 | 171.6 | 173.4 | 175.2 | 177 | 178.8 | 180.6 | 182.4 | 184.2 | 186 | 187.8 | 189.6 | 191.4 | 193.2 | 195 | 196.8 | 198.6 | 200.4 | 202.2 | 204 | 205.8 | 207.6 | 209.4 | 211.2 | 213 | 214.8 | 216.6 | 218.4 | 220.2 | 222 | 223.8 | 225.6 | 227.4 | 229.2 | 231 | 232.8 | 234.6 | 236.4 | 238.2 | 239.999 | 0 | 4.3936e-06 | 3.3071e-05 | 0.00010495 | 0.00023378 | 0.0004288 | 0.00069539 | 0.0010356 | 0.0014488 | 0.0019319 | 0.0024801 | 0.0030869 | 0.003745 | 0.0044458 | 0.0051806 | 0.0059401 | 0.0067149 | 0.0074959 | 0.0082738 | 0.0090402 | 0.0097867 | 0.010506 | 0.01119 | 0.011834 | 0.012431 | 0.012978 | 0.013468 | 0.013901 | 0.014272 | 0.01458 | 0.014824 | 0.015003 | 0.015119 | 0.01517 | 0.01516 | 0.01509 | 0.014962 | 0.014779 | 0.014545 | 0.014262 | 0.013935 | 0.013567 | 0.013162 | 0.012725 | 0.01226 | 0.011771 | 0.011263 | 0.010739 | 0.010204 | 0.0096609 | 0.0091146 | 0.0085683 | 0.0080254 | 0.007489 | 0.006962 | 0.0064472 | 0.0059468 | 0.0054631 | 0.0049979 | 0.0045527 | 0.0041288 | 0.0037272 | 0.0033488 | 0.0029939 | 0.0026629 | 0.0023559 | 0.0020726 | 0.0018127 | 0.0015756 | 0.0013606 | 0.0011669 | 0.0009935 | 0.00083937 | 0.00070333 | 0.00058417 | 0.00048065 | 0.00039148 | 0.00031539 | 0.00025109 | 0.00019733 | 0.00015292 | 0.00011668 | 8.7515e-05 | 6.4407e-05 | 4.6405e-05 | 3.2645e-05 | 2.235e-05 | 1.4833e-05 | 9.496e-06 | 5.8282e-06 | 3.402e-06 | 1.8689e-06 | 9.526e-07 | 4.4162e-07 | 1.8084e-07 | 6.2517e-08 | 1.6911e-08 | 3.1049e-09 | 2.811e-10 | 4.5281e-12 | 1.372e-31
5 | 60 | 120 | 240 | 1 | 33.3333 | R | Slight skew | 3 | 150 | Medium-High Confidence | 5 | 3 | 5 |  | 127.5 | 29.052 | 844.0187 | 150 | 77.34% | 83.1762 | 178.5729 | 90.5349 | 101.0988 | 109.7411 | 117.7054 | 125.5409 | 133.6587 | 142.5398 | 153.0164 | 167.3124 | 197.4618 | 1.8 | 60 | 61.8 | 63.6 | 65.4 | 67.2 | 69 | 70.8 | 72.6 | 74.4 | 76.2 | 78 | 79.8 | 81.6 | 83.4 | 85.2 | 87 | 88.8 | 90.6 | 92.4 | 94.2 | 96 | 97.8 | 99.6 | 101.4 | 103.2 | 105 | 106.8 | 108.6 | 110.4 | 112.2 | 114 | 115.8 | 117.6 | 119.4 | 121.2 | 123 | 124.8 | 126.6 | 128.4 | 130.2 | 132 | 133.8 | 135.6 | 137.4 | 139.2 | 141 | 142.8 | 144.6 | 146.4 | 148.2 | 150 | 151.8 | 153.6 | 155.4 | 157.2 | 159 | 160.8 | 162.6 | 164.4 | 166.2 | 168 | 169.8 | 171.6 | 173.4 | 175.2 | 177 | 178.8 | 180.6 | 182.4 | 184.2 | 186 | 187.8 | 189.6 | 191.4 | 193.2 | 195 | 196.8 | 198.6 | 200.4 | 202.2 | 204 | 205.8 | 207.6 | 209.4 | 211.2 | 213 | 214.8 | 216.6 | 218.4 | 220.2 | 222 | 223.8 | 225.6 | 227.4 | 229.2 | 231 | 232.8 | 234.6 | 236.4 | 238.2 | 239.999 | 0 | 5.6035e-05 | 0.00021522 | 0.00046478 | 0.00079272 | 0.0011878 | 0.0016396 | 0.0021382 | 0.0026745 | 0.0032402 | 0.0038272 | 0.0044286 | 0.0050374 | 0.0056478 | 0.0062541 | 0.0068513 | 0.0074349 | 0.0080007 | 0.0085451 | 0.0090649 | 0.0095573 | 0.01002 | 0.010451 | 0.010848 | 0.01121 | 0.011536 | 0.011825 | 0.012076 | 0.01229 | 0.012467 | 0.012605 | 0.012707 | 0.012772 | 0.012801 | 0.012795 | 0.012756 | 0.012684 | 0.01258 | 0.012447 | 0.012285 | 0.012096 | 0.011882 | 0.011645 | 0.011386 | 0.011106 | 0.010809 | 0.010496 | 0.010168 | 0.0098268 | 0.0094752 | 0.0091146 | 0.0087466 | 0.0083731 | 0.0079958 | 0.0076162 | 0.0072359 | 0.0068565 | 0.0064795 | 0.0061062 | 0.0057379 | 0.005376 | 0.0050215 | 0.0046756 | 0.0043392 | 0.0040132 | 0.0036984 | 0.0033956 | 0.0031054 | 0.0028284 | 0.0025648 | 0.0023152 | 0.0020798 | 0.0018587 | 0.001652 | 0.0014597 | 0.0012817 | 0.0011179 | 0.00096785 | 0.00083137 | 0.00070802 | 0.00059733 | 0.00049877 | 0.00041175 | 0.00033564 | 0.00026975 | 0.00021336 | 0.00016574 | 0.0001261 | 9.3671e-05 | 6.765e-05 | 4.725e-05 | 3.1693e-05 | 2.0223e-05 | 1.2114e-05 | 6.68e-06 | 3.2904e-06 | 1.3763e-06 | 4.4458e-07 | 8.9637e-08 | 5.7172e-09 | 5.5568e-22
6 | 60 | 120 | 240 | 1 | 33.3333 | R | Slight skew | 3 | 150 | Medium Confidence | 6 | 2.5 | 4 |  | 129.228 | 31.968 | 1021.953 | 150 | 73.61% | 80.6675 | 185.5319 | 88.3784 | 99.7938 | 109.3262 | 118.2031 | 126.9838 | 136.0975 | 146.0522 | 157.7256 | 173.4327 | 205.0138 | 1.8 | 60 | 61.8 | 63.6 | 65.4 | 67.2 | 69 | 70.8 | 72.6 | 74.4 | 76.2 | 78 | 79.8 | 81.6 | 83.4 | 85.2 | 87 | 88.8 | 90.6 | 92.4 | 94.2 | 96 | 97.8 | 99.6 | 101.4 | 103.2 | 105 | 106.8 | 108.6 | 110.4 | 112.2 | 114 | 115.8 | 117.6 | 119.4 | 121.2 | 123 | 124.8 | 126.6 | 128.4 | 130.2 | 132 | 133.8 | 135.6 | 137.4 | 139.2 | 141 | 142.8 | 144.6 | 146.4 | 148.2 | 150 | 151.8 | 153.6 | 155.4 | 157.2 | 159 | 160.8 | 162.6 | 164.4 | 166.2 | 168 | 169.8 | 171.6 | 173.4 | 175.2 | 177 | 178.8 | 180.6 | 182.4 | 184.2 | 186 | 187.8 | 189.6 | 191.4 | 193.2 | 195 | 196.8 | 198.6 | 200.4 | 202.2 | 204 | 205.8 | 207.6 | 209.4 | 211.2 | 213 | 214.8 | 216.6 | 218.4 | 220.2 | 222 | 223.8 | 225.6 | 227.4 | 229.2 | 231 | 232.8 | 234.6 | 236.4 | 238.2 | 239.999 | 0 | 0.00019457 | 0.00053381 | 0.00095095 | 0.0014193 | 0.0019221 | 0.0024478 | 0.0029871 | 0.0035331 | 0.0040799 | 0.0046226 | 0.0051573 | 0.0056804 | 0.0061892 | 0.0066811 | 0.0071541 | 0.0076064 | 0.0080365 | 0.0084433 | 0.0088256 | 0.0091828 | 0.0095141 | 0.0098192 | 0.010098 | 0.010349 | 0.010574 | 0.010772 | 0.010944 | 0.011089 | 0.011208 | 0.011301 | 0.01137 | 0.011413 | 0.011433 | 0.011429 | 0.011403 | 0.011354 | 0.011285 | 0.011195 | 0.011085 | 0.010957 | 0.010812 | 0.010649 | 0.010471 | 0.010278 | 0.010071 | 0.0098509 | 0.0096191 | 0.0093763 | 0.0091236 | 0.0088619 | 0.0085922 | 0.0083155 | 0.0080328 | 0.007745 | 0.0074532 | 0.0071581 | 0.0068608 | 0.0065622 | 0.0062631 | 0.0059644 | 0.0056669 | 0.0053715 | 0.005079 | 0.00479 | 0.0045054 | 0.0042258 | 0.003952 | 0.0036845 | 0.0034239 | 0.0031708 | 0.0029258 | 0.0026893 | 0.0024617 | 0.0022435 | 0.002035 | 0.0018366 | 0.0016485 | 0.0014709 | 0.0013039 | 0.0011478 | 0.0010026 | 0.00086836 | 0.00074494 | 0.00063232 | 0.00053035 | 0.00043882 | 0.00035749 | 0.00028604 | 0.00022409 | 0.00017121 | 0.0001269 | 9.0596e-05 | 6.1685e-05 | 3.9473e-05 | 2.3209e-05 | 1.2071e-05 | 5.1723e-06 | 1.5563e-06 | 1.9752e-07 | 3.4383e-17
7 | 60 | 120 | 240 | 1 | 33.3333 | R | Slight skew | 3 | 150 | Medium-Low Confidence | 7 | 2 | 3 |  | 132 | 36 | 1296 | 150 | 68.75% | 77.5701 | 195.2512 | 85.6607 | 98.2171 | 109.0291 | 119.25 | 129.431 | 140.01 | 151.5129 | 164.8416 | 182.3171 | 214.6438 | 1.8 | 60 | 61.8 | 63.6 | 65.4 | 67.2 | 69 | 70.8 | 72.6 | 74.4 | 76.2 | 78 | 79.8 | 81.6 | 83.4 | 85.2 | 87 | 88.8 | 90.6 | 92.4 | 94.2 | 96 | 97.8 | 99.6 | 101.4 | 103.2 | 105 | 106.8 | 108.6 | 110.4 | 112.2 | 114 | 115.8 | 117.6 | 119.4 | 121.2 | 123 | 124.8 | 126.6 | 128.4 | 130.2 | 132 | 133.8 | 135.6 | 137.4 | 139.2 | 141 | 142.8 | 144.6 | 146.4 | 148.2 | 150 | 151.8 | 153.6 | 155.4 | 157.2 | 159 | 160.8 | 162.6 | 164.4 | 166.2 | 168 | 169.8 | 171.6 | 173.4 | 175.2 | 177 | 178.8 | 180.6 | 182.4 | 184.2 | 186 | 187.8 | 189.6 | 191.4 | 193.2 | 195 | 196.8 | 198.6 | 200.4 | 202.2 | 204 | 205.8 | 207.6 | 209.4 | 211.2 | 213 | 214.8 | 216.6 | 218.4 | 220.2 | 222 | 223.8 | 225.6 | 227.4 | 229.2 | 231 | 232.8 | 234.6 | 236.4 | 238.2 | 239.999 | 0 | 0.0006534 | 0.0012805 | 0.0018818 | 0.0024576 | 0.0030083 | 0.0035344 | 0.0040362 | 0.0045141 | 0.0049686 | 0.0054 | 0.0058087 | 0.0061952 | 0.0065598 | 0.0069029 | 0.007225 | 0.0075264 | 0.0078075 | 0.0080688 | 0.0083106 | 0.0085333 | 0.0087374 | 0.0089232 | 0.0090911 | 0.0092416 | 0.009375 | 0.0094917 | 0.0095922 | 0.0096768 | 0.0097459 | 0.0098 | 0.0098394 | 0.0098645 | 0.0098758 | 0.0098736 | 0.0098583 | 0.0098304 | 0.0097902 | 0.0097381 | 0.0096746 | 0.0096 | 0.0095147 | 0.0094192 | 0.0093138 | 0.0091989 | 0.009075 | 0.0089424 | 0.0088015 | 0.0086528 | 0.0084966 | 0.0083333 | 0.0081634 | 0.0079872 | 0.0078051 | 0.0076176 | 0.007425 | 0.0072277 | 0.0070262 | 0.0068208 | 0.0066119 | 0.0064 | 0.0061854 | 0.0059685 | 0.0057498 | 0.0055296 | 0.0053083 | 0.0050864 | 0.0048642 | 0.0046421 | 0.0044206 | 0.0042 | 0.0039807 | 0.0037632 | 0.0035478 | 0.0033349 | 0.003125 | 0.0029184 | 0.0027155 | 0.0025168 | 0.0023226 | 0.0021333 | 0.0019494 | 0.0017712 | 0.0015991 | 0.0014336 | 0.001275 | 0.0011237 | 0.0009802 | 0.0008448 | 0.00071793 | 0.0006 | 0.0004914 | 0.00039253 | 0.0003038 | 0.0002256 | 0.00015833 | 0.0001024 | 5.82e-05 | 2.6133e-05 | 6.6e-06 | 2.0576e-12
8 | 60 | 120 | 240 | 1 | 33.3333 | R | Slight skew | 3 | 150 | Low Confidence | 8 | 1.5 | 2 |  | 137.13 | 41.994 | 1763.496 | 150 | 61.87% | 73.6817 | 209.715 | 82.1579 | 96.4322 | 109.3686 | 121.8833 | 134.4529 | 147.476 | 161.4358 | 177.1411 | 196.5547 | 226.6872 | 1.8 | 60 | 61.8 | 63.6 | 65.4 | 67.2 | 69 | 70.8 | 72.6 | 74.4 | 76.2 | 78 | 79.8 | 81.6 | 83.4 | 85.2 | 87 | 88.8 | 90.6 | 92.4 | 94.2 | 96 | 97.8 | 99.6 | 101.4 | 103.2 | 105 | 106.8 | 108.6 | 110.4 | 112.2 | 114 | 115.8 | 117.6 | 119.4 | 121.2 | 123 | 124.8 | 126.6 | 128.4 | 130.2 | 132 | 133.8 | 135.6 | 137.4 | 139.2 | 141 | 142.8 | 144.6 | 146.4 | 148.2 | 150 | 151.8 | 153.6 | 155.4 | 157.2 | 159 | 160.8 | 162.6 | 164.4 | 166.2 | 168 | 169.8 | 171.6 | 173.4 | 175.2 | 177 | 178.8 | 180.6 | 182.4 | 184.2 | 186 | 187.8 | 189.6 | 191.4 | 193.2 | 195 | 196.8 | 198.6 | 200.4 | 202.2 | 204 | 205.8 | 207.6 | 209.4 | 211.2 | 213 | 214.8 | 216.6 | 218.4 | 220.2 | 222 | 223.8 | 225.6 | 227.4 | 229.2 | 231 | 232.8 | 234.6 | 236.4 | 238.2 | 239.999 | 0 | 0.0020625 | 0.0028874 | 0.0035002 | 0.004 | 0.0044256 | 0.0047969 | 0.0051261 | 0.0054212 | 0.0056875 | 0.0059293 | 0.0061496 | 0.0063509 | 0.0065351 | 0.0067038 | 0.0068584 | 0.007 | 0.0071295 | 0.0072478 | 0.0073556 | 0.0074536 | 0.0075422 | 0.0076219 | 0.0076933 | 0.0077567 | 0.0078125 | 0.007861 | 0.0079025 | 0.0079373 | 0.0079656 | 0.0079876 | 0.0080037 | 0.0080139 | 0.0080185 | 0.0080176 | 0.0080114 | 0.008 | 0.0079836 | 0.0079624 | 0.0079364 | 0.0079057 | 0.0078705 | 0.0078309 | 0.007787 | 0.0077388 | 0.0076865 | 0.0076301 | 0.0075698 | 0.0075056 | 0.0074375 | 0.0073657 | 0.0072902 | 0.0072111 | 0.0071284 | 0.0070423 | 0.0069527 | 0.0068597 | 0.0067634 | 0.0066638 | 0.006561 | 0.006455 | 0.0063458 | 0.0062336 | 0.0061183 | 0.006 | 0.0058787 | 0.0057545 | 0.0056274 | 0.0054975 | 0.0053647 | 0.0052291 | 0.0050908 | 0.0049497 | 0.004806 | 0.0046596 | 0.0045105 | 0.0043589 | 0.0042047 | 0.0040479 | 0.0038886 | 0.0037268 | 0.0035625 | 0.0033958 | 0.0032266 | 0.0030551 | 0.0028811 | 0.0027048 | 0.0025262 | 0.0023452 | 0.002162 | 0.0019764 | 0.0017886 | 0.0015986 | 0.0014064 | 0.0012119 | 0.0010153 | 0.0008165 | 0.00061555 | 0.00041248 | 0.00020729 | 1.1574e-07
9 | 60 | 120 | 240 | 1 | 33.3333 | R | Slight skew | 3 | 150 | Very Low Confidence | 9 | 1.25 | 1.5 |  | 141.81 | 46.278 | 2141.6533 | 150 | 56.97% | 71.4025 | 219.6097 | 80.0792 | 95.7161 | 110.4737 | 124.9819 | 139.5921 | 154.6077 | 170.3944 | 187.5413 | 207.3867 | 233.0815 | 1.8 | 60 | 61.8 | 63.6 | 65.4 | 67.2 | 69 | 70.8 | 72.6 | 74.4 | 76.2 | 78 | 79.8 | 81.6 | 83.4 | 85.2 | 87 | 88.8 | 90.6 | 92.4 | 94.2 | 96 | 97.8 | 99.6 | 101.4 | 103.2 | 105 | 106.8 | 108.6 | 110.4 | 112.2 | 114 | 115.8 | 117.6 | 119.4 | 121.2 | 123 | 124.8 | 126.6 | 128.4 | 130.2 | 132 | 133.8 | 135.6 | 137.4 | 139.2 | 141 | 142.8 | 144.6 | 146.4 | 148.2 | 150 | 151.8 | 153.6 | 155.4 | 157.2 | 159 | 160.8 | 162.6 | 164.4 | 166.2 | 168 | 169.8 | 171.6 | 173.4 | 175.2 | 177 | 178.8 | 180.6 | 182.4 | 184.2 | 186 | 187.8 | 189.6 | 191.4 | 193.2 | 195 | 196.8 | 198.6 | 200.4 | 202.2 | 204 | 205.8 | 207.6 | 209.4 | 211.2 | 213 | 214.8 | 216.6 | 218.4 | 220.2 | 222 | 223.8 | 225.6 | 227.4 | 229.2 | 231 | 232.8 | 234.6 | 236.4 | 238.2 | 239.999 | 0 | 0.0035 | 0.0041411 | 0.0045594 | 0.0048741 | 0.0051268 | 0.0053376 | 0.0055177 | 0.0056743 | 0.005812 | 0.0059342 | 0.0060435 | 0.0061416 | 0.00623 | 0.0063099 | 0.0063823 | 0.0064478 | 0.0065072 | 0.006561 | 0.0066096 | 0.0066535 | 0.0066929 | 0.0067282 | 0.0067596 | 0.0067874 | 0.0068118 | 0.0068329 | 0.0068509 | 0.0068659 | 0.0068782 | 0.0068877 | 0.0068946 | 0.006899 | 0.006901 | 0.0069006 | 0.0068979 | 0.006893 | 0.006886 | 0.0068768 | 0.0068656 | 0.0068523 | 0.006837 | 0.0068198 | 0.0068006 | 0.0067796 | 0.0067566 | 0.0067318 | 0.0067051 | 0.0066766 | 0.0066463 | 0.0066141 | 0.0065801 | 0.0065443 | 0.0065067 | 0.0064673 | 0.006426 | 0.0063829 | 0.0063379 | 0.0062911 | 0.0062424 | 0.0061917 | 0.0061392 | 0.0060846 | 0.0060281 | 0.0059695 | 0.0059089 | 0.0058462 | 0.0057812 | 0.0057141 | 0.0056447 | 0.0055729 | 0.0054987 | 0.005422 | 0.0053427 | 0.0052606 | 0.0051758 | 0.0050881 | 0.0049973 | 0.0049032 | 0.0048057 | 0.0047047 | 0.0045998 | 0.0044909 | 0.0043776 | 0.0042597 | 0.0041366 | 0.0040081 | 0.0038734 | 0.0037321 | 0.0035833 | 0.0034261 | 0.0032593 | 0.0030813 | 0.0028901 | 0.0026829 | 0.0024556 | 0.0022021 | 0.001912 | 0.0015652 | 0.0011096 | 2.6218e-05
10 | 60 | 120 | 240 | 1 | 33.3333 | R | Slight skew | 3 | 150 | Guesstimate | 10 | 1.125 | 1.25 |  | 145.248 | 48.924 | 2393.5578 | 150 | 53.85% | 70.2008 | 225.2332 | 79.0044 | 95.618 | 111.7167 | 127.6854 | 143.7491 | 160.1047 | 176.9863 | 194.7569 | 214.1945 | 235.9391 | 1.8 | 60 | 61.8 | 63.6 | 65.4 | 67.2 | 69 | 70.8 | 72.6 | 74.4 | 76.2 | 78 | 79.8 | 81.6 | 83.4 | 85.2 | 87 | 88.8 | 90.6 | 92.4 | 94.2 | 96 | 97.8 | 99.6 | 101.4 | 103.2 | 105 | 106.8 | 108.6 | 110.4 | 112.2 | 114 | 115.8 | 117.6 | 119.4 | 121.2 | 123 | 124.8 | 126.6 | 128.4 | 130.2 | 132 | 133.8 | 135.6 | 137.4 | 139.2 | 141 | 142.8 | 144.6 | 146.4 | 148.2 | 150 | 151.8 | 153.6 | 155.4 | 157.2 | 159 | 160.8 | 162.6 | 164.4 | 166.2 | 168 | 169.8 | 171.6 | 173.4 | 175.2 | 177 | 178.8 | 180.6 | 182.4 | 184.2 | 186 | 187.8 | 189.6 | 191.4 | 193.2 | 195 | 196.8 | 198.6 | 200.4 | 202.2 | 204 | 205.8 | 207.6 | 209.4 | 211.2 | 213 | 214.8 | 216.6 | 218.4 | 220.2 | 222 | 223.8 | 225.6 | 227.4 | 229.2 | 231 | 232.8 | 234.6 | 236.4 | 238.2 | 239.999 | 0 | 0.0044622 | 0.0048537 | 0.005093 | 0.0052658 | 0.0054006 | 0.0055105 | 0.0056027 | 0.0056816 | 0.0057501 | 0.0058103 | 0.0058635 | 0.0059109 | 0.0059533 | 0.0059914 | 0.0060256 | 0.0060565 | 0.0060843 | 0.0061094 | 0.006132 | 0.0061523 | 0.0061705 | 0.0061868 | 0.0062012 | 0.0062139 | 0.0062251 | 0.0062347 | 0.0062429 | 0.0062498 | 0.0062553 | 0.0062597 | 0.0062628 | 0.0062648 | 0.0062657 | 0.0062655 | 0.0062643 | 0.0062621 | 0.0062589 | 0.0062547 | 0.0062496 | 0.0062436 | 0.0062366 | 0.0062287 | 0.00622 | 0.0062103 | 0.0061998 | 0.0061884 | 0.0061761 | 0.006163 | 0.006149 | 0.0061341 | 0.0061183 | 0.0061016 | 0.0060841 | 0.0060656 | 0.0060462 | 0.0060259 | 0.0060047 | 0.0059824 | 0.0059592 | 0.005935 | 0.0059097 | 0.0058834 | 0.005856 | 0.0058275 | 0.0057979 | 0.005767 | 0.0057349 | 0.0057015 | 0.0056667 | 0.0056306 | 0.005593 | 0.0055538 | 0.0055131 | 0.0054706 | 0.0054263 | 0.0053801 | 0.0053319 | 0.0052815 | 0.0052287 | 0.0051734 | 0.0051155 | 0.0050545 | 0.0049904 | 0.0049227 | 0.0048511 | 0.0047751 | 0.0046942 | 0.0046078 | 0.004515 | 0.0044149 | 0.004306 | 0.0041868 | 0.0040548 | 0.0039067 | 0.0037376 | 0.0035394 | 0.0032981 | 0.002984 | 0.0025124 | 0.00038621
11 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
12 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
13 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
14 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
15 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
16 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
17 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
18 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
19 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
20 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
23 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
24 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
25 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
26 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
27 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
28 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
29 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
30 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
31 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
32 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
33 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
34 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
35 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
36 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
37 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
38 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
39 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
40 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
41 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
42 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
43 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
44 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
45 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
46 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
47 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
48 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
49 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
50 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
51 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
52 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
53 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
54 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
55 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
56 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
57 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
58 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
59 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
60 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
61 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
62 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
63 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
64 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
65 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
66 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
67 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
68 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
69 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
70 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
71 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
72 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
73 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
74 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
75 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
76 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
77 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
78 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
79 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
80 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
81 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
82 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
83 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
84 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
85 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
86 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
87 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
88 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
89 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
90 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
91 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
92 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
93 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
94 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
95 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
96 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
97 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
98 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
99 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
100 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| 600 | 1200 | 2400 | [6 empty] | © 2015-2020, William W. Davis, MSPM, PMP |  |  |  |  | 1306.41 | 105.0173 | 11028.6409 | 1500 | 96.74% | 829.8207 | 1841.5481 | 901.3495 | 1012.2719 | 1108.2563 | 1199.1037 | 1289.2662 | 1382.1377 | 1481.6775 | 1594.5917 | 1738.1817 | 1995.9952 | 991.358 | 997.5966 | 1003.8353 | 1010.074 | 1016.3126 | 1022.5513 | 1028.7899 | 1035.0286 | 1041.2672 | 1047.5059 | 1053.7445 | 1059.9832 | 1066.2218 | 1072.4605 | 1078.6991 | 1084.9378 | 1091.1764 | 1097.4151 | 1103.6538 | 1109.8924 | 1116.1311 | 1122.3697 | 1128.6084 | 1134.847 | 1141.0857 | 1147.3243 | 1153.563 | 1159.8016 | 1166.0403 | 1172.2789 | 1178.5176 | 1184.7563 | 1190.9949 | 1197.2336 | 1203.4722 | 1209.7109 | 1215.9495 | 1222.1882 | 1228.4268 | 1234.6655 | 1240.9041 | 1247.1428 | 1253.3814 | 1259.6201 | 1265.8588 | 1272.0974 | 1278.3361 | 1284.5747 | 1290.8134 | 1297.052 | 1303.2907 | 1309.5293 | 1315.768 | 1322.0066 | 1328.2453 | 1334.4839 | 1340.7226 | 1346.9612 | 1353.1999 | 1359.4386 | 1365.6772 | 1371.9159 | 1378.1545 | 1384.3932 | 1390.6318 | 1396.8705 | 1403.1091 | 1409.3478 | 1415.5864 | 1421.8251 | 1428.0637 | 1434.3024 | 1440.5411 | 1446.7797 | 1453.0184 | 1459.257 | 1465.4957 | 1471.7343 | 1477.973 | 1484.2116 | 1490.4503 | 1496.6889 | 1502.9276 | 1509.1662 | 1515.4049 | 1521.6436 | 1527.8822 | 1534.1209 | 1540.3595 | 1546.5982 | 1552.8368 | 1559.0755 | 1565.3141 | 1571.5528 | 1577.7914 | 1584.0301 | 1590.2687 | 1596.5074 | 1602.746 | 1608.9847 | 1615.2234 | 1621.462 | 5.0345e-05 | 5.9849e-05 | 7.0896e-05 | 8.3687e-05 | 9.8438e-05 | 0.00011538 | 0.00013476 | 0.00015685 | 0.0001819 | 0.00021022 | 0.0002421 | 0.00027782 | 0.00031769 | 0.000362 | 0.00041104 | 0.00046508 | 0.00052437 | 0.00058914 | 0.00065957 | 0.00073582 | 0.000818 | 0.00090615 | 0.0010003 | 0.0011003 | 0.001206 | 0.0013172 | 0.0014337 | 0.0015549 | 0.0016804 | 0.0018097 | 0.001942 | 0.0020767 | 0.0022129 | 0.0023497 | 0.0024862 | 0.0026214 | 0.0027541 | 0.0028834 | 0.0030082 | 0.0031272 | 0.0032396 | 0.0033441 | 0.0034399 | 0.0035259 | 0.0036014 | 0.0036655 | 0.0037176 | 0.0037572 | 0.0037838 | 0.0037971 | 0.0037971 | 0.0037838 | 0.0037572 | 0.0037176 | 0.0036655 | 0.0036014 | 0.0035259 | 0.0034399 | 0.0033441 | 0.0032396 | 0.0031272 | 0.0030082 | 0.0028834 | 0.0027541 | 0.0026214 | 0.0024862 | 0.0023497 | 0.0022129 | 0.0020767 | 0.001942 | 0.0018097 | 0.0016804 | 0.0015549 | 0.0014337 | 0.0013172 | 0.001206 | 0.0011003 | 0.0010003 | 0.00090615 | 0.000818 | 0.00073582 | 0.00065957 | 0.00058914 | 0.00052437 | 0.00046508 | 0.00041104 | 0.000362 | 0.00031769 | 0.00027782 | 0.0002421 | 0.00021022 | 0.0001819 | 0.00015685 | 0.00013476 | 0.00011538 | 9.8438e-05 | 8.3687e-05 | 7.0896e-05 | 5.9849e-05 | 5.0345e-05 | 4.2201e-05
| Do not show currency formatting | [14 empty] | Whole project or portfolio planning estimate |  | 1500 | 96.74% | 1133.6719 | 1479.1481 | 1171.8249 | 1218.0252 | 1251.3389 | 1279.8042 | 1306.41 | 1333.0158 | 1361.4811 | 1394.7948 | 1440.9951 | 1550.7169 | [102 empty] | 5.0345e-05 | 5.9849e-05 | 7.0896e-05 | 8.3687e-05 | 9.8438e-05 | 0.00011538 | 0.00013476 | 0.00015685 | 0.0001819 | 0.00021022 | 0.0002421 | 0.00027782 | 0.00031769 | 0.000362 | 0.00041104 | 0.00046508 | 0.00052437 | 0.00058914 | 0.00065957 | 0.00073582 | 0.000818 | 0.00090615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[134 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0010003 | 0.0011003 | 0.001206 | 0.0013172 | 0.0014337 | 0.0015549 | 0.0016804 | 0.0018097 | 0.001942 | 0.0020767 | 0.0022129 | 0.0023497 | 0.0024862 | 0.0026214 | 0.0027541 | 0.0028834 | 0.0030082 | 0.0031272 | 0.0032396 | 0.0033441 | 0.0034399 | 0.0035259 | 0.0036014 | 0.0036655 | 0.0037176 | 0.0037572 | 0.0037838 | 0.0037971 | 0.0037971 | 0.0037838 | 0.0037572 | 0.0037176 | 0.0036655 | 0.0036014 | 0.0035259 | 0.0034399 | 0.0033441 | 0.0032396 | 0.0031272 | 0.0030082 | 0.0028834 | 0.0027541 | 0.0026214 | 0.0024862 | 0.0023497 | 0.0022129 | 0.0020767 | 0.001942 | 0.0018097 | 0.0016804 | 0.0015549 | 0.0014337 | 0.0013172 | 0.001206 | 0.0011003 | 0.0010003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | With | 90% | confidence | [129 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00090615 | 0.000818 | 0.00073582 | 0.00065957 | 0.00058914 | 0.00052437 | 0.00046508 | 0.00041104 | 0.000362 | 0.00031769 | 0.00027782 | 0.0002421 | 0.00021022 | 0.0001819 | 0.00015685 | 0.00013476 | 0.00011538 | 9.8438e-05 | 8.3687e-05 | 7.0896e-05 | 5.9849e-05 | 5.0345e-05 | 4.2201e-05
|  | The lowerbound threshold is | 1133.6719 | [130 empty] | 5.0345e-05 | 5.9849e-05 | 7.0896e-05 | 8.3687e-05 | 9.8438e-05 | 0.00011538 | 0.00013476 | 0.00015685 | 0.0001819 | 0.00021022 | 0.0002421 | 0.00027782 | 0.00031769 | 0.000362 | 0.00041104 | 0.00046508 | 0.00052437 | 0.00058914 | 0.00065957 | 0.00073582 | 0.000818 | 0.00090615 | 0.0010003 | 0.0011003 | 0.001206 | 0.0013172 | 0.0014337 | 0.0015549 | 0.0016804 | 0.0018097 | 0.001942 | 0.0020767 | 0.0022129 | 0.0023497 | 0.0024862 | 0.0026214 | 0.0027541 | 0.0028834 | 0.0030082 | 0.0031272 | 0.0032396 | 0.0033441 | 0.0034399 | 0.0035259 | 0.0036014 | 0.0036655 | 0.0037176 | 0.0037572 | 0.0037838 | 0.0037971 | 0.0037971 | 0.0037838 | 0.0037572 | 0.0037176 | 0.0036655 | 0.0036014 | 0.0035259 | 0.0034399 | 0.0033441 | 0.0032396 | 0.0031272 | 0.0030082 | 0.0028834 | 0.0027541 | 0.0026214 | 0.0024862 | 0.0023497 | 0.0022129 | 0.0020767 | 0.001942 | 0.0018097 | 0.0016804 | 0.0015549 | 0.0014337 | 0.0013172 | 0.001206 | 0.0011003 | 0.0010003 | 0.00090615 | 0.000818 | 0.00073582 | 0.00065957 | 0.00058914 | 0.00052437 | 0.00046508 | 0.00041104 | 0.000362 | 0.00031769 | 0.00027782 | 0.0002421 | 0.00021022 | 0.0001819 | 0.00015685 | 0.00013476 | 0.00011538 | 9.8438e-05 | 8.3687e-05 | 7.0896e-05 | 5.9849e-05 | 5.0345e-05 | 4.2201e-05
|  | and the upperbound threshold is | 1479.1481
|  | Between a lowerbound value of | 1134
|  | and an upperbound value of | 1479
|  | the range probability is | 89.95%
|  | where, below the lowerbound, the % is | 5.032%
|  | and above the upperbound, the % is | 5.015%
To use this template:
1) Create a 3-point estimate under the Minimum, Most Likely, and Maximum columns
2) Render a subjective judgment about how likely the Most Likely outcome is, under the Most Likely Confidence column
3) Examine the SPERT probabilistic estimates for various confidence levels
Optionally:
Enter any desired estimate under the Planning Estimate column to find the SPERT probability for the planning estimate
Version 3.0.s – © 2015-2020, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Subscribe to the SPERT® newsletter for monthly tips, free webinars, and new release notifications
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).
Note on S2: You may optionally enter a planning estimate for each uncertainty you enter, and see its cumulative probability result in the 'SPERT Probability' column. The cumulative probability is the likelihood your planning estimate will be EQUAL TO or GREATER THAN the uncertainty you are estimating. Choosing a larger planning estimate will increase the cumulative probability, and choosing a smaller planning estimate will decrease the cumulative probability.
Note on T2: The SPERT Probability shows the cumulative probability of each Planning Estimate you entered in column R. If you select 'Show Left-Side Area' in cell R1, this column shows the likelihood that your Planning Estimate will be EQUAL TO or GREATER THAN the uncertainty you are estimating. If you select 'Show Right-Side Area' in cell R1, this column shows the likelihood that the uncertainty will EXCEED your Planning Estimate in column R.
Note on B3: Use a simple heuristic to quickly create MINIMUM point-estimates. Do this by selecting a percentage in cell B2. Minimum point-estimates are automatically created for you by taking the Most Likely point-estimate in column C and reducing it by the percentage value specified in cell B2. If you want, overwrite any cell formula in column B to manually enter a non-calculated, minimum value for a particular three-point estimate. (If you need to modify the dropdown choices in cell B2, you can do that in the Vlookups worksheet).
Note on C3: The Most Likely point-estimate represents the value you believe will most likely occur for each uncertainty, although many other possible outcomes exist between the Minimum and Maximum point-estimates.
Note on D3: Use a simple heuristic to quickly create MAXIMUM point-estimates. Do this by selecting a percentage in cell D2. Maximum point-estimates are automatically created for you by taking the Most Likely point-estimate in column C and increasing it by the percentage value specified in cell D2. If you want, overwrite any cell formula in column D to manually enter a non-calculated, maximum value for a particular three-point estimate. (If you need to modify the dropdown choices in cell D2, you can do that in the Vlookups worksheet).
Note on E3: This checks that a proper 3-point estimate was entered: Minimum value must be > 0 and < Most Likely Most Likely must be > Minimum and < Maximum Maximum must be > Most Likely
Note on K3: The shape of the bell-curve is heavily influenced by how confident you believe the Most Likely outcome will occur relative to other, possible outcomes between the Minimum and Maximum point-estimates. When you are more confident in the Most Likely outcome, the bell-curve grows taller, and there is a shrinking likelihood of other occurrences near the Minimum and Maximum point-estimates. Conversely, when you are less confident in the Most Likely outcome, the bell-curve grows flatter, and there is a rising likelihood of other occurrences near the Minimum and Maximum point-estimates. (You can add to, remove, or modify the dropdown control options using the VLookups worksheet).
Note on O3: William Davis: SPERT builds an implied, bell-shaped curve to represent the risk characteristics for your uncertainty. The flatter, wider the bell-curve curve is, the more uncertain the outcomes are over the feasible region. If the bell-curve's vertical rise is steep, though, your uncertainty has much less volatility near the most likely outcome. If the bell-curve is both centered and symmetrical, it fits a normal distribution. The beta distribution can also show skewed bell-curves, dependent on your 3-point estimate and how likely the most likely outcome really is.
After you finish entering your estimates above, use this area to calculate the probability of all uncertainties together. This is especially useful for creating a forecast for an entire project, for example.
Choose the confidence you want for the confidence interval in cell D108, and/or choose the confidence lower and upperbound thresholds in cells D112 and D113.
Both the pie chart and tri-colored, bell-curve combo chart below represent the uncertainty of summary row #104 and assume that the Central Limit Theorem applies to that row.
IMPORTANT DISCLOSURE!
The charts on this worksheet assume that the Central Limit Theorem applies to summary row #104, which may or may not be true.
Be sure to understand the Central Limit Theorem and validate that it applies to your estimated uncertainties in rows 4-103 before relying on the probabilities shown in row 106 or the the summary charts in this worksheet.
Click for help

## SPERT® Beta (3-Point entry)
| Statistical PERT® (SPERT®) Beta Edition 3-Point Entry | [16 empty] | Show Left-Side Area |  | Show the likelihood that the SPERT estimates will be EQUAL TO or GREATER THAN an uncertainty
[18 empty] | Planning Estimate | SPERT Probability | SPERT Probabilistic Estimates using the BETA distribution | [11 empty] | This section is only to build Line Sparklines to show the bell-shaped curve for each row, and the summary bell-curve chart.
ID | Minimum | Most Likely | Maximum |  | Range % | R/L Skew | Skew Analysis | X | Midpoint | Most Likely Confidence | Y | Alpha | Beta | Curve | Mean | SPERT SD | Variance |  |  | 5% | 95% | 10% | 20% | 30% | 40% | 50% | 60% | 70% | 80% | 90% | 99% | x-axis increments (magenta in blue cells shows the increment, the next 101 columns are the x-axis values for the Line Sparkline column and summary bell-curve chart) | [101 empty] | These are the y-axis values with which the bell-shaped curve is built (used only for the Line SparkLine column) | [100 empty] | ← Columns AH through IB are hidden; they are used to create Sparklines and the bell-curve bar chart
1 | 60 | 120 | 240 | 1 | 33.3333 | R | Slight skew | 3 | 150 | Near Certainty | 1 | 13 | 25 |  | 121.578 | 13.68 | 187.1424 | 150 | 97.65% | 99.9436 | 144.9375 | 104.2664 | 109.7826 | 113.9344 | 117.5855 | 121.0755 | 124.6317 | 128.4997 | 133.0949 | 139.5564 | 155.0347 | 1.8 | 60 | 61.8 | 63.6 | 65.4 | 67.2 | 69 | 70.8 | 72.6 | 74.4 | 76.2 | 78 | 79.8 | 81.6 | 83.4 | 85.2 | 87 | 88.8 | 90.6 | 92.4 | 94.2 | 96 | 97.8 | 99.6 | 101.4 | 103.2 | 105 | 106.8 | 108.6 | 110.4 | 112.2 | 114 | 115.8 | 117.6 | 119.4 | 121.2 | 123 | 124.8 | 126.6 | 128.4 | 130.2 | 132 | 133.8 | 135.6 | 137.4 | 139.2 | 141 | 142.8 | 144.6 | 146.4 | 148.2 | 150 | 151.8 | 153.6 | 155.4 | 157.2 | 159 | 160.8 | 162.6 | 164.4 | 166.2 | 168 | 169.8 | 171.6 | 173.4 | 175.2 | 177 | 178.8 | 180.6 | 182.4 | 184.2 | 186 | 187.8 | 189.6 | 191.4 | 193.2 | 195 | 196.8 | 198.6 | 200.4 | 202.2 | 204 | 205.8 | 207.6 | 209.4 | 211.2 | 213 | 214.8 | 216.6 | 218.4 | 220.2 | 222 | 223.8 | 225.6 | 227.4 | 229.2 | 231 | 232.8 | 234.6 | 236.4 | 238.2 | 239.999 | 0 | 2.0215e-16 | 6.4894e-13 | 6.5826e-11 | 1.6205e-09 | 1.8341e-08 | 1.2685e-07 | 6.2401e-07 | 2.3901e-06 | 7.5566e-06 | 2.0523e-05 | 4.926e-05 | 0.0001067 | 0.00021194 | 0.00039077 | 0.00067542 | 0.001103 | 0.0017127 | 0.0025423 | 0.0036233 | 0.0049767 | 0.0066085 | 0.0085068 | 0.01064 | 0.012956 | 0.015388 | 0.017851 | 0.020255 | 0.022506 | 0.024513 | 0.026196 | 0.027488 | 0.028342 | 0.028733 | 0.028657 | 0.028129 | 0.027188 | 0.025883 | 0.024279 | 0.022445 | 0.020454 | 0.018377 | 0.016281 | 0.014225 | 0.012257 | 0.010415 | 0.008729 | 0.0072147 | 0.0058803 | 0.0047256 | 0.0037441 | 0.0029239 | 0.0022504 | 0.0017064 | 0.0012745 | 0.00093729 | 0.00067849 | 0.00048324 | 0.00033849 | 0.00023306 | 0.00015764 | 0.0001047 | 6.8223e-05 | 4.3586e-05 | 2.728e-05 | 1.6711e-05 | 1.001e-05 | 5.8567e-06 | 3.3429e-06 | 1.8591e-06 | 1.0058e-06 | 5.2854e-07 | 2.6928e-07 | 1.3275e-07 | 6.3178e-08 | 2.8955e-08 | 1.2743e-08 | 5.3676e-09 | 2.1563e-09 | 8.2264e-10 | 2.9663e-10 | 1.0054e-10 | 3.1822e-11 | 9.3354e-12 | 2.5157e-12 | 6.1608e-13 | 1.3536e-13 | 2.626e-14 | 4.4113e-15 | 6.2593e-16 | 7.2666e-17 | 6.6182e-18 | 4.4672e-19 | 2.0633e-20 | 5.8021e-22 | 8.2868e-24 | 4.4373e-26 | 5.0419e-29 | 3.3873e-33 | 2.2806e-40 | 1.9224e-118
2 | 60 | 120 | 240 | 1 | 33.3333 | R | Slight skew | 3 | 150 | Extremely High Confidence | 2 | 8 | 15 |  | 122.604 | 17.496 | 306.11 | 150 | 93.31% | 95.2013 | 152.7822 | 100.47 | 107.3498 | 112.6172 | 117.2973 | 121.8021 | 126.4146 | 131.4471 | 137.4326 | 145.8314 | 165.6311 | 1.8 | 60 | 61.8 | 63.6 | 65.4 | 67.2 | 69 | 70.8 | 72.6 | 74.4 | 76.2 | 78 | 79.8 | 81.6 | 83.4 | 85.2 | 87 | 88.8 | 90.6 | 92.4 | 94.2 | 96 | 97.8 | 99.6 | 101.4 | 103.2 | 105 | 106.8 | 108.6 | 110.4 | 112.2 | 114 | 115.8 | 117.6 | 119.4 | 121.2 | 123 | 124.8 | 126.6 | 128.4 | 130.2 | 132 | 133.8 | 135.6 | 137.4 | 139.2 | 141 | 142.8 | 144.6 | 146.4 | 148.2 | 150 | 151.8 | 153.6 | 155.4 | 157.2 | 159 | 160.8 | 162.6 | 164.4 | 166.2 | 168 | 169.8 | 171.6 | 173.4 | 175.2 | 177 | 178.8 | 180.6 | 182.4 | 184.2 | 186 | 187.8 | 189.6 | 191.4 | 193.2 | 195 | 196.8 | 198.6 | 200.4 | 202.2 | 204 | 205.8 | 207.6 | 209.4 | 211.2 | 213 | 214.8 | 216.6 | 218.4 | 220.2 | 222 | 223.8 | 225.6 | 227.4 | 229.2 | 231 | 232.8 | 234.6 | 236.4 | 238.2 | 239.999 | 0 | 1.2347e-10 | 1.371e-08 | 2.0291e-07 | 1.3148e-06 | 5.4147e-06 | 1.673e-05 | 4.2374e-05 | 9.275e-05 | 0.00018152 | 0.00032512 | 0.00054183 | 0.00085051 | 0.0012692 | 0.0018136 | 0.0024955 | 0.003322 | 0.0042943 | 0.005407 | 0.0066485 | 0.0080006 | 0.0094399 | 0.010938 | 0.012463 | 0.013981 | 0.015456 | 0.016854 | 0.018144 | 0.019294 | 0.02028 | 0.02108 | 0.021681 | 0.022071 | 0.022248 | 0.022214 | 0.021974 | 0.021542 | 0.020933 | 0.020166 | 0.019263 | 0.018247 | 0.017142 | 0.015973 | 0.014763 | 0.013535 | 0.012309 | 0.011104 | 0.0099358 | 0.0088184 | 0.0077627 | 0.0067768 | 0.0058667 | 0.0050357 | 0.0042851 | 0.0036143 | 0.0030211 | 0.0025021 | 0.0020528 | 0.0016678 | 0.0013415 | 0.001068 | 0.00084114 | 0.00065519 | 0.0005045 | 0.00038384 | 0.0002884 | 0.00021388 | 0.00015645 | 0.0001128 | 8.0106e-05 | 5.5981e-05 | 3.8462e-05 | 2.5953e-05 | 1.7179e-05 | 1.114e-05 | 7.0671e-06 | 4.3783e-06 | 2.6441e-06 | 1.5532e-06 | 8.8535e-07 | 4.8832e-07 | 2.5978e-07 | 1.3279e-07 | 6.4936e-08 | 3.022e-08 | 1.33e-08 | 5.4946e-09 | 2.111e-09 | 7.4571e-10 | 2.3872e-10 | 6.7976e-11 | 1.6801e-11 | 3.4868e-12 | 5.7997e-13 | 7.2222e-14 | 6.0576e-15 | 2.8668e-16 | 5.4923e-18 | 2.0214e-20 | 1.3247e-24 | 3.7916e-70
3 | 60 | 120 | 240 | 1 | 33.3333 | R | Slight skew | 3 | 150 | Very High Confidence | 3 | 5.5 | 10 |  | 123.864 | 21.204 | 449.6096 | 150 | 88.18% | 90.9719 | 160.7221 | 97.0364 | 105.1641 | 111.5052 | 117.2005 | 122.7207 | 128.3976 | 134.6044 | 141.9829 | 152.2843 | 175.9831 | 1.8 | 60 | 61.8 | 63.6 | 65.4 | 67.2 | 69 | 70.8 | 72.6 | 74.4 | 76.2 | 78 | 79.8 | 81.6 | 83.4 | 85.2 | 87 | 88.8 | 90.6 | 92.4 | 94.2 | 96 | 97.8 | 99.6 | 101.4 | 103.2 | 105 | 106.8 | 108.6 | 110.4 | 112.2 | 114 | 115.8 | 117.6 | 119.4 | 121.2 | 123 | 124.8 | 126.6 | 128.4 | 130.2 | 132 | 133.8 | 135.6 | 137.4 | 139.2 | 141 | 142.8 | 144.6 | 146.4 | 148.2 | 150 | 151.8 | 153.6 | 155.4 | 157.2 | 159 | 160.8 | 162.6 | 164.4 | 166.2 | 168 | 169.8 | 171.6 | 173.4 | 175.2 | 177 | 178.8 | 180.6 | 182.4 | 184.2 | 186 | 187.8 | 189.6 | 191.4 | 193.2 | 195 | 196.8 | 198.6 | 200.4 | 202.2 | 204 | 205.8 | 207.6 | 209.4 | 211.2 | 213 | 214.8 | 216.6 | 218.4 | 220.2 | 222 | 223.8 | 225.6 | 227.4 | 229.2 | 231 | 232.8 | 234.6 | 236.4 | 238.2 | 239.999 | 0 | 8.9466e-08 | 1.8476e-06 | 1.0446e-05 | 3.4726e-05 | 8.6262e-05 | 0.00017815 | 0.00032377 | 0.00053572 | 0.00082491 | 0.0011998 | 0.0016662 | 0.0022264 | 0.0028798 | 0.0036225 | 0.0044476 | 0.0053456 | 0.0063047 | 0.0073113 | 0.0083503 | 0.0094056 | 0.010461 | 0.0115 | 0.012506 | 0.013465 | 0.014362 | 0.015185 | 0.015922 | 0.016563 | 0.017102 | 0.017534 | 0.017853 | 0.018059 | 0.018152 | 0.018134 | 0.018008 | 0.01778 | 0.017455 | 0.017041 | 0.016546 | 0.01598 | 0.015351 | 0.01467 | 0.013945 | 0.013188 | 0.012407 | 0.011612 | 0.010811 | 0.010013 | 0.0092248 | 0.0084535 | 0.007705 | 0.0069844 | 0.006296 | 0.0056433 | 0.0050291 | 0.0044552 | 0.0039228 | 0.0034325 | 0.0029842 | 0.0025773 | 0.0022106 | 0.0018826 | 0.0015914 | 0.001335 | 0.0011109 | 0.00091665 | 0.00074973 | 0.00060755 | 0.00048755 | 0.00038724 | 0.00030422 | 0.00023624 | 0.0001812 | 0.00013717 | 0.00010237 | 7.525e-05 | 5.4413e-05 | 3.8652e-05 | 2.693e-05 | 1.837e-05 | 1.2244e-05 | 7.9535e-06 | 5.0215e-06 | 3.071e-06 | 1.812e-06 | 1.0265e-06 | 5.5497e-07 | 2.8428e-07 | 1.3669e-07 | 6.0959e-08 | 2.4821e-08 | 9.0323e-09 | 2.851e-09 | 7.471e-10 | 1.5186e-10 | 2.1365e-11 | 1.6808e-12 | 4.5786e-14 | 9.3606e-17 | 4.9372e-46
4 | 60 | 120 | 240 | 1 | 33.3333 | R | Slight skew | 3 | 150 | High Confidence | 4 | 4 | 7 |  | 125.448 | 25.002 | 625.1 | 150 | 82.81% | 87.0051 | 169.1924 | 93.7612 | 103.0994 | 110.5442 | 117.3113 | 123.918 | 130.7391 | 138.2049 | 147.0583 | 159.3115 | 186.519 | 1.8 | 60 | 61.8 | 63.6 | 65.4 | 67.2 | 69 | 70.8 | 72.6 | 74.4 | 76.2 | 78 | 79.8 | 81.6 | 83.4 | 85.2 | 87 | 88.8 | 90.6 | 92.4 | 94.2 | 96 | 97.8 | 99.6 | 101.4 | 103.2 | 105 | 106.8 | 108.6 | 110.4 | 112.2 | 114 | 115.8 | 117.6 | 119.4 | 121.2 | 123 | 124.8 | 126.6 | 128.4 | 130.2 | 132 | 133.8 | 135.6 | 137.4 | 139.2 | 141 | 142.8 | 144.6 | 146.4 | 148.2 | 150 | 151.8 | 153.6 | 155.4 | 157.2 | 159 | 160.8 | 162.6 | 164.4 | 166.2 | 168 | 169.8 | 171.6 | 173.4 | 175.2 | 177 | 178.8 | 180.6 | 182.4 | 184.2 | 186 | 187.8 | 189.6 | 191.4 | 193.2 | 195 | 196.8 | 198.6 | 200.4 | 202.2 | 204 | 205.8 | 207.6 | 209.4 | 211.2 | 213 | 214.8 | 216.6 | 218.4 | 220.2 | 222 | 223.8 | 225.6 | 227.4 | 229.2 | 231 | 232.8 | 234.6 | 236.4 | 238.2 | 239.999 | 0 | 4.3936e-06 | 3.3071e-05 | 0.00010495 | 0.00023378 | 0.0004288 | 0.00069539 | 0.0010356 | 0.0014488 | 0.0019319 | 0.0024801 | 0.0030869 | 0.003745 | 0.0044458 | 0.0051806 | 0.0059401 | 0.0067149 | 0.0074959 | 0.0082738 | 0.0090402 | 0.0097867 | 0.010506 | 0.01119 | 0.011834 | 0.012431 | 0.012978 | 0.013468 | 0.013901 | 0.014272 | 0.01458 | 0.014824 | 0.015003 | 0.015119 | 0.01517 | 0.01516 | 0.01509 | 0.014962 | 0.014779 | 0.014545 | 0.014262 | 0.013935 | 0.013567 | 0.013162 | 0.012725 | 0.01226 | 0.011771 | 0.011263 | 0.010739 | 0.010204 | 0.0096609 | 0.0091146 | 0.0085683 | 0.0080254 | 0.007489 | 0.006962 | 0.0064472 | 0.0059468 | 0.0054631 | 0.0049979 | 0.0045527 | 0.0041288 | 0.0037272 | 0.0033488 | 0.0029939 | 0.0026629 | 0.0023559 | 0.0020726 | 0.0018127 | 0.0015756 | 0.0013606 | 0.0011669 | 0.0009935 | 0.00083937 | 0.00070333 | 0.00058417 | 0.00048065 | 0.00039148 | 0.00031539 | 0.00025109 | 0.00019733 | 0.00015292 | 0.00011668 | 8.7515e-05 | 6.4407e-05 | 4.6405e-05 | 3.2645e-05 | 2.235e-05 | 1.4833e-05 | 9.496e-06 | 5.8282e-06 | 3.402e-06 | 1.8689e-06 | 9.526e-07 | 4.4162e-07 | 1.8084e-07 | 6.2517e-08 | 1.6911e-08 | 3.1049e-09 | 2.811e-10 | 4.5281e-12 | 1.372e-31
5 | 60 | 120 | 240 | 1 | 33.3333 | R | Slight skew | 3 | 150 | Medium-High Confidence | 5 | 3 | 5 |  | 127.5 | 29.052 | 844.0187 | 150 | 77.34% | 83.1762 | 178.5729 | 90.5349 | 101.0988 | 109.7411 | 117.7054 | 125.5409 | 133.6587 | 142.5398 | 153.0164 | 167.3124 | 197.4618 | 1.8 | 60 | 61.8 | 63.6 | 65.4 | 67.2 | 69 | 70.8 | 72.6 | 74.4 | 76.2 | 78 | 79.8 | 81.6 | 83.4 | 85.2 | 87 | 88.8 | 90.6 | 92.4 | 94.2 | 96 | 97.8 | 99.6 | 101.4 | 103.2 | 105 | 106.8 | 108.6 | 110.4 | 112.2 | 114 | 115.8 | 117.6 | 119.4 | 121.2 | 123 | 124.8 | 126.6 | 128.4 | 130.2 | 132 | 133.8 | 135.6 | 137.4 | 139.2 | 141 | 142.8 | 144.6 | 146.4 | 148.2 | 150 | 151.8 | 153.6 | 155.4 | 157.2 | 159 | 160.8 | 162.6 | 164.4 | 166.2 | 168 | 169.8 | 171.6 | 173.4 | 175.2 | 177 | 178.8 | 180.6 | 182.4 | 184.2 | 186 | 187.8 | 189.6 | 191.4 | 193.2 | 195 | 196.8 | 198.6 | 200.4 | 202.2 | 204 | 205.8 | 207.6 | 209.4 | 211.2 | 213 | 214.8 | 216.6 | 218.4 | 220.2 | 222 | 223.8 | 225.6 | 227.4 | 229.2 | 231 | 232.8 | 234.6 | 236.4 | 238.2 | 239.999 | 0 | 5.6035e-05 | 0.00021522 | 0.00046478 | 0.00079272 | 0.0011878 | 0.0016396 | 0.0021382 | 0.0026745 | 0.0032402 | 0.0038272 | 0.0044286 | 0.0050374 | 0.0056478 | 0.0062541 | 0.0068513 | 0.0074349 | 0.0080007 | 0.0085451 | 0.0090649 | 0.0095573 | 0.01002 | 0.010451 | 0.010848 | 0.01121 | 0.011536 | 0.011825 | 0.012076 | 0.01229 | 0.012467 | 0.012605 | 0.012707 | 0.012772 | 0.012801 | 0.012795 | 0.012756 | 0.012684 | 0.01258 | 0.012447 | 0.012285 | 0.012096 | 0.011882 | 0.011645 | 0.011386 | 0.011106 | 0.010809 | 0.010496 | 0.010168 | 0.0098268 | 0.0094752 | 0.0091146 | 0.0087466 | 0.0083731 | 0.0079958 | 0.0076162 | 0.0072359 | 0.0068565 | 0.0064795 | 0.0061062 | 0.0057379 | 0.005376 | 0.0050215 | 0.0046756 | 0.0043392 | 0.0040132 | 0.0036984 | 0.0033956 | 0.0031054 | 0.0028284 | 0.0025648 | 0.0023152 | 0.0020798 | 0.0018587 | 0.001652 | 0.0014597 | 0.0012817 | 0.0011179 | 0.00096785 | 0.00083137 | 0.00070802 | 0.00059733 | 0.00049877 | 0.00041175 | 0.00033564 | 0.00026975 | 0.00021336 | 0.00016574 | 0.0001261 | 9.3671e-05 | 6.765e-05 | 4.725e-05 | 3.1693e-05 | 2.0223e-05 | 1.2114e-05 | 6.68e-06 | 3.2904e-06 | 1.3763e-06 | 4.4458e-07 | 8.9637e-08 | 5.7172e-09 | 5.5568e-22
6 | 60 | 120 | 240 | 1 | 33.3333 | R | Slight skew | 3 | 150 | Medium Confidence | 6 | 2.5 | 4 |  | 129.228 | 31.968 | 1021.953 | 150 | 73.61% | 80.6675 | 185.5319 | 88.3784 | 99.7938 | 109.3262 | 118.2031 | 126.9838 | 136.0975 | 146.0522 | 157.7256 | 173.4327 | 205.0138 | 1.8 | 60 | 61.8 | 63.6 | 65.4 | 67.2 | 69 | 70.8 | 72.6 | 74.4 | 76.2 | 78 | 79.8 | 81.6 | 83.4 | 85.2 | 87 | 88.8 | 90.6 | 92.4 | 94.2 | 96 | 97.8 | 99.6 | 101.4 | 103.2 | 105 | 106.8 | 108.6 | 110.4 | 112.2 | 114 | 115.8 | 117.6 | 119.4 | 121.2 | 123 | 124.8 | 126.6 | 128.4 | 130.2 | 132 | 133.8 | 135.6 | 137.4 | 139.2 | 141 | 142.8 | 144.6 | 146.4 | 148.2 | 150 | 151.8 | 153.6 | 155.4 | 157.2 | 159 | 160.8 | 162.6 | 164.4 | 166.2 | 168 | 169.8 | 171.6 | 173.4 | 175.2 | 177 | 178.8 | 180.6 | 182.4 | 184.2 | 186 | 187.8 | 189.6 | 191.4 | 193.2 | 195 | 196.8 | 198.6 | 200.4 | 202.2 | 204 | 205.8 | 207.6 | 209.4 | 211.2 | 213 | 214.8 | 216.6 | 218.4 | 220.2 | 222 | 223.8 | 225.6 | 227.4 | 229.2 | 231 | 232.8 | 234.6 | 236.4 | 238.2 | 239.999 | 0 | 0.00019457 | 0.00053381 | 0.00095095 | 0.0014193 | 0.0019221 | 0.0024478 | 0.0029871 | 0.0035331 | 0.0040799 | 0.0046226 | 0.0051573 | 0.0056804 | 0.0061892 | 0.0066811 | 0.0071541 | 0.0076064 | 0.0080365 | 0.0084433 | 0.0088256 | 0.0091828 | 0.0095141 | 0.0098192 | 0.010098 | 0.010349 | 0.010574 | 0.010772 | 0.010944 | 0.011089 | 0.011208 | 0.011301 | 0.01137 | 0.011413 | 0.011433 | 0.011429 | 0.011403 | 0.011354 | 0.011285 | 0.011195 | 0.011085 | 0.010957 | 0.010812 | 0.010649 | 0.010471 | 0.010278 | 0.010071 | 0.0098509 | 0.0096191 | 0.0093763 | 0.0091236 | 0.0088619 | 0.0085922 | 0.0083155 | 0.0080328 | 0.007745 | 0.0074532 | 0.0071581 | 0.0068608 | 0.0065622 | 0.0062631 | 0.0059644 | 0.0056669 | 0.0053715 | 0.005079 | 0.00479 | 0.0045054 | 0.0042258 | 0.003952 | 0.0036845 | 0.0034239 | 0.0031708 | 0.0029258 | 0.0026893 | 0.0024617 | 0.0022435 | 0.002035 | 0.0018366 | 0.0016485 | 0.0014709 | 0.0013039 | 0.0011478 | 0.0010026 | 0.00086836 | 0.00074494 | 0.00063232 | 0.00053035 | 0.00043882 | 0.00035749 | 0.00028604 | 0.00022409 | 0.00017121 | 0.0001269 | 9.0596e-05 | 6.1685e-05 | 3.9473e-05 | 2.3209e-05 | 1.2071e-05 | 5.1723e-06 | 1.5563e-06 | 1.9752e-07 | 3.4383e-17
7 | 60 | 120 | 240 | 1 | 33.3333 | R | Slight skew | 3 | 150 | Medium-Low Confidence | 7 | 2 | 3 |  | 132 | 36 | 1296 | 150 | 68.75% | 77.5701 | 195.2512 | 85.6607 | 98.2171 | 109.0291 | 119.25 | 129.431 | 140.01 | 151.5129 | 164.8416 | 182.3171 | 214.6438 | 1.8 | 60 | 61.8 | 63.6 | 65.4 | 67.2 | 69 | 70.8 | 72.6 | 74.4 | 76.2 | 78 | 79.8 | 81.6 | 83.4 | 85.2 | 87 | 88.8 | 90.6 | 92.4 | 94.2 | 96 | 97.8 | 99.6 | 101.4 | 103.2 | 105 | 106.8 | 108.6 | 110.4 | 112.2 | 114 | 115.8 | 117.6 | 119.4 | 121.2 | 123 | 124.8 | 126.6 | 128.4 | 130.2 | 132 | 133.8 | 135.6 | 137.4 | 139.2 | 141 | 142.8 | 144.6 | 146.4 | 148.2 | 150 | 151.8 | 153.6 | 155.4 | 157.2 | 159 | 160.8 | 162.6 | 164.4 | 166.2 | 168 | 169.8 | 171.6 | 173.4 | 175.2 | 177 | 178.8 | 180.6 | 182.4 | 184.2 | 186 | 187.8 | 189.6 | 191.4 | 193.2 | 195 | 196.8 | 198.6 | 200.4 | 202.2 | 204 | 205.8 | 207.6 | 209.4 | 211.2 | 213 | 214.8 | 216.6 | 218.4 | 220.2 | 222 | 223.8 | 225.6 | 227.4 | 229.2 | 231 | 232.8 | 234.6 | 236.4 | 238.2 | 239.999 | 0 | 0.0006534 | 0.0012805 | 0.0018818 | 0.0024576 | 0.0030083 | 0.0035344 | 0.0040362 | 0.0045141 | 0.0049686 | 0.0054 | 0.0058087 | 0.0061952 | 0.0065598 | 0.0069029 | 0.007225 | 0.0075264 | 0.0078075 | 0.0080688 | 0.0083106 | 0.0085333 | 0.0087374 | 0.0089232 | 0.0090911 | 0.0092416 | 0.009375 | 0.0094917 | 0.0095922 | 0.0096768 | 0.0097459 | 0.0098 | 0.0098394 | 0.0098645 | 0.0098758 | 0.0098736 | 0.0098583 | 0.0098304 | 0.0097902 | 0.0097381 | 0.0096746 | 0.0096 | 0.0095147 | 0.0094192 | 0.0093138 | 0.0091989 | 0.009075 | 0.0089424 | 0.0088015 | 0.0086528 | 0.0084966 | 0.0083333 | 0.0081634 | 0.0079872 | 0.0078051 | 0.0076176 | 0.007425 | 0.0072277 | 0.0070262 | 0.0068208 | 0.0066119 | 0.0064 | 0.0061854 | 0.0059685 | 0.0057498 | 0.0055296 | 0.0053083 | 0.0050864 | 0.0048642 | 0.0046421 | 0.0044206 | 0.0042 | 0.0039807 | 0.0037632 | 0.0035478 | 0.0033349 | 0.003125 | 0.0029184 | 0.0027155 | 0.0025168 | 0.0023226 | 0.0021333 | 0.0019494 | 0.0017712 | 0.0015991 | 0.0014336 | 0.001275 | 0.0011237 | 0.0009802 | 0.0008448 | 0.00071793 | 0.0006 | 0.0004914 | 0.00039253 | 0.0003038 | 0.0002256 | 0.00015833 | 0.0001024 | 5.82e-05 | 2.6133e-05 | 6.6e-06 | 2.0576e-12
8 | 60 | 120 | 240 | 1 | 33.3333 | R | Slight skew | 3 | 150 | Low Confidence | 8 | 1.5 | 2 |  | 137.13 | 41.994 | 1763.496 | 150 | 61.87% | 73.6817 | 209.715 | 82.1579 | 96.4322 | 109.3686 | 121.8833 | 134.4529 | 147.476 | 161.4358 | 177.1411 | 196.5547 | 226.6872 | 1.8 | 60 | 61.8 | 63.6 | 65.4 | 67.2 | 69 | 70.8 | 72.6 | 74.4 | 76.2 | 78 | 79.8 | 81.6 | 83.4 | 85.2 | 87 | 88.8 | 90.6 | 92.4 | 94.2 | 96 | 97.8 | 99.6 | 101.4 | 103.2 | 105 | 106.8 | 108.6 | 110.4 | 112.2 | 114 | 115.8 | 117.6 | 119.4 | 121.2 | 123 | 124.8 | 126.6 | 128.4 | 130.2 | 132 | 133.8 | 135.6 | 137.4 | 139.2 | 141 | 142.8 | 144.6 | 146.4 | 148.2 | 150 | 151.8 | 153.6 | 155.4 | 157.2 | 159 | 160.8 | 162.6 | 164.4 | 166.2 | 168 | 169.8 | 171.6 | 173.4 | 175.2 | 177 | 178.8 | 180.6 | 182.4 | 184.2 | 186 | 187.8 | 189.6 | 191.4 | 193.2 | 195 | 196.8 | 198.6 | 200.4 | 202.2 | 204 | 205.8 | 207.6 | 209.4 | 211.2 | 213 | 214.8 | 216.6 | 218.4 | 220.2 | 222 | 223.8 | 225.6 | 227.4 | 229.2 | 231 | 232.8 | 234.6 | 236.4 | 238.2 | 239.999 | 0 | 0.0020625 | 0.0028874 | 0.0035002 | 0.004 | 0.0044256 | 0.0047969 | 0.0051261 | 0.0054212 | 0.0056875 | 0.0059293 | 0.0061496 | 0.0063509 | 0.0065351 | 0.0067038 | 0.0068584 | 0.007 | 0.0071295 | 0.0072478 | 0.0073556 | 0.0074536 | 0.0075422 | 0.0076219 | 0.0076933 | 0.0077567 | 0.0078125 | 0.007861 | 0.0079025 | 0.0079373 | 0.0079656 | 0.0079876 | 0.0080037 | 0.0080139 | 0.0080185 | 0.0080176 | 0.0080114 | 0.008 | 0.0079836 | 0.0079624 | 0.0079364 | 0.0079057 | 0.0078705 | 0.0078309 | 0.007787 | 0.0077388 | 0.0076865 | 0.0076301 | 0.0075698 | 0.0075056 | 0.0074375 | 0.0073657 | 0.0072902 | 0.0072111 | 0.0071284 | 0.0070423 | 0.0069527 | 0.0068597 | 0.0067634 | 0.0066638 | 0.006561 | 0.006455 | 0.0063458 | 0.0062336 | 0.0061183 | 0.006 | 0.0058787 | 0.0057545 | 0.0056274 | 0.0054975 | 0.0053647 | 0.0052291 | 0.0050908 | 0.0049497 | 0.004806 | 0.0046596 | 0.0045105 | 0.0043589 | 0.0042047 | 0.0040479 | 0.0038886 | 0.0037268 | 0.0035625 | 0.0033958 | 0.0032266 | 0.0030551 | 0.0028811 | 0.0027048 | 0.0025262 | 0.0023452 | 0.002162 | 0.0019764 | 0.0017886 | 0.0015986 | 0.0014064 | 0.0012119 | 0.0010153 | 0.0008165 | 0.00061555 | 0.00041248 | 0.00020729 | 1.1574e-07
9 | 60 | 120 | 240 | 1 | 33.3333 | R | Slight skew | 3 | 150 | Very Low Confidence | 9 | 1.25 | 1.5 |  | 141.81 | 46.278 | 2141.6533 | 150 | 56.97% | 71.4025 | 219.6097 | 80.0792 | 95.7161 | 110.4737 | 124.9819 | 139.5921 | 154.6077 | 170.3944 | 187.5413 | 207.3867 | 233.0815 | 1.8 | 60 | 61.8 | 63.6 | 65.4 | 67.2 | 69 | 70.8 | 72.6 | 74.4 | 76.2 | 78 | 79.8 | 81.6 | 83.4 | 85.2 | 87 | 88.8 | 90.6 | 92.4 | 94.2 | 96 | 97.8 | 99.6 | 101.4 | 103.2 | 105 | 106.8 | 108.6 | 110.4 | 112.2 | 114 | 115.8 | 117.6 | 119.4 | 121.2 | 123 | 124.8 | 126.6 | 128.4 | 130.2 | 132 | 133.8 | 135.6 | 137.4 | 139.2 | 141 | 142.8 | 144.6 | 146.4 | 148.2 | 150 | 151.8 | 153.6 | 155.4 | 157.2 | 159 | 160.8 | 162.6 | 164.4 | 166.2 | 168 | 169.8 | 171.6 | 173.4 | 175.2 | 177 | 178.8 | 180.6 | 182.4 | 184.2 | 186 | 187.8 | 189.6 | 191.4 | 193.2 | 195 | 196.8 | 198.6 | 200.4 | 202.2 | 204 | 205.8 | 207.6 | 209.4 | 211.2 | 213 | 214.8 | 216.6 | 218.4 | 220.2 | 222 | 223.8 | 225.6 | 227.4 | 229.2 | 231 | 232.8 | 234.6 | 236.4 | 238.2 | 239.999 | 0 | 0.0035 | 0.0041411 | 0.0045594 | 0.0048741 | 0.0051268 | 0.0053376 | 0.0055177 | 0.0056743 | 0.005812 | 0.0059342 | 0.0060435 | 0.0061416 | 0.00623 | 0.0063099 | 0.0063823 | 0.0064478 | 0.0065072 | 0.006561 | 0.0066096 | 0.0066535 | 0.0066929 | 0.0067282 | 0.0067596 | 0.0067874 | 0.0068118 | 0.0068329 | 0.0068509 | 0.0068659 | 0.0068782 | 0.0068877 | 0.0068946 | 0.006899 | 0.006901 | 0.0069006 | 0.0068979 | 0.006893 | 0.006886 | 0.0068768 | 0.0068656 | 0.0068523 | 0.006837 | 0.0068198 | 0.0068006 | 0.0067796 | 0.0067566 | 0.0067318 | 0.0067051 | 0.0066766 | 0.0066463 | 0.0066141 | 0.0065801 | 0.0065443 | 0.0065067 | 0.0064673 | 0.006426 | 0.0063829 | 0.0063379 | 0.0062911 | 0.0062424 | 0.0061917 | 0.0061392 | 0.0060846 | 0.0060281 | 0.0059695 | 0.0059089 | 0.0058462 | 0.0057812 | 0.0057141 | 0.0056447 | 0.0055729 | 0.0054987 | 0.005422 | 0.0053427 | 0.0052606 | 0.0051758 | 0.0050881 | 0.0049973 | 0.0049032 | 0.0048057 | 0.0047047 | 0.0045998 | 0.0044909 | 0.0043776 | 0.0042597 | 0.0041366 | 0.0040081 | 0.0038734 | 0.0037321 | 0.0035833 | 0.0034261 | 0.0032593 | 0.0030813 | 0.0028901 | 0.0026829 | 0.0024556 | 0.0022021 | 0.001912 | 0.0015652 | 0.0011096 | 2.6218e-05
10 | 60 | 120 | 240 | 1 | 33.3333 | R | Slight skew | 3 | 150 | Guesstimate | 10 | 1.125 | 1.25 |  | 145.248 | 48.924 | 2393.5578 | 150 | 53.85% | 70.2008 | 225.2332 | 79.0044 | 95.618 | 111.7167 | 127.6854 | 143.7491 | 160.1047 | 176.9863 | 194.7569 | 214.1945 | 235.9391 | 1.8 | 60 | 61.8 | 63.6 | 65.4 | 67.2 | 69 | 70.8 | 72.6 | 74.4 | 76.2 | 78 | 79.8 | 81.6 | 83.4 | 85.2 | 87 | 88.8 | 90.6 | 92.4 | 94.2 | 96 | 97.8 | 99.6 | 101.4 | 103.2 | 105 | 106.8 | 108.6 | 110.4 | 112.2 | 114 | 115.8 | 117.6 | 119.4 | 121.2 | 123 | 124.8 | 126.6 | 128.4 | 130.2 | 132 | 133.8 | 135.6 | 137.4 | 139.2 | 141 | 142.8 | 144.6 | 146.4 | 148.2 | 150 | 151.8 | 153.6 | 155.4 | 157.2 | 159 | 160.8 | 162.6 | 164.4 | 166.2 | 168 | 169.8 | 171.6 | 173.4 | 175.2 | 177 | 178.8 | 180.6 | 182.4 | 184.2 | 186 | 187.8 | 189.6 | 191.4 | 193.2 | 195 | 196.8 | 198.6 | 200.4 | 202.2 | 204 | 205.8 | 207.6 | 209.4 | 211.2 | 213 | 214.8 | 216.6 | 218.4 | 220.2 | 222 | 223.8 | 225.6 | 227.4 | 229.2 | 231 | 232.8 | 234.6 | 236.4 | 238.2 | 239.999 | 0 | 0.0044622 | 0.0048537 | 0.005093 | 0.0052658 | 0.0054006 | 0.0055105 | 0.0056027 | 0.0056816 | 0.0057501 | 0.0058103 | 0.0058635 | 0.0059109 | 0.0059533 | 0.0059914 | 0.0060256 | 0.0060565 | 0.0060843 | 0.0061094 | 0.006132 | 0.0061523 | 0.0061705 | 0.0061868 | 0.0062012 | 0.0062139 | 0.0062251 | 0.0062347 | 0.0062429 | 0.0062498 | 0.0062553 | 0.0062597 | 0.0062628 | 0.0062648 | 0.0062657 | 0.0062655 | 0.0062643 | 0.0062621 | 0.0062589 | 0.0062547 | 0.0062496 | 0.0062436 | 0.0062366 | 0.0062287 | 0.00622 | 0.0062103 | 0.0061998 | 0.0061884 | 0.0061761 | 0.006163 | 0.006149 | 0.0061341 | 0.0061183 | 0.0061016 | 0.0060841 | 0.0060656 | 0.0060462 | 0.0060259 | 0.0060047 | 0.0059824 | 0.0059592 | 0.005935 | 0.0059097 | 0.0058834 | 0.005856 | 0.0058275 | 0.0057979 | 0.005767 | 0.0057349 | 0.0057015 | 0.0056667 | 0.0056306 | 0.005593 | 0.0055538 | 0.0055131 | 0.0054706 | 0.0054263 | 0.0053801 | 0.0053319 | 0.0052815 | 0.0052287 | 0.0051734 | 0.0051155 | 0.0050545 | 0.0049904 | 0.0049227 | 0.0048511 | 0.0047751 | 0.0046942 | 0.0046078 | 0.004515 | 0.0044149 | 0.004306 | 0.0041868 | 0.0040548 | 0.0039067 | 0.0037376 | 0.0035394 | 0.0032981 | 0.002984 | 0.0025124 | 0.00038621
11 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
12 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
13 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
14 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
15 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
16 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
17 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
18 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
19 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
20 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
23 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
24 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
25 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
26 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
27 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
28 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
29 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
30 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
31 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
32 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
33 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
34 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
35 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
36 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
37 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
38 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
39 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
40 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
41 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
42 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
43 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
44 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
45 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
46 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
47 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
48 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
49 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
50 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
51 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
52 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
53 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
54 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
55 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
56 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
57 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
58 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
59 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
60 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
61 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
62 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
63 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
64 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
65 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
66 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
67 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
68 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
69 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
70 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
71 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
72 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
73 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
74 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
75 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
76 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
77 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
78 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
79 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
80 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
81 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
82 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
83 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
84 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
85 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
86 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
87 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
88 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
89 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
90 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
91 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
92 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
93 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
94 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
95 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
96 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
97 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
98 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
99 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
100 | [133 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| 600 | 1200 | 2400 | [6 empty] | © 2015-2020, William W. Davis, MSPM, PMP |  |  |  |  | 1306.41 | 105.0173 | 11028.6409 | 1500 | 96.74% | 829.8207 | 1841.5481 | 901.3495 | 1012.2719 | 1108.2563 | 1199.1037 | 1289.2662 | 1382.1377 | 1481.6775 | 1594.5917 | 1738.1817 | 1995.9952 | 991.358 | 997.5966 | 1003.8353 | 1010.074 | 1016.3126 | 1022.5513 | 1028.7899 | 1035.0286 | 1041.2672 | 1047.5059 | 1053.7445 | 1059.9832 | 1066.2218 | 1072.4605 | 1078.6991 | 1084.9378 | 1091.1764 | 1097.4151 | 1103.6538 | 1109.8924 | 1116.1311 | 1122.3697 | 1128.6084 | 1134.847 | 1141.0857 | 1147.3243 | 1153.563 | 1159.8016 | 1166.0403 | 1172.2789 | 1178.5176 | 1184.7563 | 1190.9949 | 1197.2336 | 1203.4722 | 1209.7109 | 1215.9495 | 1222.1882 | 1228.4268 | 1234.6655 | 1240.9041 | 1247.1428 | 1253.3814 | 1259.6201 | 1265.8588 | 1272.0974 | 1278.3361 | 1284.5747 | 1290.8134 | 1297.052 | 1303.2907 | 1309.5293 | 1315.768 | 1322.0066 | 1328.2453 | 1334.4839 | 1340.7226 | 1346.9612 | 1353.1999 | 1359.4386 | 1365.6772 | 1371.9159 | 1378.1545 | 1384.3932 | 1390.6318 | 1396.8705 | 1403.1091 | 1409.3478 | 1415.5864 | 1421.8251 | 1428.0637 | 1434.3024 | 1440.5411 | 1446.7797 | 1453.0184 | 1459.257 | 1465.4957 | 1471.7343 | 1477.973 | 1484.2116 | 1490.4503 | 1496.6889 | 1502.9276 | 1509.1662 | 1515.4049 | 1521.6436 | 1527.8822 | 1534.1209 | 1540.3595 | 1546.5982 | 1552.8368 | 1559.0755 | 1565.3141 | 1571.5528 | 1577.7914 | 1584.0301 | 1590.2687 | 1596.5074 | 1602.746 | 1608.9847 | 1615.2234 | 1621.462 | 5.0345e-05 | 5.9849e-05 | 7.0896e-05 | 8.3687e-05 | 9.8438e-05 | 0.00011538 | 0.00013476 | 0.00015685 | 0.0001819 | 0.00021022 | 0.0002421 | 0.00027782 | 0.00031769 | 0.000362 | 0.00041104 | 0.00046508 | 0.00052437 | 0.00058914 | 0.00065957 | 0.00073582 | 0.000818 | 0.00090615 | 0.0010003 | 0.0011003 | 0.001206 | 0.0013172 | 0.0014337 | 0.0015549 | 0.0016804 | 0.0018097 | 0.001942 | 0.0020767 | 0.0022129 | 0.0023497 | 0.0024862 | 0.0026214 | 0.0027541 | 0.0028834 | 0.0030082 | 0.0031272 | 0.0032396 | 0.0033441 | 0.0034399 | 0.0035259 | 0.0036014 | 0.0036655 | 0.0037176 | 0.0037572 | 0.0037838 | 0.0037971 | 0.0037971 | 0.0037838 | 0.0037572 | 0.0037176 | 0.0036655 | 0.0036014 | 0.0035259 | 0.0034399 | 0.0033441 | 0.0032396 | 0.0031272 | 0.0030082 | 0.0028834 | 0.0027541 | 0.0026214 | 0.0024862 | 0.0023497 | 0.0022129 | 0.0020767 | 0.001942 | 0.0018097 | 0.0016804 | 0.0015549 | 0.0014337 | 0.0013172 | 0.001206 | 0.0011003 | 0.0010003 | 0.00090615 | 0.000818 | 0.00073582 | 0.00065957 | 0.00058914 | 0.00052437 | 0.00046508 | 0.00041104 | 0.000362 | 0.00031769 | 0.00027782 | 0.0002421 | 0.00021022 | 0.0001819 | 0.00015685 | 0.00013476 | 0.00011538 | 9.8438e-05 | 8.3687e-05 | 7.0896e-05 | 5.9849e-05 | 5.0345e-05 | 4.2201e-05
| Do not show currency formatting | [14 empty] | Whole project or portfolio planning estimate |  | 1500 | 96.74% | 1133.6719 | 1479.1481 | 1171.8249 | 1218.0252 | 1251.3389 | 1279.8042 | 1306.41 | 1333.0158 | 1361.4811 | 1394.7948 | 1440.9951 | 1550.7169 | [102 empty] | 5.0345e-05 | 5.9849e-05 | 7.0896e-05 | 8.3687e-05 | 9.8438e-05 | 0.00011538 | 0.00013476 | 0.00015685 | 0.0001819 | 0.00021022 | 0.0002421 | 0.00027782 | 0.00031769 | 0.000362 | 0.00041104 | 0.00046508 | 0.00052437 | 0.00058914 | 0.00065957 | 0.00073582 | 0.000818 | 0.00090615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[134 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0010003 | 0.0011003 | 0.001206 | 0.0013172 | 0.0014337 | 0.0015549 | 0.0016804 | 0.0018097 | 0.001942 | 0.0020767 | 0.0022129 | 0.0023497 | 0.0024862 | 0.0026214 | 0.0027541 | 0.0028834 | 0.0030082 | 0.0031272 | 0.0032396 | 0.0033441 | 0.0034399 | 0.0035259 | 0.0036014 | 0.0036655 | 0.0037176 | 0.0037572 | 0.0037838 | 0.0037971 | 0.0037971 | 0.0037838 | 0.0037572 | 0.0037176 | 0.0036655 | 0.0036014 | 0.0035259 | 0.0034399 | 0.0033441 | 0.0032396 | 0.0031272 | 0.0030082 | 0.0028834 | 0.0027541 | 0.0026214 | 0.0024862 | 0.0023497 | 0.0022129 | 0.0020767 | 0.001942 | 0.0018097 | 0.0016804 | 0.0015549 | 0.0014337 | 0.0013172 | 0.001206 | 0.0011003 | 0.0010003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | With | 90% | confidence | [129 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00090615 | 0.000818 | 0.00073582 | 0.00065957 | 0.00058914 | 0.00052437 | 0.00046508 | 0.00041104 | 0.000362 | 0.00031769 | 0.00027782 | 0.0002421 | 0.00021022 | 0.0001819 | 0.00015685 | 0.00013476 | 0.00011538 | 9.8438e-05 | 8.3687e-05 | 7.0896e-05 | 5.9849e-05 | 5.0345e-05 | 4.2201e-05
|  | The lowerbound threshold is | 1133.6719 | [130 empty] | 5.0345e-05 | 5.9849e-05 | 7.0896e-05 | 8.3687e-05 | 9.8438e-05 | 0.00011538 | 0.00013476 | 0.00015685 | 0.0001819 | 0.00021022 | 0.0002421 | 0.00027782 | 0.00031769 | 0.000362 | 0.00041104 | 0.00046508 | 0.00052437 | 0.00058914 | 0.00065957 | 0.00073582 | 0.000818 | 0.00090615 | 0.0010003 | 0.0011003 | 0.001206 | 0.0013172 | 0.0014337 | 0.0015549 | 0.0016804 | 0.0018097 | 0.001942 | 0.0020767 | 0.0022129 | 0.0023497 | 0.0024862 | 0.0026214 | 0.0027541 | 0.0028834 | 0.0030082 | 0.0031272 | 0.0032396 | 0.0033441 | 0.0034399 | 0.0035259 | 0.0036014 | 0.0036655 | 0.0037176 | 0.0037572 | 0.0037838 | 0.0037971 | 0.0037971 | 0.0037838 | 0.0037572 | 0.0037176 | 0.0036655 | 0.0036014 | 0.0035259 | 0.0034399 | 0.0033441 | 0.0032396 | 0.0031272 | 0.0030082 | 0.0028834 | 0.0027541 | 0.0026214 | 0.0024862 | 0.0023497 | 0.0022129 | 0.0020767 | 0.001942 | 0.0018097 | 0.0016804 | 0.0015549 | 0.0014337 | 0.0013172 | 0.001206 | 0.0011003 | 0.0010003 | 0.00090615 | 0.000818 | 0.00073582 | 0.00065957 | 0.00058914 | 0.00052437 | 0.00046508 | 0.00041104 | 0.000362 | 0.00031769 | 0.00027782 | 0.0002421 | 0.00021022 | 0.0001819 | 0.00015685 | 0.00013476 | 0.00011538 | 9.8438e-05 | 8.3687e-05 | 7.0896e-05 | 5.9849e-05 | 5.0345e-05 | 4.2201e-05
|  | and the upperbound threshold is | 1479.1481
|  | Between a lowerbound value of | 1134
|  | and an upperbound value of | 1479
|  | the range probability is | 89.95%
|  | where, below the lowerbound, the % is | 5.032%
|  | and above the upperbound, the % is | 5.015%
To use this template:
1) Create a 3-point estimate under the Minimum, Most Likely, and Maximum columns
2) Render a subjective judgment about how likely the Most Likely outcome is, under the Most Likely Confidence column
3) Examine the SPERT probabilistic estimates for various confidence levels
Optionally:
Enter any desired estimate under the Planning Estimate column to find the SPERT probability for the planning estimate
Version 3.0.s – © 2015-2020, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Subscribe to the SPERT® newsletter for monthly tips, free webinars, and new release notifications
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).
Note on S2: You may optionally enter a planning estimate for each uncertainty you enter, and see its cumulative probability result in the 'SPERT Probability' column. The cumulative probability is the likelihood your planning estimate will be EQUAL TO or GREATER THAN the uncertainty you are estimating. Choosing a larger planning estimate will increase the cumulative probability, and choosing a smaller planning estimate will decrease the cumulative probability.
Note on T2: The SPERT Probability shows the cumulative probability of each Planning Estimate you entered in column R. If you select 'Show Left-Side Area' in cell R1, this column shows the likelihood that your Planning Estimate will be EQUAL TO or GREATER THAN the uncertainty you are estimating. If you select 'Show Right-Side Area' in cell R1, this column shows the likelihood that the uncertainty will EXCEED your Planning Estimate in column R.
Note on B3: The Minimum point-estimate represents the smallest value that is feasible, but highly improbable.
Note on C3: The Most Likely point-estimate represents the value you believe will most likely occur for each uncertainty, although many other possible outcomes exist between the Minimum and Maximum point-estimates.
Note on D3: The Maximum point-estimate represents the largest value that is feasible, but highly improbable
Note on E3: This checks that a proper 3-point estimate was entered: Minimum value must be > 0 and < Most Likely Most Likely must be > Minimum and < Maximum Maximum must be > Most Likely
Note on K3: The shape of the bell-curve is heavily influenced by how confident you believe the Most Likely outcome will occur relative to other, possible outcomes between the Minimum and Maximum point-estimates. When you are more confident in the Most Likely outcome, the bell-curve grows taller, and there is a shrinking likelihood of other occurrences near the Minimum and Maximum point-estimates. Conversely, when you are less confident in the Most Likely outcome, the bell-curve grows flatter, and there is a rising likelihood of other occurrences near the Minimum and Maximum point-estimates. (You can add to, remove, or modify the dropdown control options using the VLookups worksheet).
Note on O3: William Davis: SPERT builds an implied, bell-shaped curve to represent the risk characteristics for your uncertainty. The flatter, wider the bell-curve curve is, the more uncertain the outcomes are over the feasible region. If the bell-curve's vertical rise is steep, though, your uncertainty has much less volatility near the most likely outcome. If the bell-curve is both centered and symmetrical, it fits a normal distribution. The beta distribution can also show skewed bell-curves, dependent on your 3-point estimate and how likely the most likely outcome really is.
After you finish entering your estimates above, use this area to calculate the probability of all uncertainties together. This is especially useful for creating a forecast for an entire project, for example.
Choose the confidence you want for the confidence interval in cell D108, and/or choose the confidence lower and upperbound thresholds in cells D112 and D113.
Both the pie chart and tri-colored, bell-curve combo chart below represent the uncertainty of summary row #104 and assume that the Central Limit Theorem applies to that row.
IMPORTANT DISCLOSURE!
The charts on this worksheet assume that the Central Limit Theorem applies to summary row #104, which may or may not be true.
Be sure to understand the Central Limit Theorem and validate that it applies to your estimated uncertainties in rows 4-103 before relying on the probabilities shown in row 106 or the the summary charts in this worksheet.
Click for help

## SPERT® Scheduler (Mixed Entry)
SPERT® Scheduler | Start & Finish | 2020-08-01 | 2021-08-13 | Statistical PERT® (SPERT®) Beta Edition Scheduler & Mixed Entry | [20 empty] | Show Left-Side Area |  | Show the likelihood that the SPERT estimates will be EQUAL TO or GREATER THAN an uncertainty
For scheduling the critical path ONLY! | 90% |  | 34.87% |  |  | -50% | < Heuristics > | 50% | [16 empty] | Planning Estimate | SPERT Probability | SPERT Probabilistic Estimates using the BETA distribution | [11 empty] | This section is only to build Line Sparklines to show the bell-shaped curve for each row, and the summary bell-curve chart.
Activity | Duration | Start Date | Finish Date | Min % | Min point | Minimum | Most Likely | Maximum | Max point | Max % |  | Range % | R/L Skew | Skew Analysis | X | Midpoint | Most Likely Confidence | Y | Alpha | Beta | Curve | Mean | SPERT SD | Variance |  |  | 80% | 95% | 10% | 20% | 30% | 40% | 50% | 60% | 70% | 80% | 90% | 99% | x-axis increments (magenta in blue cells shows the increment, the next 101 columns are the x-axis values for the Line Sparkline column and summary bell-curve chart) | [101 empty] | These are the y-axis values with which the bell-shaped curve is built (used only for the Line SparkLine column) | [100 empty] | ← Columns AH through IB are hidden; they are used to create Sparklines and the bell-curve bar chart
Project initiation | 6 | 2020-08-01 | 2020-08-10 |  |  | 2.5 | 5 | 7.5 |  |  | 1 | 50 | EQ | No skew | 1 | 5 | High Confidence | 4 | 7 | 7 |  | 5 | 0.625 | 0.39062 | 5 | 50% | 5.565 | 6.0648 | 4.1543 | 4.435 | 4.6451 | 4.8279 | 5 | 5.1721 | 5.3549 | 5.565 | 5.8457 | 6.4356 | 0.05 | 2.5 | 2.55 | 2.6 | 2.65 | 2.7 | 2.75 | 2.8 | 2.85 | 2.9 | 2.95 | 3 | 3.05 | 3.1 | 3.15 | 3.2 | 3.25 | 3.3 | 3.35 | 3.4 | 3.45 | 3.5 | 3.55 | 3.6 | 3.65 | 3.7 | 3.75 | 3.8 | 3.85 | 3.9 | 3.95 | 4 | 4.05 | 4.1 | 4.15 | 4.2 | 4.25 | 4.3 | 4.35 | 4.4 | 4.45 | 4.5 | 4.55 | 4.6 | 4.65 | 4.7 | 4.75 | 4.8 | 4.85 | 4.9 | 4.95 | 5 | 5.05 | 5.1 | 5.15 | 5.2 | 5.25 | 5.3 | 5.35 | 5.4 | 5.45 | 5.5 | 5.55 | 5.6 | 5.65 | 5.7 | 5.75 | 5.8 | 5.85 | 5.9 | 5.95 | 6 | 6.05 | 6.1 | 6.15 | 6.2 | 6.25 | 6.3 | 6.35 | 6.4 | 6.45 | 6.5 | 6.55 | 6.6 | 6.65 | 6.7 | 6.75 | 6.8 | 6.85 | 6.9 | 6.95 | 7 | 7.05 | 7.1 | 7.15 | 7.2 | 7.25 | 7.3 | 7.35 | 7.4 | 7.45 | 7.499 | 0 | 2.2618e-09 | 1.362e-07 | 1.4588e-06 | 7.7025e-06 | 2.7594e-05 | 7.7325e-05 | 0.00018287 | 0.00038187 | 0.00072502 | 0.0012767 | 0.0021152 | 0.0033314 | 0.0050283 | 0.0073182 | 0.010321 | 0.014159 | 0.018959 | 0.024841 | 0.031921 | 0.040306 | 0.050087 | 0.061341 | 0.074124 | 0.08847 | 0.10439 | 0.12186 | 0.14085 | 0.16128 | 0.18306 | 0.20604 | 0.2301 | 0.25503 | 0.28066 | 0.30675 | 0.33307 | 0.35937 | 0.38539 | 0.41086 | 0.43552 | 0.45911 | 0.48135 | 0.50201 | 0.52084 | 0.53764 | 0.5522 | 0.56436 | 0.57397 | 0.58092 | 0.58512 | 0.58652 | 0.58512 | 0.58092 | 0.57397 | 0.56436 | 0.5522 | 0.53764 | 0.52084 | 0.50201 | 0.48135 | 0.45911 | 0.43552 | 0.41086 | 0.38539 | 0.35937 | 0.33307 | 0.30675 | 0.28066 | 0.25503 | 0.2301 | 0.20604 | 0.18306 | 0.16128 | 0.14085 | 0.12186 | 0.10439 | 0.08847 | 0.074124 | 0.061341 | 0.050087 | 0.040306 | 0.031921 | 0.024841 | 0.018959 | 0.014159 | 0.010321 | 0.0073182 | 0.0050283 | 0.0033314 | 0.0021152 | 0.0012767 | 0.00072502 | 0.00038187 | 0.00018287 | 7.7325e-05 | 2.7594e-05 | 7.7025e-06 | 1.4588e-06 | 1.362e-07 | 2.2618e-09 | 1.5357e-19
Business Reqs Analysis | 24 | 2020-08-10 | 2020-09-14 | -25% |  | 15 | 20 | 30 |  |  | 1 | 33.3333 | R | Slight skew | 3 | 22.5 | Medium-High Confidence | 5 | 3 | 5 |  | 20.625 | 2.421 | 5.8612 | 25 | 95.47% | 22.7514 | 24.8811 | 17.5446 | 18.4249 | 19.1451 | 19.8088 | 20.4617 | 21.1382 | 21.8783 | 22.7514 | 23.9427 | 26.4551 | 0.15 | 15 | 15.15 | 15.3 | 15.45 | 15.6 | 15.75 | 15.9 | 16.05 | 16.2 | 16.35 | 16.5 | 16.65 | 16.8 | 16.95 | 17.1 | 17.25 | 17.4 | 17.55 | 17.7 | 17.85 | 18 | 18.15 | 18.3 | 18.45 | 18.6 | 18.75 | 18.9 | 19.05 | 19.2 | 19.35 | 19.5 | 19.65 | 19.8 | 19.95 | 20.1 | 20.25 | 20.4 | 20.55 | 20.7 | 20.85 | 21 | 21.15 | 21.3 | 21.45 | 21.6 | 21.75 | 21.9 | 22.05 | 22.2 | 22.35 | 22.5 | 22.65 | 22.8 | 22.95 | 23.1 | 23.25 | 23.4 | 23.55 | 23.7 | 23.85 | 24 | 24.15 | 24.3 | 24.45 | 24.6 | 24.75 | 24.9 | 25.05 | 25.2 | 25.35 | 25.5 | 25.65 | 25.8 | 25.95 | 26.1 | 26.25 | 26.4 | 26.55 | 26.7 | 26.85 | 27 | 27.15 | 27.3 | 27.45 | 27.6 | 27.75 | 27.9 | 28.05 | 28.2 | 28.35 | 28.5 | 28.65 | 28.8 | 28.95 | 29.1 | 29.25 | 29.4 | 29.55 | 29.7 | 29.85 | 29.999 | 0 | 0.00067242 | 0.0025826 | 0.0055773 | 0.0095127 | 0.014254 | 0.019675 | 0.025658 | 0.032094 | 0.038882 | 0.045927 | 0.053143 | 0.060449 | 0.067774 | 0.07505 | 0.082216 | 0.089219 | 0.096008 | 0.10254 | 0.10878 | 0.11469 | 0.12024 | 0.12541 | 0.13017 | 0.13452 | 0.13843 | 0.1419 | 0.14492 | 0.14748 | 0.1496 | 0.15126 | 0.15248 | 0.15326 | 0.15361 | 0.15354 | 0.15307 | 0.1522 | 0.15096 | 0.14936 | 0.14742 | 0.14515 | 0.14258 | 0.13974 | 0.13663 | 0.13328 | 0.12971 | 0.12595 | 0.12201 | 0.11792 | 0.1137 | 0.10938 | 0.10496 | 0.10048 | 0.095949 | 0.091394 | 0.086831 | 0.082278 | 0.077754 | 0.073274 | 0.068855 | 0.064512 | 0.060258 | 0.056107 | 0.05207 | 0.048158 | 0.044381 | 0.040748 | 0.037265 | 0.03394 | 0.030778 | 0.027783 | 0.024958 | 0.022305 | 0.019824 | 0.017517 | 0.015381 | 0.013414 | 0.011614 | 0.0099765 | 0.0084963 | 0.007168 | 0.0059853 | 0.004941 | 0.0040276 | 0.003237 | 0.0025604 | 0.0019889 | 0.0015132 | 0.0011241 | 0.0008118 | 0.000567 | 0.00038032 | 0.00024268 | 0.00014536 | 8.016e-05 | 3.9484e-05 | 1.6515e-05 | 5.3349e-06 | 1.0756e-06 | 6.8607e-08 | 1.3825e-16
Detail Design | 18 | 2020-09-14 | 2020-10-08 | -25% |  | 11.25 | 15 | 22.5 |  |  | 1 | 33.3333 | R | Slight skew | 3 | 16.875 | Medium Confidence | 6 | 2.5 | 4 |  | 15.5768 | 1.998 | 3.992 | 20 | 98.36% | 17.3578 | 19.0957 | 13.0237 | 13.7371 | 14.3329 | 14.8877 | 15.4365 | 16.0061 | 16.6283 | 17.3578 | 18.3395 | 20.3134 | 0.1125 | 11.25 | 11.3625 | 11.475 | 11.5875 | 11.7 | 11.8125 | 11.925 | 12.0375 | 12.15 | 12.2625 | 12.375 | 12.4875 | 12.6 | 12.7125 | 12.825 | 12.9375 | 13.05 | 13.1625 | 13.275 | 13.3875 | 13.5 | 13.6125 | 13.725 | 13.8375 | 13.95 | 14.0625 | 14.175 | 14.2875 | 14.4 | 14.5125 | 14.625 | 14.7375 | 14.85 | 14.9625 | 15.075 | 15.1875 | 15.3 | 15.4125 | 15.525 | 15.6375 | 15.75 | 15.8625 | 15.975 | 16.0875 | 16.2 | 16.3125 | 16.425 | 16.5375 | 16.65 | 16.7625 | 16.875 | 16.9875 | 17.1 | 17.2125 | 17.325 | 17.4375 | 17.55 | 17.6625 | 17.775 | 17.8875 | 18 | 18.1125 | 18.225 | 18.3375 | 18.45 | 18.5625 | 18.675 | 18.7875 | 18.9 | 19.0125 | 19.125 | 19.2375 | 19.35 | 19.4625 | 19.575 | 19.6875 | 19.8 | 19.9125 | 20.025 | 20.1375 | 20.25 | 20.3625 | 20.475 | 20.5875 | 20.7 | 20.8125 | 20.925 | 21.0375 | 21.15 | 21.2625 | 21.375 | 21.4875 | 21.6 | 21.7125 | 21.825 | 21.9375 | 22.05 | 22.1625 | 22.275 | 22.3875 | 22.499 | 0 | 0.003113 | 0.0085409 | 0.015215 | 0.022708 | 0.030754 | 0.039164 | 0.047794 | 0.05653 | 0.065278 | 0.073962 | 0.082516 | 0.090886 | 0.099027 | 0.1069 | 0.11447 | 0.1217 | 0.12858 | 0.13509 | 0.14121 | 0.14692 | 0.15223 | 0.15711 | 0.16156 | 0.16559 | 0.16919 | 0.17236 | 0.1751 | 0.17742 | 0.17933 | 0.18082 | 0.18192 | 0.18261 | 0.18293 | 0.18286 | 0.18244 | 0.18167 | 0.18055 | 0.17911 | 0.17736 | 0.17532 | 0.17299 | 0.17039 | 0.16754 | 0.16445 | 0.16113 | 0.15761 | 0.15391 | 0.15002 | 0.14598 | 0.14179 | 0.13747 | 0.13305 | 0.12852 | 0.12392 | 0.11925 | 0.11453 | 0.10977 | 0.105 | 0.10021 | 0.09543 | 0.090671 | 0.085944 | 0.081263 | 0.07664 | 0.072086 | 0.067613 | 0.063232 | 0.058951 | 0.054782 | 0.050733 | 0.046812 | 0.043028 | 0.039387 | 0.035896 | 0.032561 | 0.029386 | 0.026375 | 0.023534 | 0.020863 | 0.018366 | 0.016042 | 0.013894 | 0.011919 | 0.010117 | 0.0084856 | 0.0070212 | 0.0057199 | 0.0045766 | 0.0035854 | 0.0027393 | 0.0020303 | 0.0014495 | 0.00098696 | 0.00063158 | 0.00037134 | 0.00019314 | 8.2756e-05 | 2.4901e-05 | 3.1603e-06 | 2.253e-12
Prototype | 25 | 2020-10-08 | 2020-11-12 |  |  | 10 | 20 | 30 |  |  | 1 | 50 | EQ | No skew | 1 | 20 | Medium-Low Confidence | 7 | 3 | 3 |  | 20 | 3.78 | 14.2884 | 25 | 89.65% | 23.468 | 26.2149 | 14.9327 | 16.532 | 17.7964 | 18.9251 | 20 | 21.0749 | 22.2036 | 23.468 | 25.0673 | 27.8872 | 0.2 | 10 | 10.2 | 10.4 | 10.6 | 10.8 | 11 | 11.2 | 11.4 | 11.6 | 11.8 | 12 | 12.2 | 12.4 | 12.6 | 12.8 | 13 | 13.2 | 13.4 | 13.6 | 13.8 | 14 | 14.2 | 14.4 | 14.6 | 14.8 | 15 | 15.2 | 15.4 | 15.6 | 15.8 | 16 | 16.2 | 16.4 | 16.6 | 16.8 | 17 | 17.2 | 17.4 | 17.6 | 17.8 | 18 | 18.2 | 18.4 | 18.6 | 18.8 | 19 | 19.2 | 19.4 | 19.6 | 19.8 | 20 | 20.2 | 20.4 | 20.6 | 20.8 | 21 | 21.2 | 21.4 | 21.6 | 21.8 | 22 | 22.2 | 22.4 | 22.6 | 22.8 | 23 | 23.2 | 23.4 | 23.6 | 23.8 | 24 | 24.2 | 24.4 | 24.6 | 24.8 | 25 | 25.2 | 25.4 | 25.6 | 25.8 | 26 | 26.2 | 26.4 | 26.6 | 26.8 | 27 | 27.2 | 27.4 | 27.6 | 27.8 | 28 | 28.2 | 28.4 | 28.6 | 28.8 | 29 | 29.2 | 29.4 | 29.6 | 29.8 | 29.999 | 0 | 0.00014701 | 0.00057624 | 0.0012702 | 0.0022118 | 0.0033844 | 0.0047714 | 0.006357 | 0.0081254 | 0.010061 | 0.01215 | 0.014377 | 0.016727 | 0.019187 | 0.021744 | 0.024384 | 0.027095 | 0.029864 | 0.032679 | 0.035528 | 0.0384 | 0.041284 | 0.04417 | 0.047047 | 0.049905 | 0.052734 | 0.055527 | 0.058273 | 0.060964 | 0.063592 | 0.06615 | 0.06863 | 0.071025 | 0.073328 | 0.075533 | 0.077634 | 0.079626 | 0.081503 | 0.083261 | 0.084895 | 0.0864 | 0.087773 | 0.089011 | 0.090111 | 0.091069 | 0.091884 | 0.092554 | 0.093076 | 0.09345 | 0.093675 | 0.09375 | 0.093675 | 0.09345 | 0.093076 | 0.092554 | 0.091884 | 0.091069 | 0.090111 | 0.089011 | 0.087773 | 0.0864 | 0.084895 | 0.083261 | 0.081503 | 0.079626 | 0.077634 | 0.075533 | 0.073328 | 0.071025 | 0.06863 | 0.06615 | 0.063592 | 0.060964 | 0.058273 | 0.055527 | 0.052734 | 0.049905 | 0.047047 | 0.04417 | 0.041284 | 0.0384 | 0.035528 | 0.032679 | 0.029864 | 0.027095 | 0.024384 | 0.021744 | 0.019187 | 0.016727 | 0.014377 | 0.01215 | 0.010061 | 0.0081254 | 0.006357 | 0.0047714 | 0.0033844 | 0.0022118 | 0.0012702 | 0.00057624 | 0.00014702 | 3.7496e-09
Build Solution | 98 | 2020-11-12 | 2021-04-15 | -25% |  | 60 | 80 | 120 |  |  | 1 | 33.3333 | R | Slight skew | 3 | 90 | Medium Confidence | 6 | 2.5 | 4 |  | 83.076 | 10.656 | 113.5503 | 100 | 92.99% | 92.5752 | 101.844 | 69.4595 | 73.2646 | 76.4421 | 79.401 | 82.3279 | 85.3658 | 88.6841 | 92.5752 | 97.8109 | 108.3379 | 0.6 | 60 | 60.6 | 61.2 | 61.8 | 62.4 | 63 | 63.6 | 64.2 | 64.8 | 65.4 | 66 | 66.6 | 67.2 | 67.8 | 68.4 | 69 | 69.6 | 70.2 | 70.8 | 71.4 | 72 | 72.6 | 73.2 | 73.8 | 74.4 | 75 | 75.6 | 76.2 | 76.8 | 77.4 | 78 | 78.6 | 79.2 | 79.8 | 80.4 | 81 | 81.6 | 82.2 | 82.8 | 83.4 | 84 | 84.6 | 85.2 | 85.8 | 86.4 | 87 | 87.6 | 88.2 | 88.8 | 89.4 | 90 | 90.6 | 91.2 | 91.8 | 92.4 | 93 | 93.6 | 94.2 | 94.8 | 95.4 | 96 | 96.6 | 97.2 | 97.8 | 98.4 | 99 | 99.6 | 100.2 | 100.8 | 101.4 | 102 | 102.6 | 103.2 | 103.8 | 104.4 | 105 | 105.6 | 106.2 | 106.8 | 107.4 | 108 | 108.6 | 109.2 | 109.8 | 110.4 | 111 | 111.6 | 112.2 | 112.8 | 113.4 | 114 | 114.6 | 115.2 | 115.8 | 116.4 | 117 | 117.6 | 118.2 | 118.8 | 119.4 | 119.999 | 0 | 0.0005837 | 0.0016014 | 0.0028528 | 0.0042578 | 0.0057664 | 0.0073433 | 0.0089614 | 0.010599 | 0.01224 | 0.013868 | 0.015472 | 0.017041 | 0.018568 | 0.020043 | 0.021462 | 0.022819 | 0.02411 | 0.02533 | 0.026477 | 0.027548 | 0.028542 | 0.029458 | 0.030293 | 0.031048 | 0.031723 | 0.032317 | 0.032832 | 0.033267 | 0.033624 | 0.033904 | 0.034109 | 0.03424 | 0.034299 | 0.034287 | 0.034208 | 0.034062 | 0.033854 | 0.033584 | 0.033256 | 0.032872 | 0.032435 | 0.031948 | 0.031413 | 0.030834 | 0.030213 | 0.029553 | 0.028857 | 0.028129 | 0.027371 | 0.026586 | 0.025777 | 0.024946 | 0.024098 | 0.023235 | 0.02236 | 0.021474 | 0.020583 | 0.019687 | 0.018789 | 0.017893 | 0.017001 | 0.016115 | 0.015237 | 0.01437 | 0.013516 | 0.012677 | 0.011856 | 0.011053 | 0.010272 | 0.0095124 | 0.0087773 | 0.0080678 | 0.0073851 | 0.0067305 | 0.0061051 | 0.0055098 | 0.0049454 | 0.0044126 | 0.0039118 | 0.0034435 | 0.0030079 | 0.0026051 | 0.0022348 | 0.001897 | 0.001591 | 0.0013165 | 0.0010725 | 0.00085812 | 0.00067227 | 0.00051362 | 0.00038069 | 0.00027179 | 0.00018505 | 0.00011842 | 6.9627e-05 | 3.6213e-05 | 1.5517e-05 | 4.6688e-06 | 5.9256e-07 | 2.7849e-15
Migrate to QA | 8 | 2021-04-15 | 2021-04-27 |  |  | 2.5 | 5 | 10 |  | 100% | 1 | 33.3333 | R | Slight skew | 3 | 6.25 | Low Confidence | 8 | 1.5 | 2 |  | 5.7138 | 1.7498 | 3.0616 | 7 | 74.36% | 7.3809 | 8.7381 | 3.4232 | 4.018 | 4.557 | 5.0785 | 5.6022 | 6.1448 | 6.7265 | 7.3809 | 8.1898 | 9.4453 | 0.075 | 2.5 | 2.575 | 2.65 | 2.725 | 2.8 | 2.875 | 2.95 | 3.025 | 3.1 | 3.175 | 3.25 | 3.325 | 3.4 | 3.475 | 3.55 | 3.625 | 3.7 | 3.775 | 3.85 | 3.925 | 4 | 4.075 | 4.15 | 4.225 | 4.3 | 4.375 | 4.45 | 4.525 | 4.6 | 4.675 | 4.75 | 4.825 | 4.9 | 4.975 | 5.05 | 5.125 | 5.2 | 5.275 | 5.35 | 5.425 | 5.5 | 5.575 | 5.65 | 5.725 | 5.8 | 5.875 | 5.95 | 6.025 | 6.1 | 6.175 | 6.25 | 6.325 | 6.4 | 6.475 | 6.55 | 6.625 | 6.7 | 6.775 | 6.85 | 6.925 | 7 | 7.075 | 7.15 | 7.225 | 7.3 | 7.375 | 7.45 | 7.525 | 7.6 | 7.675 | 7.75 | 7.825 | 7.9 | 7.975 | 8.05 | 8.125 | 8.2 | 8.275 | 8.35 | 8.425 | 8.5 | 8.575 | 8.65 | 8.725 | 8.8 | 8.875 | 8.95 | 9.025 | 9.1 | 9.175 | 9.25 | 9.325 | 9.4 | 9.475 | 9.55 | 9.625 | 9.7 | 9.775 | 9.85 | 9.925 | 9.999 | 0 | 0.0495 | 0.069296 | 0.084004 | 0.096 | 0.10621 | 0.11513 | 0.12303 | 0.13011 | 0.1365 | 0.1423 | 0.14759 | 0.15242 | 0.15684 | 0.16089 | 0.1646 | 0.168 | 0.17111 | 0.17395 | 0.17654 | 0.17889 | 0.18101 | 0.18293 | 0.18464 | 0.18616 | 0.1875 | 0.18866 | 0.18966 | 0.19049 | 0.19117 | 0.1917 | 0.19209 | 0.19233 | 0.19244 | 0.19242 | 0.19227 | 0.192 | 0.19161 | 0.1911 | 0.19047 | 0.18974 | 0.18889 | 0.18794 | 0.18689 | 0.18573 | 0.18448 | 0.18312 | 0.18167 | 0.18013 | 0.1785 | 0.17678 | 0.17496 | 0.17307 | 0.17108 | 0.16901 | 0.16686 | 0.16463 | 0.16232 | 0.15993 | 0.15746 | 0.15492 | 0.1523 | 0.14961 | 0.14684 | 0.144 | 0.14109 | 0.13811 | 0.13506 | 0.13194 | 0.12875 | 0.1255 | 0.12218 | 0.11879 | 0.11534 | 0.11183 | 0.10825 | 0.10461 | 0.10091 | 0.097149 | 0.093326 | 0.089443 | 0.0855 | 0.081498 | 0.077439 | 0.073321 | 0.069147 | 0.064915 | 0.060628 | 0.056285 | 0.051887 | 0.047434 | 0.042927 | 0.038367 | 0.033753 | 0.029086 | 0.024367 | 0.019596 | 0.014773 | 0.0098995 | 0.0049749 | 6.6662e-05
QA UAT | 42 | 2021-04-27 | 2021-06-25 | -25% |  | 22.5 | 30 | 60 |  | 100% | 1 | 20 | R | Medium skew | 7 | 41.25 | Medium-High Confidence | 5 | 2 | 5 |  | 33.2138 | 5.9888 | 35.8651 | 40 | 85.62% | 38.3418 | 44.3176 | 25.9723 | 27.7455 | 29.3176 | 30.8469 | 32.4169 | 34.1042 | 36.0134 | 38.3418 | 41.6369 | 48.9632 | 0.375 | 22.5 | 22.875 | 23.25 | 23.625 | 24 | 24.375 | 24.75 | 25.125 | 25.5 | 25.875 | 26.25 | 26.625 | 27 | 27.375 | 27.75 | 28.125 | 28.5 | 28.875 | 29.25 | 29.625 | 30 | 30.375 | 30.75 | 31.125 | 31.5 | 31.875 | 32.25 | 32.625 | 33 | 33.375 | 33.75 | 34.125 | 34.5 | 34.875 | 35.25 | 35.625 | 36 | 36.375 | 36.75 | 37.125 | 37.5 | 37.875 | 38.25 | 38.625 | 39 | 39.375 | 39.75 | 40.125 | 40.5 | 40.875 | 41.25 | 41.625 | 42 | 42.375 | 42.75 | 43.125 | 43.5 | 43.875 | 44.25 | 44.625 | 45 | 45.375 | 45.75 | 46.125 | 46.5 | 46.875 | 47.25 | 47.625 | 48 | 48.375 | 48.75 | 49.125 | 49.5 | 49.875 | 50.25 | 50.625 | 51 | 51.375 | 51.75 | 52.125 | 52.5 | 52.875 | 53.25 | 53.625 | 54 | 54.375 | 54.75 | 55.125 | 55.5 | 55.875 | 56.25 | 56.625 | 57 | 57.375 | 57.75 | 58.125 | 58.5 | 58.875 | 59.25 | 59.625 | 59.999 | 0 | 0.0076848 | 0.014758 | 0.021247 | 0.027179 | 0.03258 | 0.037476 | 0.041891 | 0.045849 | 0.049374 | 0.052488 | 0.055213 | 0.057571 | 0.059581 | 0.061265 | 0.062641 | 0.063728 | 0.064543 | 0.065106 | 0.065431 | 0.065536 | 0.065436 | 0.065146 | 0.064682 | 0.064055 | 0.063281 | 0.062372 | 0.06134 | 0.060197 | 0.058955 | 0.057624 | 0.056214 | 0.054736 | 0.053199 | 0.051611 | 0.049982 | 0.048318 | 0.046629 | 0.04492 | 0.043199 | 0.041472 | 0.039745 | 0.038023 | 0.036313 | 0.034617 | 0.032942 | 0.031291 | 0.029668 | 0.028077 | 0.02652 | 0.025 | 0.02352 | 0.022083 | 0.02069 | 0.019343 | 0.018043 | 0.016791 | 0.01559 | 0.014438 | 0.013338 | 0.012288 | 0.01129 | 0.010342 | 0.0094458 | 0.0085996 | 0.0078033 | 0.0070559 | 0.0063565 | 0.0057043 | 0.0050978 | 0.004536 | 0.0040174 | 0.0035404 | 0.0031036 | 0.0027053 | 0.0023438 | 0.0020172 | 0.0017238 | 0.0014618 | 0.0012291 | 0.001024 | 0.00084448 | 0.00068864 | 0.00055458 | 0.0004404 | 0.00034425 | 0.0002643 | 0.00019878 | 0.00014598 | 0.00010424 | 7.2e-05 | 4.7764e-05 | 3.0147e-05 | 1.7863e-05 | 9.7459e-06 | 4.75e-06 | 1.9661e-06 | 6.2856e-07 | 1.2544e-07 | 7.92e-09 | 4.0453e-19
Pre-production prep | 11 | 2021-06-25 | 2021-07-13 |  |  | 5 | 10 | 15 |  |  | 1 | 50 | EQ | No skew | 1 | 10 | Very High Confidence | 3 | 10 | 10 |  | 10 | 1.091 | 1.1903 | 10 | 50% | 10.9442 | 11.7991 | 8.5793 | 9.0558 | 9.4084 | 9.7134 | 10 | 10.2866 | 10.5916 | 10.9442 | 11.4207 | 12.4605 | 0.1 | 5 | 5.1 | 5.2 | 5.3 | 5.4 | 5.5 | 5.6 | 5.7 | 5.8 | 5.9 | 6 | 6.1 | 6.2 | 6.3 | 6.4 | 6.5 | 6.6 | 6.7 | 6.8 | 6.9 | 7 | 7.1 | 7.2 | 7.3 | 7.4 | 7.5 | 7.6 | 7.7 | 7.8 | 7.9 | 8 | 8.1 | 8.2 | 8.3 | 8.4 | 8.5 | 8.6 | 8.7 | 8.8 | 8.9 | 9 | 9.1 | 9.2 | 9.3 | 9.4 | 9.5 | 9.6 | 9.7 | 9.8 | 9.9 | 10 | 10.1 | 10.2 | 10.3 | 10.4 | 10.5 | 10.6 | 10.7 | 10.8 | 10.9 | 11 | 11.1 | 11.2 | 11.3 | 11.4 | 11.5 | 11.6 | 11.7 | 11.8 | 11.9 | 12 | 12.1 | 12.2 | 12.3 | 12.4 | 12.5 | 12.6 | 12.7 | 12.8 | 12.9 | 13 | 13.1 | 13.2 | 13.3 | 13.4 | 13.5 | 13.6 | 13.7 | 13.8 | 13.9 | 14 | 14.1 | 14.2 | 14.3 | 14.4 | 14.5 | 14.6 | 14.7 | 14.8 | 14.9 | 14.999 | 0 | 8.4389e-14 | 3.9434e-11 | 1.3823e-09 | 1.6771e-08 | 1.1371e-07 | 5.3343e-07 | 1.94e-06 | 5.8542e-06 | 1.5315e-05 | 3.5789e-05 | 7.6316e-05 | 0.00015085 | 0.00027973 | 0.00049114 | 0.00082255 | 0.0013218 | 0.0020479 | 0.0030715 | 0.0044742 | 0.0063482 | 0.008794 | 0.011919 | 0.015832 | 0.020644 | 0.026459 | 0.033374 | 0.041471 | 0.050814 | 0.061443 | 0.073374 | 0.08659 | 0.10104 | 0.11665 | 0.13328 | 0.1508 | 0.16901 | 0.18769 | 0.20661 | 0.22549 | 0.24404 | 0.26199 | 0.27904 | 0.29489 | 0.30927 | 0.32192 | 0.33261 | 0.34114 | 0.34735 | 0.35113 | 0.35239 | 0.35113 | 0.34735 | 0.34114 | 0.33261 | 0.32192 | 0.30927 | 0.29489 | 0.27904 | 0.26199 | 0.24404 | 0.22549 | 0.20661 | 0.18769 | 0.16901 | 0.1508 | 0.13328 | 0.11665 | 0.10104 | 0.08659 | 0.073374 | 0.061443 | 0.050814 | 0.041471 | 0.033374 | 0.026459 | 0.020644 | 0.015832 | 0.011919 | 0.008794 | 0.0063482 | 0.0044742 | 0.0030715 | 0.0020479 | 0.0013218 | 0.00082255 | 0.00049114 | 0.00027973 | 0.00015085 | 7.6316e-05 | 3.5789e-05 | 1.5315e-05 | 5.8542e-06 | 1.94e-06 | 5.3343e-07 | 1.1371e-07 | 1.6771e-08 | 1.3823e-09 | 3.9434e-11 | 8.4389e-14 | 9.2295e-32
Production migration | 2 | 2021-07-13 | 2021-07-15 |  |  | 1 | 2 | 3 |  |  | 1 | 50 | EQ | No skew | 1 | 2 | Extremely High Confidence | 2 | 15 | 15 |  | 2 | 0.1796 | 0.032256 | 2 | 50% | 2.154 | 2.296 | 1.7673 | 1.846 | 1.9037 | 1.9534 | 2 | 2.0466 | 2.0963 | 2.154 | 2.2327 | 2.4093 | 0.02 | 1 | 1.02 | 1.04 | 1.06 | 1.08 | 1.1 | 1.12 | 1.14 | 1.16 | 1.18 | 1.2 | 1.22 | 1.24 | 1.26 | 1.28 | 1.3 | 1.32 | 1.34 | 1.36 | 1.38 | 1.4 | 1.42 | 1.44 | 1.46 | 1.48 | 1.5 | 1.52 | 1.54 | 1.56 | 1.58 | 1.6 | 1.62 | 1.64 | 1.66 | 1.68 | 1.7 | 1.72 | 1.74 | 1.76 | 1.78 | 1.8 | 1.82 | 1.84 | 1.86 | 1.88 | 1.9 | 1.92 | 1.94 | 1.96 | 1.98 | 2 | 2.02 | 2.04 | 2.06 | 2.08 | 2.1 | 2.12 | 2.14 | 2.16 | 2.18 | 2.2 | 2.22 | 2.24 | 2.26 | 2.28 | 2.3 | 2.32 | 2.34 | 2.36 | 2.38 | 2.4 | 2.42 | 2.44 | 2.46 | 2.48 | 2.5 | 2.52 | 2.54 | 2.56 | 2.58 | 2.6 | 2.62 | 2.64 | 2.66 | 2.68 | 2.7 | 2.72 | 2.74 | 2.76 | 2.78 | 2.8 | 2.82 | 2.84 | 2.86 | 2.88 | 2.9 | 2.92 | 2.94 | 2.96 | 2.98 | 2.999 | 0 | 5.0534e-20 | 7.1825e-16 | 1.8163e-13 | 8.8172e-12 | 1.7314e-10 | 1.9169e-09 | 1.4283e-08 | 7.9613e-08 | 3.5536e-07 | 1.3307e-06 | 4.3217e-06 | 1.2473e-05 | 3.2596e-05 | 7.8246e-05 | 0.00017452 | 0.00036499 | 0.00072122 | 0.0013549 | 0.0024324 | 0.0041915 | 0.0069589 | 0.011167 | 0.017368 | 0.026245 | 0.038611 | 0.055407 | 0.077679 | 0.10655 | 0.14318 | 0.1887 | 0.24414 | 0.3104 | 0.38809 | 0.47754 | 0.57867 | 0.69095 | 0.81336 | 0.94438 | 1.082 | 1.2236 | 1.3665 | 1.5072 | 1.6425 | 1.7687 | 1.8825 | 1.9807 | 2.0603 | 2.1189 | 2.1549 | 2.167 | 2.1549 | 2.1189 | 2.0603 | 1.9807 | 1.8825 | 1.7687 | 1.6425 | 1.5072 | 1.3665 | 1.2236 | 1.082 | 0.94438 | 0.81336 | 0.69095 | 0.57867 | 0.47754 | 0.38809 | 0.3104 | 0.24414 | 0.1887 | 0.14318 | 0.10655 | 0.077679 | 0.055407 | 0.038611 | 0.026245 | 0.017368 | 0.011167 | 0.0069589 | 0.0041915 | 0.0024324 | 0.0013549 | 0.00072122 | 0.00036499 | 0.00017452 | 7.8246e-05 | 3.2596e-05 | 1.2473e-05 | 4.3217e-06 | 1.3307e-06 | 3.5536e-07 | 7.9613e-08 | 1.4283e-08 | 1.9169e-09 | 1.7314e-10 | 8.8172e-12 | 1.8163e-13 | 7.1825e-16 | 5.0534e-20 | 3.5256e-38
Project closure | 11 | 2021-07-15 | 2021-07-30 | -20% |  | 8 | 10 | 12 |  | 20% | 1 | 50 | EQ | No skew | 1 | 10 | Very High Confidence | 3 | 10 | 10 |  | 10 | 0.4364 | 0.19044 | 10 | 50% | 10.3777 | 10.7197 | 9.4317 | 9.6223 | 9.7634 | 9.8854 | 10 | 10.1146 | 10.2366 | 10.3777 | 10.5683 | 10.9842 | 0.04 | 8 | 8.04 | 8.08 | 8.12 | 8.16 | 8.2 | 8.24 | 8.28 | 8.32 | 8.36 | 8.4 | 8.44 | 8.48 | 8.52 | 8.56 | 8.6 | 8.64 | 8.68 | 8.72 | 8.76 | 8.8 | 8.84 | 8.88 | 8.92 | 8.96 | 9 | 9.04 | 9.08 | 9.12 | 9.16 | 9.2 | 9.24 | 9.28 | 9.32 | 9.36 | 9.4 | 9.44 | 9.48 | 9.52 | 9.56 | 9.6 | 9.64 | 9.68 | 9.72 | 9.76 | 9.8 | 9.84 | 9.88 | 9.92 | 9.96 | 10 | 10.04 | 10.08 | 10.12 | 10.16 | 10.2 | 10.24 | 10.28 | 10.32 | 10.36 | 10.4 | 10.44 | 10.48 | 10.52 | 10.56 | 10.6 | 10.64 | 10.68 | 10.72 | 10.76 | 10.8 | 10.84 | 10.88 | 10.92 | 10.96 | 11 | 11.04 | 11.08 | 11.12 | 11.16 | 11.2 | 11.24 | 11.28 | 11.32 | 11.36 | 11.4 | 11.44 | 11.48 | 11.52 | 11.56 | 11.6 | 11.64 | 11.68 | 11.72 | 11.76 | 11.8 | 11.84 | 11.88 | 11.92 | 11.96 | 11.999 | 0 | 2.1097e-13 | 9.8586e-11 | 3.4558e-09 | 4.1927e-08 | 2.8428e-07 | 1.3336e-06 | 4.85e-06 | 1.4636e-05 | 3.8288e-05 | 8.9473e-05 | 0.00019079 | 0.00037712 | 0.00069931 | 0.0012279 | 0.0020564 | 0.0033045 | 0.0051198 | 0.0076787 | 0.011186 | 0.01587 | 0.021985 | 0.029796 | 0.03958 | 0.05161 | 0.066149 | 0.083436 | 0.10368 | 0.12703 | 0.15361 | 0.18344 | 0.21647 | 0.2526 | 0.29161 | 0.33321 | 0.377 | 0.42252 | 0.46923 | 0.51652 | 0.56371 | 0.61011 | 0.65499 | 0.6976 | 0.73722 | 0.77317 | 0.8048 | 0.83152 | 0.85285 | 0.86838 | 0.87782 | 0.88099 | 0.87782 | 0.86838 | 0.85285 | 0.83152 | 0.8048 | 0.77317 | 0.73722 | 0.6976 | 0.65499 | 0.61011 | 0.56371 | 0.51652 | 0.46923 | 0.42252 | 0.377 | 0.33321 | 0.29161 | 0.2526 | 0.21647 | 0.18344 | 0.15361 | 0.12703 | 0.10368 | 0.083436 | 0.066149 | 0.05161 | 0.03958 | 0.029796 | 0.021985 | 0.01587 | 0.011186 | 0.0076787 | 0.0051198 | 0.0033045 | 0.0020564 | 0.0012279 | 0.00069931 | 0.00037712 | 0.00019079 | 8.9473e-05 | 3.8288e-05 | 1.4636e-05 | 4.85e-06 | 1.3336e-06 | 2.8428e-07 | 4.1927e-08 | 3.4558e-09 | 9.8586e-11 | 2.1097e-13 | 8.7901e-28
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[39 empty] | 0: #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| 245 |  |  |  |  | 137.75 | 197 | 310 | [8 empty] | © 2015-2020, William W. Davis, MSPM, PMP |  |  |  |  | 205.2053 | 13.3575 | 178.4223 | 244 | 99.82% | 230.9159 | 255.971 | 168.2886 | 178.6812 | 187.3117 | 195.328 | 203.2453 | 211.454 | 220.4136 | 230.9159 | 245.0544 | 273.6918 | 165.1328 | 165.9263 | 166.7198 | 167.5133 | 168.3069 | 169.1004 | 169.8939 | 170.6874 | 171.4809 | 172.2744 | 173.0679 | 173.8615 | 174.655 | 175.4485 | 176.242 | 177.0355 | 177.829 | 178.6225 | 179.4161 | 180.2096 | 181.0031 | 181.7966 | 182.5901 | 183.3836 | 184.1771 | 184.9706 | 185.7642 | 186.5577 | 187.3512 | 188.1447 | 188.9382 | 189.7317 | 190.5252 | 191.3188 | 192.1123 | 192.9058 | 193.6993 | 194.4928 | 195.2863 | 196.0798 | 196.8734 | 197.6669 | 198.4604 | 199.2539 | 200.0474 | 200.8409 | 201.6344 | 202.428 | 203.2215 | 204.015 | 204.8085 | 205.602 | 206.3955 | 207.189 | 207.9825 | 208.7761 | 209.5696 | 210.3631 | 211.1566 | 211.9501 | 212.7436 | 213.5371 | 214.3307 | 215.1242 | 215.9177 | 216.7112 | 217.5047 | 218.2982 | 219.0917 | 219.8853 | 220.6788 | 221.4723 | 222.2658 | 223.0593 | 223.8528 | 224.6463 | 225.4399 | 226.2334 | 227.0269 | 227.8204 | 228.6139 | 229.4074 | 230.2009 | 230.9944 | 231.788 | 232.5815 | 233.375 | 234.1685 | 234.962 | 235.7555 | 236.549 | 237.3426 | 238.1361 | 238.9296 | 239.7231 | 240.5166 | 241.3101 | 242.1036 | 242.8972 | 243.6907 | 244.4842 | 245.2777 | 0.00039582 | 0.00047054 | 0.00055739 | 0.00065795 | 0.00077392 | 0.00090712 | 0.0010595 | 0.0012331 | 0.0014301 | 0.0016528 | 0.0019034 | 0.0021842 | 0.0024977 | 0.0028461 | 0.0032316 | 0.0036565 | 0.0041226 | 0.0046318 | 0.0051856 | 0.0057851 | 0.0064312 | 0.0071242 | 0.0078641 | 0.0086503 | 0.0094816 | 0.010356 | 0.011271 | 0.012225 | 0.013211 | 0.014228 | 0.015268 | 0.016327 | 0.017398 | 0.018474 | 0.019547 | 0.020609 | 0.021653 | 0.02267 | 0.02365 | 0.024587 | 0.02547 | 0.026292 | 0.027045 | 0.027721 | 0.028314 | 0.028818 | 0.029228 | 0.029539 | 0.029748 | 0.029853 | 0.029853 | 0.029748 | 0.029539 | 0.029228 | 0.028818 | 0.028314 | 0.027721 | 0.027045 | 0.026292 | 0.02547 | 0.024587 | 0.02365 | 0.02267 | 0.021653 | 0.020609 | 0.019547 | 0.018474 | 0.017398 | 0.016327 | 0.015268 | 0.014228 | 0.013211 | 0.012225 | 0.011271 | 0.010356 | 0.0094816 | 0.0086503 | 0.0078641 | 0.0071242 | 0.0064312 | 0.0057851 | 0.0051856 | 0.0046318 | 0.0041226 | 0.0036565 | 0.0032316 | 0.0028461 | 0.0024977 | 0.0021842 | 0.0019034 | 0.0016528 | 0.0014301 | 0.0012331 | 0.0010595 | 0.00090712 | 0.00077392 | 0.00065795 | 0.00055739 | 0.00047054 | 0.00039582 | 0.00033179
| 10 | Optional schedule contingency
[6 empty] | Do not show currency formatting | [16 empty] | Whole project or portfolio planning estimate |  | 1500 | 100% | 216.4472 | 227.1764 | 188.0869 | 193.9633 | 198.2006 | 201.8212 | 205.2053 | 208.5893 | 212.2099 | 216.4472 | 222.3236 | 236.2794 | 0: 0.00039582 | 0.00047054 | 0.00055739 | 0.00065795 | 0.00077392 | 0.00090712 | 0.0010595 | 0.0012331 | 0.0014301 | 0.0016528 | 0.0019034 | 0.0021842 | 0.0024977 | 0.0028461 | 0.0032316 | 0.0036565 | 0.0041226 | 0.0046318 | 0.0051856 | 0.0057851 | 0.0064312 | 0.0071242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Non-work Day Description | Date | [37 empty] | 0: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0078641 | 0.0086503 | 0.0094816 | 0.010356 | 0.011271 | 0.012225 | 0.013211 | 0.014228 | 0.015268 | 0.016327 | 0.017398 | 0.018474 | 0.019547 | 0.020609 | 0.021653 | 0.02267 | 0.02365 | 0.024587 | 0.02547 | 0.026292 | 0.027045 | 0.027721 | 0.028314 | 0.028818 | 0.029228 | 0.029539 | 0.029748 | 0.029853 | 0.029853 | 0.029748 | 0.029539 | 0.029228 | 0.028818 | 0.028314 | 0.027721 | 0.027045 | 0.026292 | 0.02547 | 0.024587 | 0.02365 | 0.02267 | 0.021653 | 0.020609 | 0.019547 | 0.018474 | 0.017398 | 0.016327 | 0.015268 | 0.014228 | 0.013211 | 0.012225 | 0.011271 | 0.010356 | 0.0094816 | 0.0086503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Labor Day (USA) | 2020-09-07 | [5 empty] | With | 90% | confidence | [29 empty] | 0: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0078641 | 0.0071242 | 0.0064312 | 0.0057851 | 0.0051856 | 0.0046318 | 0.0041226 | 0.0036565 | 0.0032316 | 0.0028461 | 0.0024977 | 0.0021842 | 0.0019034 | 0.0016528 | 0.0014301 | 0.0012331 | 0.0010595 | 0.00090712 | 0.00077392 | 0.00065795 | 0.00055739 | 0.00047054 | 0.00039582 | 0.00033179
Thanksgiving Day (USA) | 2020-11-26 | [5 empty] | The lowerbound threshold is | 183.2341 | [30 empty] | 0: 0.00039582 | 0.00047054 | 0.00055739 | 0.00065795 | 0.00077392 | 0.00090712 | 0.0010595 | 0.0012331 | 0.0014301 | 0.0016528 | 0.0019034 | 0.0021842 | 0.0024977 | 0.0028461 | 0.0032316 | 0.0036565 | 0.0041226 | 0.0046318 | 0.0051856 | 0.0057851 | 0.0064312 | 0.0071242 | 0.0078641 | 0.0086503 | 0.0094816 | 0.010356 | 0.011271 | 0.012225 | 0.013211 | 0.014228 | 0.015268 | 0.016327 | 0.017398 | 0.018474 | 0.019547 | 0.020609 | 0.021653 | 0.02267 | 0.02365 | 0.024587 | 0.02547 | 0.026292 | 0.027045 | 0.027721 | 0.028314 | 0.028818 | 0.029228 | 0.029539 | 0.029748 | 0.029853 | 0.029853 | 0.029748 | 0.029539 | 0.029228 | 0.028818 | 0.028314 | 0.027721 | 0.027045 | 0.026292 | 0.02547 | 0.024587 | 0.02365 | 0.02267 | 0.021653 | 0.020609 | 0.019547 | 0.018474 | 0.017398 | 0.016327 | 0.015268 | 0.014228 | 0.013211 | 0.012225 | 0.011271 | 0.010356 | 0.0094816 | 0.0086503 | 0.0078641 | 0.0071242 | 0.0064312 | 0.0057851 | 0.0051856 | 0.0046318 | 0.0041226 | 0.0036565 | 0.0032316 | 0.0028461 | 0.0024977 | 0.0021842 | 0.0019034 | 0.0016528 | 0.0014301 | 0.0012331 | 0.0010595 | 0.00090712 | 0.00077392 | 0.00065795 | 0.00055739 | 0.00047054 | 0.00039582 | 0.00033179
Day after Thanksgiving Day (USA) | 2020-11-27 | [5 empty] | and the upperbound threshold is | 227.1764
Christmas Break | 2020-12-21
Christmas Break | 2020-12-22 | [5 empty] | Between a lowerbound value of | 183
Christmas Break | 2020-12-23 | [5 empty] | and an upperbound value of | 227
Christmas Break | 2020-12-24 | [5 empty] | the range probability is | 90.04%
Christmas Break | 2020-12-25 | [5 empty] | where, below the lowerbound, the % is | 4.822%
New Years Break | 2020-12-28 | [5 empty] | and above the upperbound, the % is | 5.138%
New Years Break | 2020-12-29
New Years Break | 2020-12-30
New Year's Eve | 2020-12-31
New Year's Day | 2021-01-01
Memorial Day (USA) | 2021-05-31
Independence Day, observed (USA) | 2021-07-02
Labor Day (USA) | 2021-09-06
Thanksgiving Day (USA) | 2021-11-25
Day after Thanksgiving Day (USA) | 2021-11-26
Christmas Break | 2021-12-20
Christmas Break | 2021-12-21
Christmas Break | 2021-12-22
Christmas Break | 2021-12-23
Christmas Break | 2021-12-24
New Year's Break | 2021-12-27
New Year's Break | 2021-12-28
New Year's Break | 2021-12-29
New Year's Break | 2021-12-30
New Year's Eve | 2021-12-31
New Year's Day (observed) | 2022-01-03
To use this template:
1) Create a 3-point estimate under the Minimum, Most Likely, and Maximum columns
2) Render a subjective judgment about how likely the Most Likely outcome is, under the Most Likely Confidence column
3) Examine the SPERT probabilistic estimates for various confidence levels
Optionally:
Enter any desired estimate under the Planning Estimate column to find the SPERT probability for the planning estimate
Version 3.0.s – © 2015-2020, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Subscribe to the SPERT® newsletter for monthly tips, free webinars, and new release notifications
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).
After you finish entering your estimates above, use this area to calculate the probability of all uncertainties together. This is especially useful for creating a forecast for an entire project, for example.
Choose the confidence you want for the confidence interval in cell D108, and/or choose the confidence lower and upperbound thresholds in cells D112 and D113.
Both the pie chart and tri-colored, bell-curve combo chart below represent the uncertainty of summary row #104 and assume that the Central Limit Theorem applies to that row.
IMPORTANT DISCLOSURE!
The charts on this worksheet assume that the Central Limit Theorem applies to summary row #104, which may or may not be true.
Be sure to understand the Central Limit Theorem and validate that it applies to your estimated uncertainties in rows 4-103 before relying on the probabilities shown in row 106 or the the summary charts in this worksheet.
Click for help
Note on B1: Enter the project start date is cell C1. The project finish date in cell D2 is calculated based upon the activity duration estimates in column B, which are calculated based upon the specified reliability in cell B2.
Note on D1: This finish date excludes weekend days and all other non-work days listed in the table below. It adds the optional schedule contingency value from cell B105 (if any).
Note on A2: SPERT Scheduler only works for a project's critical path, and the critical path must be sequentially ordered and have no concurrent tasks or activities. Be aware of the limitations of this approach to scheduling. SPERT Scheduler cannot address merge bias, for instance. Only a full Monte Carlo simulation of the entire project schedule can evaluate shifting critical paths (merge bias) and different kinds of probability distributions at the activity or task level.
Note on B2: Choose any probability between 50% and 99% and SPERT will calculate the duration estimates needed to achieve your desired reliability level. Choosing more reliable estimates will increase the project timeline. Choosing less reliable estimates will shrink the overall project schedule, but there will be an increased chance the project will finish late. To buffer the project for instances where scheduled activities take longer to finish than you planned for, add a schedule contingency in cell B105. Use Soothsayer™ for Project Contingency to calculate how big that buffer should be. It's a bonus download on the Statistical PERT website.
Note on D2: This calculates the likelihood of the project finishing on-time without a schedule contingency. This calculation assumes that Parkinson's Law applies to the project: "Work expands so as to fill the time available for its completion." Commonly, project activities only finish on-time or late; they rarely finish early, even if a statistical model suggests that they should.
Note on Z2: You may optionally enter a planning estimate for each uncertainty you enter, and see its cumulative probability result in the 'SPERT Probability' column. The cumulative probability is the likelihood your planning estimate will be EQUAL TO or GREATER THAN the uncertainty you are estimating. Choosing a larger planning estimate will increase the cumulative probability, and choosing a smaller planning estimate will decrease the cumulative probability.
Note on AA2: The SPERT Probability shows the cumulative probability of each Planning Estimate you entered in column Z. If you select 'Show Left-Side Area' in cell Z1, this column shows the likelihood that your Planning Estimate will be EQUAL TO or GREATER THAN the uncertainty you are estimating. If you select 'Show Right-Side Area' in cell Z1, this column shows the likelihood that the uncertainty will EXCEED your Planning Estimate in column AA.
Note on A3: Use this column to add critical path activities or tasks for a project. The list of activities or tasks must be sequential, not concurrent.
Note on B3: This column calculates the activity or task duration with the reliability specified in cell B2.
Note on E3: Optionally, choose a minimum point-estimate for a single uncertainty by selecting a dropdown value in this column for any row. The percentage you choose will reduce the row's Most Likely point-estimate, and it will override the minimum point-estimate calculated by the heuristic in cell G2.
Note on F3: Optionally, manually enter a minimum point-estimate for a single uncertainty by entering a specific value in this column for any row. The value you enter will override the row's calculated, mininum point-estimate using percentage adjustments.
Note on G3: Use a simple heuristic to quickly create MINIMUM point-estimates for all rows. Do this by selecting a percentage in cell G2. Minimum point-estimates are automatically created for you by taking the Most Likely point-estimate in column H and reducing it by the percentage value specified in cell G2. Optionally, choose a row-speciific heuristic by selecting a percentage in column E, or enter a specific minimum point-estimate in column F. (If you need to modify the dropdown choices in cell G2 or column E, you can do that in the Vlookups worksheet).
Note on H3: The Most Likely point-estimate represents the value you believe will most likely occur for each uncertainty, although many other possible outcomes exist between the Minimum and Maximum point-estimates.
Note on I3: Use a simple heuristic to quickly create MAXIMUM point-estimates for all rows. Do this by selecting a percentage in cell I2. Maximum point-estimates are automatically created for you by taking the Most Likely point-estimate in column H and increasing it by the percentage value specified in cell I2. Optionally, choose a row-speciific heuristic by selecting a percentage in column K, or enter a specific maximum point-estimate in column J. (If you need to modify the dropdown choices in cell I2 or column K, you can do that in the Vlookups worksheet).
Note on J3: Optionally, manually enter a maximum point-estimate for a single uncertainty by entering a specific value in this column for any row. The value you enter will override the row's calculated, maximum point-estimate using percentage adjustments.
Note on K3: Optionally, choose a maximum point-estimate for a single uncertainty by selecting a dropdown value in this column for any row. The percentage you choose will increase the row's Most Likely point-estimate, and it will override the maximum point-estimate calculated by the heuristic in cell I2.
Note on L3: This checks that a proper 3-point estimate was entered: Minimum value must be > 0 and < Most Likely Most Likely must be > Minimum and < Maximum Maximum must be > Most Likely
Note on R3: The shape of the bell-curve is heavily influenced by how confident you believe the Most Likely outcome will occur relative to other, possible outcomes between the Minimum and Maximum point-estimates. When you are more confident in the Most Likely outcome, the bell-curve grows taller, and there is a shrinking likelihood of other occurrences near the Minimum and Maximum point-estimates. Conversely, when you are less confident in the Most Likely outcome, the bell-curve grows flatter, and there is a rising likelihood of other occurrences near the Minimum and Maximum point-estimates. (You can add to, remove, or modify the dropdown control options using the VLookups worksheet).
Note on V3: William Davis: SPERT builds an implied, bell-shaped curve to represent the risk characteristics for your uncertainty. The flatter, wider the bell-curve curve is, the more uncertain the outcomes are over the feasible region. If the bell-curve's vertical rise is steep, though, your uncertainty has much less volatility near the most likely outcome. If the bell-curve is both centered and symmetrical, it fits a normal distribution. The beta distribution can also show skewed bell-curves, dependent on your 3-point estimate and how likely the most likely outcome really is.
Note on B105: Download Soothsayer™ for Project Contingency from the Statistical PERT website and calculate a right-sized, risk-adjusted schedule contingency. It's another free download!

## SPERT® Beta - Charts
| Statistical PERT® (SPERT®) Beta Edition Beta Distribution Charts | [15 empty] | Show Left-Side Area |  | Show the likelihood that the SPERT estimates will be EQUAL TO or GREATER THAN an uncertainty
[17 empty] | Planning Estimate | SPERT Beta Probability | SPERT Probabilistic Estimates using the BETA distribution | [11 empty] | This section is only to build Line Sparklines to show the bell-shaped curve for each row, and the summary bell-curve chart.
ID | Minimum | Most Likely | Maximum |  | Range % | R/L Skew | Skew Analysis | X | Midpoint | Most Likely Confidence | Y | Alpha | Beta | Mean | SPERT SD | Variance |  |  | 5% | 95% | 10% | 20% | 30% | 40% | 50% | 60% | 70% | 80% | 90% | 99% | x-axis increments (magenta in blue cells shows the increment, the next 101 columns are the x-axis values for the Line Sparkline column and summary bell-curve chart) | [201 empty] | These are the y-axis values with which the bell-shaped curve is built (used only for the Line SparkLine column) | [200 empty] | ← Columns AH through PT are hidden; they are used to create Sparklines and the bell-curve bar chart
1 | 60 | 120 | 240 | 1 | 33.3333 | R | Slight skew | 3 | 150 | Medium Confidence | 6 | 2.5 | 4 | 129.228 | 31.968 | 1021.953 | 160 | 81.7% | 80.6675 | 185.5319 | 88.3784 | 99.7938 | 109.3262 | 118.2031 | 126.9838 | 136.0975 | 146.0522 | 157.7256 | 173.4327 | 205.0138 | 0.9 | 60 | 60.9 | 61.8 | 62.7 | 63.6 | 64.5 | 65.4 | 66.3 | 67.2 | 68.1 | 69 | 69.9 | 70.8 | 71.7 | 72.6 | 73.5 | 74.4 | 75.3 | 76.2 | 77.1 | 78 | 78.9 | 79.8 | 80.7 | 81.6 | 82.5 | 83.4 | 84.3 | 85.2 | 86.1 | 87 | 87.9 | 88.8 | 89.7 | 90.6 | 91.5 | 92.4 | 93.3 | 94.2 | 95.1 | 96 | 96.9 | 97.8 | 98.7 | 99.6 | 100.5 | 101.4 | 102.3 | 103.2 | 104.1 | 105 | 105.9 | 106.8 | 107.7 | 108.6 | 109.5 | 110.4 | 111.3 | 112.2 | 113.1 | 114 | 114.9 | 115.8 | 116.7 | 117.6 | 118.5 | 119.4 | 120.3 | 121.2 | 122.1 | 123 | 123.9 | 124.8 | 125.7 | 126.6 | 127.5 | 128.4 | 129.3 | 130.2 | 131.1 | 132 | 132.9 | 133.8 | 134.7 | 135.6 | 136.5 | 137.4 | 138.3 | 139.2 | 140.1 | 141 | 141.9 | 142.8 | 143.7 | 144.6 | 145.5 | 146.4 | 147.3 | 148.2 | 149.1 | 150 | 150.9 | 151.8 | 152.7 | 153.6 | 154.5 | 155.4 | 156.3 | 157.2 | 158.1 | 159 | 159.9 | 160.8 | 161.7 | 162.6 | 163.5 | 164.4 | 165.3 | 166.2 | 167.1 | 168 | 168.9 | 169.8 | 170.7 | 171.6 | 172.5 | 173.4 | 174.3 | 175.2 | 176.1 | 177 | 177.9 | 178.8 | 179.7 | 180.6 | 181.5 | 182.4 | 183.3 | 184.2 | 185.1 | 186 | 186.9 | 187.8 | 188.7 | 189.6 | 190.5 | 191.4 | 192.3 | 193.2 | 194.1 | 195 | 195.9 | 196.8 | 197.7 | 198.6 | 199.5 | 200.4 | 201.3 | 202.2 | 203.1 | 204 | 204.9 | 205.8 | 206.7 | 207.6 | 208.5 | 209.4 | 210.3 | 211.2 | 212.1 | 213 | 213.9 | 214.8 | 215.7 | 216.6 | 217.5 | 218.4 | 219.3 | 220.2 | 221.1 | 222 | 222.9 | 223.8 | 224.7 | 225.6 | 226.5 | 227.4 | 228.3 | 229.2 | 230.1 | 231 | 231.9 | 232.8 | 233.7 | 234.6 | 235.5 | 236.4 | 237.3 | 238.2 | 239.1 | 239.999 | 0 | 6.9837e-05 | 0.00019457 | 0.00035205 | 0.00053381 | 0.00073465 | 0.00095095 | 0.0011799 | 0.0014193 | 0.0016672 | 0.0019221 | 0.0021827 | 0.0024478 | 0.0027162 | 0.0029871 | 0.0032597 | 0.0035331 | 0.0038067 | 0.0040799 | 0.004352 | 0.0046226 | 0.0048912 | 0.0051573 | 0.0054205 | 0.0056804 | 0.0059367 | 0.0061892 | 0.0064374 | 0.0066811 | 0.0069201 | 0.0071541 | 0.0073829 | 0.0076064 | 0.0078243 | 0.0080365 | 0.0082429 | 0.0084433 | 0.0086375 | 0.0088256 | 0.0090074 | 0.0091828 | 0.0093517 | 0.0095141 | 0.00967 | 0.0098192 | 0.0099618 | 0.010098 | 0.010227 | 0.010349 | 0.010465 | 0.010574 | 0.010677 | 0.010772 | 0.010862 | 0.010944 | 0.01102 | 0.011089 | 0.011152 | 0.011208 | 0.011258 | 0.011301 | 0.011339 | 0.01137 | 0.011395 | 0.011413 | 0.011426 | 0.011433 | 0.011434 | 0.011429 | 0.011419 | 0.011403 | 0.011381 | 0.011354 | 0.011322 | 0.011285 | 0.011242 | 0.011195 | 0.011142 | 0.011085 | 0.011024 | 0.010957 | 0.010887 | 0.010812 | 0.010732 | 0.010649 | 0.010562 | 0.010471 | 0.010376 | 0.010278 | 0.010176 | 0.010071 | 0.0099624 | 0.0098509 | 0.0097364 | 0.0096191 | 0.009499 | 0.0093763 | 0.0092511 | 0.0091236 | 0.0089938 | 0.0088619 | 0.0087279 | 0.0085922 | 0.0084546 | 0.0083155 | 0.0081748 | 0.0080328 | 0.0078895 | 0.007745 | 0.0075996 | 0.0074532 | 0.007306 | 0.0071581 | 0.0070097 | 0.0068608 | 0.0067116 | 0.0065622 | 0.0064127 | 0.0062631 | 0.0061136 | 0.0059644 | 0.0058155 | 0.0056669 | 0.0055189 | 0.0053715 | 0.0052248 | 0.005079 | 0.004934 | 0.00479 | 0.0046471 | 0.0045054 | 0.0043649 | 0.0042258 | 0.0040881 | 0.003952 | 0.0038174 | 0.0036845 | 0.0035533 | 0.0034239 | 0.0032964 | 0.0031708 | 0.0030473 | 0.0029258 | 0.0028064 | 0.0026893 | 0.0025743 | 0.0024617 | 0.0023514 | 0.0022435 | 0.002138 | 0.002035 | 0.0019345 | 0.0018366 | 0.0017412 | 0.0016485 | 0.0015583 | 0.0014709 | 0.0013861 | 0.0013039 | 0.0012245 | 0.0011478 | 0.0010739 | 0.0010026 | 0.00093414 | 0.00086836 | 0.00080529 | 0.00074494 | 0.00068729 | 0.00063232 | 0.00058002 | 0.00053035 | 0.0004833 | 0.00043882 | 0.0003969 | 0.00035749 | 0.00032055 | 0.00028604 | 0.0002539 | 0.00022409 | 0.00019654 | 0.00017121 | 0.00014801 | 0.0001269 | 0.00010778 | 9.0596e-05 | 7.5259e-05 | 6.1685e-05 | 4.9787e-05 | 3.9473e-05 | 3.0648e-05 | 2.3209e-05 | 1.7053e-05 | 1.2071e-05 | 8.1499e-06 | 5.1723e-06 | 3.0164e-06 | 1.5563e-06 | 6.6159e-07 | 1.9752e-07 | 2.4877e-08 | 3.4383e-17
[233 empty] | 0 | 6.9837e-05 | 0.00019457 | 0.00035205 | 0.00053381 | 0.00073465 | 0.00095095 | 0.0011799 | 0.0014193 | 0.0016672 | 0.0019221 | 0.0021827 | 0.0024478 | 0.0027162 | 0.0029871 | 0.0032597 | 0.0035331 | 0.0038067 | 0.0040799 | 0.004352 | 0.0046226 | 0.0048912 | 0.0051573 | 0.0054205 | 0.0056804 | 0.0059367 | 0.0061892 | 0.0064374 | 0.0066811 | 0.0069201 | 0.0071541 | 0.0073829 | 0.0076064 | 0.0078243 | 0.0080365 | 0.0082429 | 0.0084433 | 0.0086375 | 0.0088256 | 0.0090074 | 0.0091828 | 0.0093517 | 0.0095141 | 0.00967 | 0.0098192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[233 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0099618 | 0.010098 | 0.010227 | 0.010349 | 0.010465 | 0.010574 | 0.010677 | 0.010772 | 0.010862 | 0.010944 | 0.01102 | 0.011089 | 0.011152 | 0.011208 | 0.011258 | 0.011301 | 0.011339 | 0.01137 | 0.011395 | 0.011413 | 0.011426 | 0.011433 | 0.011434 | 0.011429 | 0.011419 | 0.011403 | 0.011381 | 0.011354 | 0.011322 | 0.011285 | 0.011242 | 0.011195 | 0.011142 | 0.011085 | 0.011024 | 0.010957 | 0.010887 | 0.010812 | 0.010732 | 0.010649 | 0.010562 | 0.010471 | 0.010376 | 0.010278 | 0.010176 | 0.010071 | 0.0099624 | 0.0098509 | 0.0097364 | 0.0096191 | 0.009499 | 0.0093763 | 0.0092511 | 0.0091236 | 0.0089938 | 0.0088619 | 0.0087279 | 0.0085922 | 0.0084546 | 0.0083155 | 0.0081748 | 0.0080328 | 0.0078895 | 0.007745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | © 2015-2020, William W. Davis, MSPM, PMP | [222 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0075996 | 0.0074532 | 0.007306 | 0.0071581 | 0.0070097 | 0.0068608 | 0.0067116 | 0.0065622 | 0.0064127 | 0.0062631 | 0.0061136 | 0.0059644 | 0.0058155 | 0.0056669 | 0.0055189 | 0.0053715 | 0.0052248 | 0.005079 | 0.004934 | 0.00479 | 0.0046471 | 0.0045054 | 0.0043649 | 0.0042258 | 0.0040881 | 0.003952 | 0.0038174 | 0.0036845 | 0.0035533 | 0.0034239 | 0.0032964 | 0.0031708 | 0.0030473 | 0.0029258 | 0.0028064 | 0.0026893 | 0.0025743 | 0.0024617 | 0.0023514 | 0.0022435 | 0.002138 | 0.002035 | 0.0019345 | 0.0018366 | 0.0017412 | 0.0016485 | 0.0015583 | 0.0014709 | 0.0013861 | 0.0013039 | 0.0012245 | 0.0011478 | 0.0010739 | 0.0010026 | 0.00093414 | 0.00086836 | 0.00080529 | 0.00074494 | 0.00068729 | 0.00063232 | 0.00058002 | 0.00053035 | 0.0004833 | 0.00043882 | 0.0003969 | 0.00035749 | 0.00032055 | 0.00028604 | 0.0002539 | 0.00022409 | 0.00019654 | 0.00017121 | 0.00014801 | 0.0001269 | 0.00010778 | 9.0596e-05 | 7.5259e-05 | 6.1685e-05 | 4.9787e-05 | 3.9473e-05 | 3.0648e-05 | 2.3209e-05 | 1.7053e-05 | 1.2071e-05 | 8.1499e-06 | 5.1723e-06 | 3.0164e-06 | 1.5563e-06 | 6.6159e-07 | 1.9752e-07 | 2.4877e-08 | 3.4383e-17
[233 empty] | 0 | 6.9837e-05 | 0.00019457 | 0.00035205 | 0.00053381 | 0.00073465 | 0.00095095 | 0.0011799 | 0.0014193 | 0.0016672 | 0.0019221 | 0.0021827 | 0.0024478 | 0.0027162 | 0.0029871 | 0.0032597 | 0.0035331 | 0.0038067 | 0.0040799 | 0.004352 | 0.0046226 | 0.0048912 | 0.0051573 | 0.0054205 | 0.0056804 | 0.0059367 | 0.0061892 | 0.0064374 | 0.0066811 | 0.0069201 | 0.0071541 | 0.0073829 | 0.0076064 | 0.0078243 | 0.0080365 | 0.0082429 | 0.0084433 | 0.0086375 | 0.0088256 | 0.0090074 | 0.0091828 | 0.0093517 | 0.0095141 | 0.00967 | 0.0098192 | 0.0099618 | 0.010098 | 0.010227 | 0.010349 | 0.010465 | 0.010574 | 0.010677 | 0.010772 | 0.010862 | 0.010944 | 0.01102 | 0.011089 | 0.011152 | 0.011208 | 0.011258 | 0.011301 | 0.011339 | 0.01137 | 0.011395 | 0.011413 | 0.011426 | 0.011433 | 0.011434 | 0.011429 | 0.011419 | 0.011403 | 0.011381 | 0.011354 | 0.011322 | 0.011285 | 0.011242 | 0.011195 | 0.011142 | 0.011085 | 0.011024 | 0.010957 | 0.010887 | 0.010812 | 0.010732 | 0.010649 | 0.010562 | 0.010471 | 0.010376 | 0.010278 | 0.010176 | 0.010071 | 0.0099624 | 0.0098509 | 0.0097364 | 0.0096191 | 0.009499 | 0.0093763 | 0.0092511 | 0.0091236 | 0.0089938 | 0.0088619 | 0.0087279 | 0.0085922 | 0.0084546 | 0.0083155 | 0.0081748 | 0.0080328 | 0.0078895 | 0.007745 | 0.0075996 | 0.0074532 | 0.007306 | 0.0071581 | 0.0070097 | 0.0068608 | 0.0067116 | 0.0065622 | 0.0064127 | 0.0062631 | 0.0061136 | 0.0059644 | 0.0058155 | 0.0056669 | 0.0055189 | 0.0053715 | 0.0052248 | 0.005079 | 0.004934 | 0.00479 | 0.0046471 | 0.0045054 | 0.0043649 | 0.0042258 | 0.0040881 | 0.003952 | 0.0038174 | 0.0036845 | 0.0035533 | 0.0034239 | 0.0032964 | 0.0031708 | 0.0030473 | 0.0029258 | 0.0028064 | 0.0026893 | 0.0025743 | 0.0024617 | 0.0023514 | 0.0022435 | 0.002138 | 0.002035 | 0.0019345 | 0.0018366 | 0.0017412 | 0.0016485 | 0.0015583 | 0.0014709 | 0.0013861 | 0.0013039 | 0.0012245 | 0.0011478 | 0.0010739 | 0.0010026 | 0.00093414 | 0.00086836 | 0.00080529 | 0.00074494 | 0.00068729 | 0.00063232 | 0.00058002 | 0.00053035 | 0.0004833 | 0.00043882 | 0.0003969 | 0.00035749 | 0.00032055 | 0.00028604 | 0.0002539 | 0.00022409 | 0.00019654 | 0.00017121 | 0.00014801 | 0.0001269 | 0.00010778 | 9.0596e-05 | 7.5259e-05 | 6.1685e-05 | 4.9787e-05 | 3.9473e-05 | 3.0648e-05 | 2.3209e-05 | 1.7053e-05 | 1.2071e-05 | 8.1499e-06 | 5.1723e-06 | 3.0164e-06 | 1.5563e-06 | 6.6159e-07 | 1.9752e-07 | 2.4877e-08 | 3.4383e-17
|  | With | 60% | confidence
|  | The lowerbound threshold is | 99.7938
|  | and the upperbound threshold is | 157.7256
|  | Between a lowerbound value of | 100 |  | Miss the pie
|  | and an upperbound value of | 158 |  | chart? Press
|  | the range probability is | 60.01% |  | CTRL and 6
|  | The lowerbound area covers | 20.2% |  | to show the
|  | and the upperbound area covers | 19.79% |  | pie chart
Version 3.0.s – © 2015-2020, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Subscribe to the SPERT® newsletter for monthly tips, free webinars, and new release notifications
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).
Note on R2: You may optionally enter a planning estimate for each uncertainty you enter, and see its cumulative probability result in the 'SPERT Probability' column. The cumulative probability is the likelihood your planning estimate will be EQUAL TO or GREATER THAN the uncertainty you are estimating. Choosing a larger planning estimate will increase the cumulative probability, and choosing a smaller planning estimate will decrease the cumulative probability.
Note on S2: The SPERT Probability shows the cumulative probability of each Planning Estimate you entered in column R. If you select 'Show Left-Side Area' in cell R1, this column shows the likelihood that your Planning Estimate will be EQUAL TO or GREATER THAN the uncertainty you are estimating. If you select 'Show Right-Side Area' in cell R1, this column shows the likelihood that the uncertainty will EXCEED your Planning Estimate in column R.
Note on B3: The Minimum point-estimate represents the smallest value that is feasible, but highly improbable.
Note on C3: The Most Likely point-estimate represents the value you believe will most likely occur for each uncertainty, although many other possible outcomes exist between the Minimum and Maximum point-estimates.
Note on D3: The Maximum point-estimate represents the largest value that is feasible, but highly improbable
Note on E3: This checks that a proper 3-point estimate was entered: Minimum value must be > 0 and =< Most Likely Most Likely must be >= Minimum and =< Maximum Maximum must be >= Most Likely
Note on K3: The shape of the bell-curve is heavily influenced by how confident you believe the Most Likely outcome will occur relative to other, possible outcomes between the Minimum and Maximum point-estimates. When you are more confident in the Most Likely outcome, the bell-curve grows taller, and there is a shrinking likelihood of other occurrences near the Minimum and Maximum point-estimates. Conversely, when you are less confident in the Most Likely outcome, the bell-curve grows flatter, and there is a rising likelihood of other occurrences near the Minimum and Maximum point-estimates. (You can add to, remove, or modify the dropdown control options using the VLookups worksheet).
Click for help

## SPERT® Beta - MC Simulation
| Statistical PERT® (SPERT®) Beta Edition Beta Distribution Charts | [17 empty] | Show Left-Side Area |  | Show the likelihood that the SPERT estimates will be EQUAL TO or GREATER THAN an uncertainty
[19 empty] | Planning Estimate | SPERT Beta Probability | SPERT Probabilistic Estimates using the BETA distribution | [11 empty] | This section is only to build Line Sparklines to show the bell-shaped curve for each row, and the summary bell-curve chart.
ID | Minimum | Most Likely | Maximum |  | Range % | R/L Skew | Skew Analysis | X | Midpoint | Most Likely Confidence | Y | Alpha | Beta | Mean | SPERT SD | Variance | Rand() | Trial Outcome |  |  | 5% | 95% | 10% | 20% | 30% | 40% | 50% | 60% | 70% | 80% | 90% | 99% | x-axis increments (magenta in blue cells shows the increment, the next 101 columns are the x-axis values for the Line Sparkline column and summary bell-curve chart) | [201 empty] | These are the y-axis values with which the bell-shaped curve is built (used only for the Line SparkLine column) | [200 empty] | ← Columns AH through PT are hidden; they are used to create Sparklines and the bell-curve bar chart
1 | 60 | 120 | 240 | 1 | 33.3333 | R | Slight skew | 3 | 150 | Medium Confidence | 6 | 2.5 | 4 | 129.228 | 31.968 | 1021.953 | 0.83312 | 162.2699 | 160 | 81.7% | 80.6675 | 185.5319 | 88.3784 | 99.7938 | 109.3262 | 118.2031 | 126.9838 | 136.0975 | 146.0522 | 157.7256 | 173.4327 | 205.0138 | 0.9 | 60 | 60.9 | 61.8 | 62.7 | 63.6 | 64.5 | 65.4 | 66.3 | 67.2 | 68.1 | 69 | 69.9 | 70.8 | 71.7 | 72.6 | 73.5 | 74.4 | 75.3 | 76.2 | 77.1 | 78 | 78.9 | 79.8 | 80.7 | 81.6 | 82.5 | 83.4 | 84.3 | 85.2 | 86.1 | 87 | 87.9 | 88.8 | 89.7 | 90.6 | 91.5 | 92.4 | 93.3 | 94.2 | 95.1 | 96 | 96.9 | 97.8 | 98.7 | 99.6 | 100.5 | 101.4 | 102.3 | 103.2 | 104.1 | 105 | 105.9 | 106.8 | 107.7 | 108.6 | 109.5 | 110.4 | 111.3 | 112.2 | 113.1 | 114 | 114.9 | 115.8 | 116.7 | 117.6 | 118.5 | 119.4 | 120.3 | 121.2 | 122.1 | 123 | 123.9 | 124.8 | 125.7 | 126.6 | 127.5 | 128.4 | 129.3 | 130.2 | 131.1 | 132 | 132.9 | 133.8 | 134.7 | 135.6 | 136.5 | 137.4 | 138.3 | 139.2 | 140.1 | 141 | 141.9 | 142.8 | 143.7 | 144.6 | 145.5 | 146.4 | 147.3 | 148.2 | 149.1 | 150 | 150.9 | 151.8 | 152.7 | 153.6 | 154.5 | 155.4 | 156.3 | 157.2 | 158.1 | 159 | 159.9 | 160.8 | 161.7 | 162.6 | 163.5 | 164.4 | 165.3 | 166.2 | 167.1 | 168 | 168.9 | 169.8 | 170.7 | 171.6 | 172.5 | 173.4 | 174.3 | 175.2 | 176.1 | 177 | 177.9 | 178.8 | 179.7 | 180.6 | 181.5 | 182.4 | 183.3 | 184.2 | 185.1 | 186 | 186.9 | 187.8 | 188.7 | 189.6 | 190.5 | 191.4 | 192.3 | 193.2 | 194.1 | 195 | 195.9 | 196.8 | 197.7 | 198.6 | 199.5 | 200.4 | 201.3 | 202.2 | 203.1 | 204 | 204.9 | 205.8 | 206.7 | 207.6 | 208.5 | 209.4 | 210.3 | 211.2 | 212.1 | 213 | 213.9 | 214.8 | 215.7 | 216.6 | 217.5 | 218.4 | 219.3 | 220.2 | 221.1 | 222 | 222.9 | 223.8 | 224.7 | 225.6 | 226.5 | 227.4 | 228.3 | 229.2 | 230.1 | 231 | 231.9 | 232.8 | 233.7 | 234.6 | 235.5 | 236.4 | 237.3 | 238.2 | 239.1 | 239.999 | 0 | 6.9837e-05 | 0.00019457 | 0.00035205 | 0.00053381 | 0.00073465 | 0.00095095 | 0.0011799 | 0.0014193 | 0.0016672 | 0.0019221 | 0.0021827 | 0.0024478 | 0.0027162 | 0.0029871 | 0.0032597 | 0.0035331 | 0.0038067 | 0.0040799 | 0.004352 | 0.0046226 | 0.0048912 | 0.0051573 | 0.0054205 | 0.0056804 | 0.0059367 | 0.0061892 | 0.0064374 | 0.0066811 | 0.0069201 | 0.0071541 | 0.0073829 | 0.0076064 | 0.0078243 | 0.0080365 | 0.0082429 | 0.0084433 | 0.0086375 | 0.0088256 | 0.0090074 | 0.0091828 | 0.0093517 | 0.0095141 | 0.00967 | 0.0098192 | 0.0099618 | 0.010098 | 0.010227 | 0.010349 | 0.010465 | 0.010574 | 0.010677 | 0.010772 | 0.010862 | 0.010944 | 0.01102 | 0.011089 | 0.011152 | 0.011208 | 0.011258 | 0.011301 | 0.011339 | 0.01137 | 0.011395 | 0.011413 | 0.011426 | 0.011433 | 0.011434 | 0.011429 | 0.011419 | 0.011403 | 0.011381 | 0.011354 | 0.011322 | 0.011285 | 0.011242 | 0.011195 | 0.011142 | 0.011085 | 0.011024 | 0.010957 | 0.010887 | 0.010812 | 0.010732 | 0.010649 | 0.010562 | 0.010471 | 0.010376 | 0.010278 | 0.010176 | 0.010071 | 0.0099624 | 0.0098509 | 0.0097364 | 0.0096191 | 0.009499 | 0.0093763 | 0.0092511 | 0.0091236 | 0.0089938 | 0.0088619 | 0.0087279 | 0.0085922 | 0.0084546 | 0.0083155 | 0.0081748 | 0.0080328 | 0.0078895 | 0.007745 | 0.0075996 | 0.0074532 | 0.007306 | 0.0071581 | 0.0070097 | 0.0068608 | 0.0067116 | 0.0065622 | 0.0064127 | 0.0062631 | 0.0061136 | 0.0059644 | 0.0058155 | 0.0056669 | 0.0055189 | 0.0053715 | 0.0052248 | 0.005079 | 0.004934 | 0.00479 | 0.0046471 | 0.0045054 | 0.0043649 | 0.0042258 | 0.0040881 | 0.003952 | 0.0038174 | 0.0036845 | 0.0035533 | 0.0034239 | 0.0032964 | 0.0031708 | 0.0030473 | 0.0029258 | 0.0028064 | 0.0026893 | 0.0025743 | 0.0024617 | 0.0023514 | 0.0022435 | 0.002138 | 0.002035 | 0.0019345 | 0.0018366 | 0.0017412 | 0.0016485 | 0.0015583 | 0.0014709 | 0.0013861 | 0.0013039 | 0.0012245 | 0.0011478 | 0.0010739 | 0.0010026 | 0.00093414 | 0.00086836 | 0.00080529 | 0.00074494 | 0.00068729 | 0.00063232 | 0.00058002 | 0.00053035 | 0.0004833 | 0.00043882 | 0.0003969 | 0.00035749 | 0.00032055 | 0.00028604 | 0.0002539 | 0.00022409 | 0.00019654 | 0.00017121 | 0.00014801 | 0.0001269 | 0.00010778 | 9.0596e-05 | 7.5259e-05 | 6.1685e-05 | 4.9787e-05 | 3.9473e-05 | 3.0648e-05 | 2.3209e-05 | 1.7053e-05 | 1.2071e-05 | 8.1499e-06 | 5.1723e-06 | 3.0164e-06 | 1.5563e-06 | 6.6159e-07 | 1.9752e-07 | 2.4877e-08 | 3.4383e-17
[235 empty] | 0 | 6.9837e-05 | 0.00019457 | 0.00035205 | 0.00053381 | 0.00073465 | 0.00095095 | 0.0011799 | 0.0014193 | 0.0016672 | 0.0019221 | 0.0021827 | 0.0024478 | 0.0027162 | 0.0029871 | 0.0032597 | 0.0035331 | 0.0038067 | 0.0040799 | 0.004352 | 0.0046226 | 0.0048912 | 0.0051573 | 0.0054205 | 0.0056804 | 0.0059367 | 0.0061892 | 0.0064374 | 0.0066811 | 0.0069201 | 0.0071541 | 0.0073829 | 0.0076064 | 0.0078243 | 0.0080365 | 0.0082429 | 0.0084433 | 0.0086375 | 0.0088256 | 0.0090074 | 0.0091828 | 0.0093517 | 0.0095141 | 0.00967 | 0.0098192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[235 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0099618 | 0.010098 | 0.010227 | 0.010349 | 0.010465 | 0.010574 | 0.010677 | 0.010772 | 0.010862 | 0.010944 | 0.01102 | 0.011089 | 0.011152 | 0.011208 | 0.011258 | 0.011301 | 0.011339 | 0.01137 | 0.011395 | 0.011413 | 0.011426 | 0.011433 | 0.011434 | 0.011429 | 0.011419 | 0.011403 | 0.011381 | 0.011354 | 0.011322 | 0.011285 | 0.011242 | 0.011195 | 0.011142 | 0.011085 | 0.011024 | 0.010957 | 0.010887 | 0.010812 | 0.010732 | 0.010649 | 0.010562 | 0.010471 | 0.010376 | 0.010278 | 0.010176 | 0.010071 | 0.0099624 | 0.0098509 | 0.0097364 | 0.0096191 | 0.009499 | 0.0093763 | 0.0092511 | 0.0091236 | 0.0089938 | 0.0088619 | 0.0087279 | 0.0085922 | 0.0084546 | 0.0083155 | 0.0081748 | 0.0080328 | 0.0078895 | 0.007745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | © 2015-2020, William W. Davis, MSPM, PMP | [224 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0075996 | 0.0074532 | 0.007306 | 0.0071581 | 0.0070097 | 0.0068608 | 0.0067116 | 0.0065622 | 0.0064127 | 0.0062631 | 0.0061136 | 0.0059644 | 0.0058155 | 0.0056669 | 0.0055189 | 0.0053715 | 0.0052248 | 0.005079 | 0.004934 | 0.00479 | 0.0046471 | 0.0045054 | 0.0043649 | 0.0042258 | 0.0040881 | 0.003952 | 0.0038174 | 0.0036845 | 0.0035533 | 0.0034239 | 0.0032964 | 0.0031708 | 0.0030473 | 0.0029258 | 0.0028064 | 0.0026893 | 0.0025743 | 0.0024617 | 0.0023514 | 0.0022435 | 0.002138 | 0.002035 | 0.0019345 | 0.0018366 | 0.0017412 | 0.0016485 | 0.0015583 | 0.0014709 | 0.0013861 | 0.0013039 | 0.0012245 | 0.0011478 | 0.0010739 | 0.0010026 | 0.00093414 | 0.00086836 | 0.00080529 | 0.00074494 | 0.00068729 | 0.00063232 | 0.00058002 | 0.00053035 | 0.0004833 | 0.00043882 | 0.0003969 | 0.00035749 | 0.00032055 | 0.00028604 | 0.0002539 | 0.00022409 | 0.00019654 | 0.00017121 | 0.00014801 | 0.0001269 | 0.00010778 | 9.0596e-05 | 7.5259e-05 | 6.1685e-05 | 4.9787e-05 | 3.9473e-05 | 3.0648e-05 | 2.3209e-05 | 1.7053e-05 | 1.2071e-05 | 8.1499e-06 | 5.1723e-06 | 3.0164e-06 | 1.5563e-06 | 6.6159e-07 | 1.9752e-07 | 2.4877e-08 | 3.4383e-17
Show the percentage of simulated trials that were EQUAL TO or LESS THAN the SPERT estimates above
| Press F9 to re-simulate 10,000 trials | [19 empty] | SPERT Probabilistic Estimates using the BETA distribution 5%: SPERT Monte Carlo Simulation (PRESS F9 to simulate 10,000 trials)
[21 empty] | 5.04% | 95.36% | 10.43% | 20.43% | 30.56% | 40.98% | 50.7% | 60.73% | 70.71% | 80.28% | 90.23% | 99.11%
|  | Planning Estimate | 126
|  | Planning estimate is greater than | 49.57% | of the 10,000 trials
|  | Between a lowerbound value of | 100
|  | and an upperbound value of | 158 | [17 empty] | SPERT Probabilistic Estimates using the BETA distribution 5%: Monte Carlo Simulation Probabilities and Values
|  | the range probability is | 59.83% | [17 empty] | SPERT Probabilistic Estimates using the BETA distribution 5%: 1%; SPERT Probabilistic Estimates using the BETA distribution 95%: 70.0096; SPERT Probabilistic Estimates using the BETA distribution 10%: 50%; SPERT Probabilistic Estimates using the BETA distribution 20%: 126.3821
|  | The lowerbound area covers | 20.64% | [17 empty] | SPERT Probabilistic Estimates using the BETA distribution 5%: 5%; SPERT Probabilistic Estimates using the BETA distribution 95%: 80.5976; SPERT Probabilistic Estimates using the BETA distribution 10%: 55%; SPERT Probabilistic Estimates using the BETA distribution 20%: 130.7386
|  | and the upperbound area covers | 19.53% | [17 empty] | SPERT Probabilistic Estimates using the BETA distribution 5%: 10%; SPERT Probabilistic Estimates using the BETA distribution 95%: 87.889; SPERT Probabilistic Estimates using the BETA distribution 10%: 60%; SPERT Probabilistic Estimates using the BETA distribution 20%: 135.4986
[21 empty] | 15% | 94.0819 | 65% | 140.2196
|  | Minimum | 61.0186 | [17 empty] | SPERT Probabilistic Estimates using the BETA distribution 5%: 20%; SPERT Probabilistic Estimates using the BETA distribution 95%: 99.3761; SPERT Probabilistic Estimates using the BETA distribution 10%: 70%; SPERT Probabilistic Estimates using the BETA distribution 20%: 145.1311
|  | Maximum | 230.417 | [17 empty] | SPERT Probabilistic Estimates using the BETA distribution 5%: 25%; SPERT Probabilistic Estimates using the BETA distribution 95%: 104.2754; SPERT Probabilistic Estimates using the BETA distribution 10%: 75%; SPERT Probabilistic Estimates using the BETA distribution 20%: 151.1081
|  | Mean | 128.6387 | [17 empty] | SPERT Probabilistic Estimates using the BETA distribution 5%: 30%; SPERT Probabilistic Estimates using the BETA distribution 95%: 108.7368; SPERT Probabilistic Estimates using the BETA distribution 10%: 80%; SPERT Probabilistic Estimates using the BETA distribution 20%: 157.3193
|  | Median | 126.3821 | [17 empty] | SPERT Probabilistic Estimates using the BETA distribution 5%: 35%; SPERT Probabilistic Estimates using the BETA distribution 95%: 113.0052; SPERT Probabilistic Estimates using the BETA distribution 10%: 85%; SPERT Probabilistic Estimates using the BETA distribution 20%: 164.375
|  | Mode | 107 | [17 empty] | SPERT Probabilistic Estimates using the BETA distribution 5%: 40%; SPERT Probabilistic Estimates using the BETA distribution 95%: 117.4344; SPERT Probabilistic Estimates using the BETA distribution 10%: 90%; SPERT Probabilistic Estimates using the BETA distribution 20%: 172.9623
|  | Standard Deviation | 31.8424 | [17 empty] | SPERT Probabilistic Estimates using the BETA distribution 5%: 45%; SPERT Probabilistic Estimates using the BETA distribution 95%: 122.0074; SPERT Probabilistic Estimates using the BETA distribution 10%: 95%; SPERT Probabilistic Estimates using the BETA distribution 20%: 184.394
[21 empty] | 50% | 126.3821 | 99% | 203.8698
[235 empty] | 0 | 6.9837e-05 | 0.00019457 | 0.00035205 | 0.00053381 | 0.00073465 | 0.00095095 | 0.0011799 | 0.0014193 | 0.0016672 | 0.0019221 | 0.0021827 | 0.0024478 | 0.0027162 | 0.0029871 | 0.0032597 | 0.0035331 | 0.0038067 | 0.0040799 | 0.004352 | 0.0046226 | 0.0048912 | 0.0051573 | 0.0054205 | 0.0056804 | 0.0059367 | 0.0061892 | 0.0064374 | 0.0066811 | 0.0069201 | 0.0071541 | 0.0073829 | 0.0076064 | 0.0078243 | 0.0080365 | 0.0082429 | 0.0084433 | 0.0086375 | 0.0088256 | 0.0090074 | 0.0091828 | 0.0093517 | 0.0095141 | 0.00967 | 0.0098192 | 0.0099618 | 0.010098 | 0.010227 | 0.010349 | 0.010465 | 0.010574 | 0.010677 | 0.010772 | 0.010862 | 0.010944 | 0.01102 | 0.011089 | 0.011152 | 0.011208 | 0.011258 | 0.011301 | 0.011339 | 0.01137 | 0.011395 | 0.011413 | 0.011426 | 0.011433 | 0.011434 | 0.011429 | 0.011419 | 0.011403 | 0.011381 | 0.011354 | 0.011322 | 0.011285 | 0.011242 | 0.011195 | 0.011142 | 0.011085 | 0.011024 | 0.010957 | 0.010887 | 0.010812 | 0.010732 | 0.010649 | 0.010562 | 0.010471 | 0.010376 | 0.010278 | 0.010176 | 0.010071 | 0.0099624 | 0.0098509 | 0.0097364 | 0.0096191 | 0.009499 | 0.0093763 | 0.0092511 | 0.0091236 | 0.0089938 | 0.0088619 | 0.0087279 | 0.0085922 | 0.0084546 | 0.0083155 | 0.0081748 | 0.0080328 | 0.0078895 | 0.007745 | 0.0075996 | 0.0074532 | 0.007306 | 0.0071581 | 0.0070097 | 0.0068608 | 0.0067116 | 0.0065622 | 0.0064127 | 0.0062631 | 0.0061136 | 0.0059644 | 0.0058155 | 0.0056669 | 0.0055189 | 0.0053715 | 0.0052248 | 0.005079 | 0.004934 | 0.00479 | 0.0046471 | 0.0045054 | 0.0043649 | 0.0042258 | 0.0040881 | 0.003952 | 0.0038174 | 0.0036845 | 0.0035533 | 0.0034239 | 0.0032964 | 0.0031708 | 0.0030473 | 0.0029258 | 0.0028064 | 0.0026893 | 0.0025743 | 0.0024617 | 0.0023514 | 0.0022435 | 0.002138 | 0.002035 | 0.0019345 | 0.0018366 | 0.0017412 | 0.0016485 | 0.0015583 | 0.0014709 | 0.0013861 | 0.0013039 | 0.0012245 | 0.0011478 | 0.0010739 | 0.0010026 | 0.00093414 | 0.00086836 | 0.00080529 | 0.00074494 | 0.00068729 | 0.00063232 | 0.00058002 | 0.00053035 | 0.0004833 | 0.00043882 | 0.0003969 | 0.00035749 | 0.00032055 | 0.00028604 | 0.0002539 | 0.00022409 | 0.00019654 | 0.00017121 | 0.00014801 | 0.0001269 | 0.00010778 | 9.0596e-05 | 7.5259e-05 | 6.1685e-05 | 4.9787e-05 | 3.9473e-05 | 3.0648e-05 | 2.3209e-05 | 1.7053e-05 | 1.2071e-05 | 8.1499e-06 | 5.1723e-06 | 3.0164e-06 | 1.5563e-06 | 6.6159e-07 | 1.9752e-07 | 2.4877e-08 | 3.4383e-17
|  | With | 60% | confidence
|  | The lowerbound threshold is | 99.7938
|  | and the upperbound threshold is | 157.7256
|  | Between a lowerbound value of | 100 |  | Miss the pie
|  | and an upperbound value of | 158 |  | chart? Press
|  | the range probability is | 60.01% |  | CTRL and 6
|  | The lowerbound area covers | 20.2% |  | to show the
|  | and the upperbound area covers | 19.79% |  | pie chart
Version 3.0.s – © 2015-2020, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Subscribe to the SPERT® newsletter for monthly tips, free webinars, and new release notifications
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).
| Simulation Data Table |  | To create the data table, select B67 to C10067, then from the Data menu, choose the What-If Analysis button and create a data table specifying a column input R3. Cell R3 is not really used, but the result of this action is a random sampling of 10,000 values stored in column C.
| Trial | Result
162.2699
| 1 | 82.0969
| 2 | 114.0395
| 3 | 150.5786
| 4 | 82.1219
| 5 | 131.5739
| 6 | 166.8271
| 7 | 121.0725
| 8 | 136.5153
| 9 | 155.9203
| 10 | 141.3454
| 11 | 141.7834
| 12 | 78.815
| 13 | 138.32
| 14 | 152.5838
| 15 | 163.8578
| 16 | 126.768
| 17 | 199.5207
| 18 | 87.952
| 19 | 214.6811
| 20 | 111.3519
| 21 | 129.5304
| 22 | 148.6289
| 23 | 91.2004
| 24 | 191.3987
| 25 | 92.6629
| 26 | 90.2494
| 27 | 97.7506
| 28 | 209.8456
| 29 | 74.06
| 30 | 196.151
| 31 | 153.8093
| 32 | 87.2656
| 33 | 128.6449
| 34 | 128.5568
| 35 | 131.8997
| 36 | 154.758
| 37 | 194.6448
| 38 | 127.6725
| 39 | 160.7043
| 40 | 105.5399
| 41 | 151.6806
| 42 | 146.6415
| 43 | 149.0853
| 44 | 70.3315
| 45 | 98.2291
| 46 | 61.0186
| 47 | 133.8914
| 48 | 128.7603
| 49 | 102.0286
| 50 | 173.9271
| 51 | 87.2449
| 52 | 140.7376
| 53 | 127.0283
| 54 | 147.098
| 55 | 163.5138
| 56 | 166.569
| 57 | 182.2218
| 58 | 177.1052
| 59 | 85.1331
| 60 | 156.0856
| 61 | 145.8247
| 62 | 191.9505
| 63 | 117.4939
| 64 | 147.7784
| 65 | 115.6692
| 66 | 83.8528
| 67 | 93.1101
| 68 | 163.7191
| 69 | 91.6978
| 70 | 104.3484
| 71 | 93.6519
| 72 | 141.5197
| 73 | 149.4515
| 74 | 181.534
| 75 | 146.9303
| 76 | 67.4984
| 77 | 115.2151
| 78 | 78.5413
| 79 | 169.6673
| 80 | 119.6684
| 81 | 100.5162
| 82 | 64.2763
| 83 | 168.0972
| 84 | 162.6815
| 85 | 110.2188
| 86 | 179.5822
| 87 | 122.7001
| 88 | 191.3052
| 89 | 105.727
| 90 | 87.6828
| 91 | 120.1515
| 92 | 122.3434
| 93 | 146.3304
| 94 | 150.4674
| 95 | 116.6835
| 96 | 99.1364
| 97 | 110.2723
| 98 | 175.3218
| 99 | 156.7945
| 100 | 129.9594
| 101 | 165.7864
| 102 | 84.849
| 103 | 128.4671
| 104 | 135.3766
| 105 | 82.2914
| 106 | 79.5409
| 107 | 93.8179
| 108 | 135.9449
| 109 | 88.1535
| 110 | 154.4676
| 111 | 138.4617
| 112 | 85.0671
| 113 | 94.5442
| 114 | 96.7265
| 115 | 119.9701
| 116 | 85.4573
| 117 | 144.7664
| 118 | 160.3111
| 119 | 136.6547
| 120 | 117.1409
| 121 | 96.0311
| 122 | 164.1901
| 123 | 163.7671
| 124 | 110.409
| 125 | 102.42
| 126 | 107.5266
| 127 | 141.6508
| 128 | 83.3542
| 129 | 133.9606
| 130 | 106.8974
| 131 | 106.3225
| 132 | 112.4123
| 133 | 140.5733
| 134 | 105.4332
| 135 | 127.6887
| 136 | 87.2715
| 137 | 118.8209
| 138 | 157.0355
| 139 | 119.0963
| 140 | 88.296
| 141 | 99.674
| 142 | 100.2062
| 143 | 172.0488
| 144 | 139.7663
| 145 | 90.7579
| 146 | 141.6075
| 147 | 152.4829
| 148 | 79.264
| 149 | 132.4642
| 150 | 90.929
| 151 | 156.2833
| 152 | 100.6139
| 153 | 154.3223
| 154 | 143.8523
| 155 | 163.1943
| 156 | 77.5389
| 157 | 137.7047
| 158 | 120.282
| 159 | 105.2413
| 160 | 182.1082
| 161 | 103.1552
| 162 | 196.717
| 163 | 121.5364
| 164 | 144.604
| 165 | 102.2193
| 166 | 82.3975
| 167 | 105.4842
| 168 | 87.3976
| 169 | 79.9583
| 170 | 152.6189
| 171 | 157.7699
| 172 | 88.2948
| 173 | 163.5253
| 174 | 111.0185
| 175 | 125.2266
| 176 | 150.8363
| 177 | 86.9676
| 178 | 127.079
| 179 | 226.7128
| 180 | 126.788
| 181 | 117.3926
| 182 | 79.9692
| 183 | 149.3414
| 184 | 102.474
| 185 | 121.5581
| 186 | 115.7294
| 187 | 155.4999
| 188 | 120.4898
| 189 | 118.6009
| 190 | 139.2591
| 191 | 134.7389
| 192 | 153.0078
| 193 | 95.1662
| 194 | 78.022
| 195 | 99.6353
| 196 | 173.6895
| 197 | 124.0539
| 198 | 143.426
| 199 | 102.523
| 200 | 189.6405
| 201 | 116.3527
| 202 | 190.1089
| 203 | 109.4879
| 204 | 118.3327
| 205 | 158.3826
| 206 | 100.0865
| 207 | 159.3032
| 208 | 185.5887
| 209 | 175.6634
| 210 | 194.1388
| 211 | 108.1865
| 212 | 136.8625
| 213 | 164.2731
| 214 | 172.0126
| 215 | 147.3815
| 216 | 209.1244
| 217 | 132.7813
| 218 | 95.5363
| 219 | 126.9968
| 220 | 126.9345
| 221 | 189.7266
| 222 | 127.4859
| 223 | 99.3438
| 224 | 165.5659
| 225 | 143.4915
| 226 | 173.036
| 227 | 149.3397
| 228 | 131.3932
| 229 | 112.7075
| 230 | 145.6618
| 231 | 143.0692
| 232 | 113.0995
| 233 | 159.6125
| 234 | 114.7361
| 235 | 69.9584
| 236 | 74.2624
| 237 | 71.1218
| 238 | 157.5667
| 239 | 92.4369
| 240 | 94.2662
| 241 | 134.96
| 242 | 142.213
| 243 | 95.7235
| 244 | 151.5427
| 245 | 147.3086
| 246 | 84.9504
| 247 | 124.6563
| 248 | 187.2865
| 249 | 160.5631
| 250 | 109.8446
| 251 | 94.5132
| 252 | 165.3805
| 253 | 120.5014
| 254 | 112.8314
| 255 | 129.0751
| 256 | 102.2691
| 257 | 173.8214
| 258 | 181.3003
| 259 | 141.4974
| 260 | 134.2891
| 261 | 128.327
| 262 | 110.122
| 263 | 123.7303
| 264 | 66.394
| 265 | 184.5286
| 266 | 127.6028
| 267 | 123.0312
| 268 | 146.8313
| 269 | 149.3571
| 270 | 132.7152
| 271 | 142.1995
| 272 | 154.9055
| 273 | 123.0029
| 274 | 82.655
| 275 | 100.7145
| 276 | 124.1937
| 277 | 148.0452
| 278 | 158.0273
| 279 | 131.1292
| 280 | 166.1153
| 281 | 107.9765
| 282 | 125.2533
| 283 | 85.9619
| 284 | 130.7055
| 285 | 148.6078
| 286 | 124.4659
| 287 | 114.4119
| 288 | 103.7799
| 289 | 137.2318
| 290 | 170.5813
| 291 | 97.7695
| 292 | 113.1621
| 293 | 168.6779
| 294 | 91.634
| 295 | 85.5775
| 296 | 92.3497
| 297 | 141.5695
| 298 | 158.2858
| 299 | 154.9406
| 300 | 171.0031
| 301 | 170.9036
| 302 | 135.9296
| 303 | 126.9708
| 304 | 146.1597
| 305 | 135.276
| 306 | 112.1672
| 307 | 137.8929
| 308 | 89.5276
| 309 | 106.6105
| 310 | 188.0942
| 311 | 172.9237
| 312 | 89.6988
| 313 | 110.8362
| 314 | 191.0695
| 315 | 116.7738
| 316 | 84.4168
| 317 | 182.3574
| 318 | 117.8139
| 319 | 173.2623
| 320 | 167.3402
| 321 | 107.8926
| 322 | 119.2446
| 323 | 185.3977
| 324 | 86.8358
| 325 | 141.4124
| 326 | 126.8844
| 327 | 91.1907
| 328 | 133.1245
| 329 | 79.8662
| 330 | 90.716
| 331 | 117.7136
| 332 | 165.9114
| 333 | 87.0391
| 334 | 129.1103
| 335 | 82.1586
| 336 | 170.6703
| 337 | 155.3495
| 338 | 135.892
| 339 | 104.1818
| 340 | 116.3169
| 341 | 171.2293
| 342 | 102.8419
| 343 | 104.4629
| 344 | 156.4858
| 345 | 105.3994
| 346 | 147.4986
| 347 | 96.468
| 348 | 129.4793
| 349 | 110.0139
| 350 | 89.4504
| 351 | 129.7748
| 352 | 78.3081
| 353 | 123.0882
| 354 | 133.7313
| 355 | 124.2745
| 356 | 115.4255
| 357 | 92.9287
| 358 | 149.2575
| 359 | 117.1677
| 360 | 128.5519
| 361 | 95.1844
| 362 | 198.3621
| 363 | 158.8295
| 364 | 130.0678
| 365 | 161.7741
| 366 | 87.1766
| 367 | 124.785
| 368 | 117.9214
| 369 | 129.6377
| 370 | 108.3105
| 371 | 128.2237
| 372 | 128.2415
| 373 | 162.9628
| 374 | 139.6812
| 375 | 120.2059
| 376 | 123.755
| 377 | 101.5193
| 378 | 131.1423
| 379 | 87.6051
| 380 | 105.2155
| 381 | 125.2053
| 382 | 143.6678
| 383 | 73.9301
| 384 | 161.0222
| 385 | 156.7744
| 386 | 81.1564
| 387 | 132.4451
| 388 | 192.4275
| 389 | 116.666
| 390 | 77.2115
| 391 | 180.6705
| 392 | 136.2425
| 393 | 133.6032
| 394 | 142.9837
| 395 | 168.6737
| 396 | 113.8169
| 397 | 160.9678
| 398 | 171.4191
| 399 | 118.8983
| 400 | 104.3478
| 401 | 100.047
| 402 | 124.1693
| 403 | 112.8432
| 404 | 140.5022
| 405 | 101.7739
| 406 | 131.6509
| 407 | 145.2292
| 408 | 106.9799
| 409 | 103.0286
| 410 | 181.4032
| 411 | 110.4252
| 412 | 79.2755
| 413 | 150.9553
| 414 | 119.3018
| 415 | 146.4649
| 416 | 90.3027
| 417 | 157.9907
| 418 | 138.0015
| 419 | 92.2191
| 420 | 181.4621
| 421 | 116.8046
| 422 | 146.944
| 423 | 122.7801
| 424 | 164.8041
| 425 | 82.6659
| 426 | 155.6591
| 427 | 95.8468
| 428 | 149.3025
| 429 | 107.7305
| 430 | 181.7811
| 431 | 79.843
| 432 | 115.5053
| 433 | 110.2259
| 434 | 121.5481
| 435 | 101.397
| 436 | 114.6592
| 437 | 147.5102
| 438 | 99.6423
| 439 | 158.6177
| 440 | 128.9268
| 441 | 96.3114
| 442 | 182.8738
| 443 | 133.8138
| 444 | 146.6715
| 445 | 109.7829
| 446 | 133.4858
| 447 | 151.7503
| 448 | 79.9568
| 449 | 161.075
| 450 | 111.3449
| 451 | 141.8216
| 452 | 133.1993
| 453 | 74.0468
| 454 | 122.2826
| 455 | 135.7167
| 456 | 175.1765
| 457 | 67.1755
| 458 | 110.2111
| 459 | 122.6384
| 460 | 193.1076
| 461 | 116.2911
| 462 | 102.0449
| 463 | 112.3897
| 464 | 100.5933
| 465 | 132.7135
| 466 | 137.0184
| 467 | 206.1149
| 468 | 117.6217
| 469 | 70.0096
| 470 | 103.5484
| 471 | 161.3036
| 472 | 150.2182
| 473 | 82.3359
| 474 | 107.5544
| 475 | 121.7482
| 476 | 181.2306
| 477 | 147.6408
| 478 | 152.6233
| 479 | 167.0963
| 480 | 123.6451
| 481 | 96.4928
| 482 | 116.4531
| 483 | 132.5465
| 484 | 110.1837
| 485 | 122.9892
| 486 | 78.2234
| 487 | 112.4693
| 488 | 144.0509
| 489 | 151.365
| 490 | 135.0961
| 491 | 115.6097
| 492 | 152.1312
| 493 | 99.8468
| 494 | 117.934
| 495 | 154.5344
| 496 | 119.243
| 497 | 145.0707
| 498 | 100.9988
| 499 | 114.9381
| 500 | 182.3543
| 501 | 109.2694
| 502 | 160.9282
| 503 | 124.5491
| 504 | 110.8105
| 505 | 86.1314
| 506 | 136.4307
| 507 | 159.5236
| 508 | 185.3972
| 509 | 168.2053
| 510 | 165.6528
| 511 | 157.7301
| 512 | 71.7614
| 513 | 105.3083
| 514 | 84.4479
| 515 | 134.981
| 516 | 126.2273
| 517 | 101.3729
| 518 | 84.35
| 519 | 117.8084
| 520 | 189.3923
| 521 | 131.3879
| 522 | 146.0849
| 523 | 113.8968
| 524 | 157.3948
| 525 | 115.5123
| 526 | 133.6613
| 527 | 110.7668
| 528 | 142.2746
| 529 | 87.5049
| 530 | 120.428
| 531 | 111.4579
| 532 | 109.5597
| 533 | 132.3221
| 534 | 90.5841
| 535 | 148.7255
| 536 | 118.0209
| 537 | 163.1376
| 538 | 177.9421
| 539 | 116.5442
| 540 | 139.7743
| 541 | 170.305
| 542 | 142.6388
| 543 | 177.9834
| 544 | 93.9224
| 545 | 106.0337
| 546 | 116.6732
| 547 | 170.2741
| 548 | 120.3759
| 549 | 68.0929
| 550 | 163.0976
| 551 | 152.6235
| 552 | 144.227
| 553 | 131.8484
| 554 | 128.7401
| 555 | 119.8884
| 556 | 99.2874
| 557 | 167.9284
| 558 | 118.6606
| 559 | 114.7346
| 560 | 159.9086
| 561 | 99.6061
| 562 | 99.1571
| 563 | 95.1182
| 564 | 94.0759
| 565 | 118.8442
| 566 | 144.3834
| 567 | 132.6093
| 568 | 84.2789
| 569 | 130.1276
| 570 | 145.8413
| 571 | 170.6044
| 572 | 102.8566
| 573 | 117.6352
| 574 | 115.7061
| 575 | 73.389
| 576 | 136.697
| 577 | 131.6081
| 578 | 198.4828
| 579 | 183.1532
| 580 | 108.5366
| 581 | 124.5333
| 582 | 103.6715
| 583 | 123.0047
| 584 | 120.9312
| 585 | 200.0422
| 586 | 93.3814
| 587 | 182.2738
| 588 | 137.0981
| 589 | 180.5807
| 590 | 84.5319
| 591 | 185.0734
| 592 | 196.1809
| 593 | 160.027
| 594 | 135.6112
| 595 | 158.1415
| 596 | 156.3947
| 597 | 92.6497
| 598 | 155.6863
| 599 | 137.5808
| 600 | 100.128
| 601 | 126.5958
| 602 | 78.5535
| 603 | 153.2864
| 604 | 134.5081
| 605 | 108.2765
| 606 | 146.8064
| 607 | 112.2976
| 608 | 106.946
| 609 | 96.0568
| 610 | 122.4407
| 611 | 71.7326
| 612 | 96.2403
| 613 | 149.4205
| 614 | 143.128
| 615 | 83.4483
| 616 | 157.3884
| 617 | 138.4575
| 618 | 162.705
| 619 | 184.3956
| 620 | 184.5782
| 621 | 108.191
| 622 | 86.8539
| 623 | 147.8211
| 624 | 99.3065
| 625 | 119.5866
| 626 | 185.453
| 627 | 153.248
| 628 | 173.5359
| 629 | 85.2738
| 630 | 150.1094
| 631 | 107.422
| 632 | 159.0229
| 633 | 90.5605
| 634 | 153.7169
| 635 | 101.1242
| 636 | 115.8066
| 637 | 144.4106
| 638 | 118.8461
| 639 | 78.466
| 640 | 146.3257
| 641 | 111.0675
| 642 | 110.8332
| 643 | 135.8857
| 644 | 89.751
| 645 | 139.5539
| 646 | 70.6705
| 647 | 109.4371
| 648 | 151.5779
| 649 | 125.7583
| 650 | 140.5121
| 651 | 89.6976
| 652 | 104.9091
| 653 | 112.0362
| 654 | 116.0966
| 655 | 91.6777
| 656 | 114.2118
| 657 | 122.6789
| 658 | 143.6706
| 659 | 79.1605
| 660 | 211.5841
| 661 | 138.8368
| 662 | 94.5544
| 663 | 126.1394
| 664 | 122.1711
| 665 | 128.9483
| 666 | 133.2878
| 667 | 115.8163
| 668 | 141.4304
| 669 | 90.4596
| 670 | 202.0535
| 671 | 107.4448
| 672 | 184.3082
| 673 | 100.4812
| 674 | 72.6836
| 675 | 86.3865
| 676 | 96.3597
| 677 | 169.4785
| 678 | 172.0645
| 679 | 114.5069
| 680 | 89.131
| 681 | 99.5151
| 682 | 151.8306
| 683 | 136.7443
| 684 | 127.2887
| 685 | 185.1119
| 686 | 109.865
| 687 | 184.0716
| 688 | 136.8299
| 689 | 176.6895
| 690 | 153.9677
| 691 | 93.1902
| 692 | 83.6882
| 693 | 145.3429
| 694 | 146.1525
| 695 | 105.0007
| 696 | 72.7455
| 697 | 160.8049
| 698 | 193.3864
| 699 | 101.1274
| 700 | 155.8075
| 701 | 142.3768
| 702 | 149.5931
| 703 | 88.6606
| 704 | 154.6331
| 705 | 135.7012
| 706 | 126.5122
| 707 | 177.6131
| 708 | 104.1715
| 709 | 114.7468
| 710 | 155.2526
| 711 | 103.94
| 712 | 139.0556
| 713 | 79.4597
| 714 | 90.2319
| 715 | 128.4614
| 716 | 170.6551
| 717 | 97.3595
| 718 | 155.6918
| 719 | 162.1736
| 720 | 86.8137
| 721 | 126.0168
| 722 | 203.226
| 723 | 100.3508
| 724 | 80.3406
| 725 | 153.6074
| 726 | 141.4131
| 727 | 150.458
| 728 | 95.2181
| 729 | 132.7297
| 730 | 83.8789
| 731 | 94.8179
| 732 | 205.833
| 733 | 91.2763
| 734 | 146.9519
| 735 | 182.3899
| 736 | 130.7551
| 737 | 150.8812
| 738 | 163.9955
| 739 | 84.6609
| 740 | 178.3117
| 741 | 131.4048
| 742 | 123.0236
| 743 | 96.8914
| 744 | 177.2534
| 745 | 101.7471
| 746 | 145.9925
| 747 | 129.7702
| 748 | 152.2592
| 749 | 134.8853
| 750 | 167.7699
| 751 | 92.1564
| 752 | 129.108
| 753 | 98.9248
| 754 | 91.3735
| 755 | 179.5004
| 756 | 145.1944
| 757 | 93.8709
| 758 | 172.0535
| 759 | 128.7567
| 760 | 91.4409
| 761 | 158.6323
| 762 | 134.8751
| 763 | 157.0775
| 764 | 117.2333
| 765 | 117.9929
| 766 | 114.1974
| 767 | 92.447
| 768 | 86.5227
| 769 | 106.6207
| 770 | 205.8097
| 771 | 151.3969
| 772 | 102.8455
| 773 | 143.5806
| 774 | 164.5171
| 775 | 138.3978
| 776 | 138.831
| 777 | 142.0682
| 778 | 125.2685
| 779 | 157.2219
| 780 | 93.3986
| 781 | 95.1721
| 782 | 77.0147
| 783 | 165.8751
| 784 | 173.7919
| 785 | 97.0702
| 786 | 165.4754
| 787 | 167.5451
| 788 | 122.5461
| 789 | 145.0833
| 790 | 129.4604
| 791 | 66.2589
| 792 | 118.307
| 793 | 93.7018
| 794 | 185.4833
| 795 | 99.5983
| 796 | 154.7146
| 797 | 187.7756
| 798 | 81.9773
| 799 | 124.7464
| 800 | 83.9435
| 801 | 141.7245
| 802 | 198.8216
| 803 | 98.5719
| 804 | 143.7434
| 805 | 112.4464
| 806 | 138.1861
| 807 | 126.1742
| 808 | 164.8443
| 809 | 132.9051
| 810 | 166.6904
| 811 | 136.1596
| 812 | 101.8502
| 813 | 141.9259
| 814 | 123.2616
| 815 | 92.1775
| 816 | 100.6707
| 817 | 76.4085
| 818 | 140.2497
| 819 | 118.051
| 820 | 89.7137
| 821 | 95.0918
| 822 | 78.3896
| 823 | 89.2042
| 824 | 86.6568
| 825 | 118.4738
| 826 | 102.3485
| 827 | 134.8694
| 828 | 81.096
| 829 | 108.4806
| 830 | 156.6719
| 831 | 118.6497
| 832 | 67.7225
| 833 | 107.9665
| 834 | 139.3324
| 835 | 81.2195
| 836 | 106.5427
| 837 | 88.6002
| 838 | 105.4306
| 839 | 169.494
| 840 | 105.6692
| 841 | 146.43
| 842 | 114.3175
| 843 | 77.3507
| 844 | 112.2501
| 845 | 179.9026
| 846 | 125.18
| 847 | 112.5243
| 848 | 86.5772
| 849 | 114.0712
| 850 | 110.8812
| 851 | 141.4284
| 852 | 114.6276
| 853 | 158.3027
| 854 | 190.6065
| 855 | 116.3735
| 856 | 96.2635
| 857 | 109.7165
| 858 | 90.483
| 859 | 96.2442
| 860 | 209.7391
| 861 | 146.849
| 862 | 116.3112
| 863 | 101.906
| 864 | 133.444
| 865 | 81.4704
| 866 | 153.4993
| 867 | 96.2614
| 868 | 211.702
| 869 | 108.6503
| 870 | 186.5315
| 871 | 109.9742
| 872 | 155.2078
| 873 | 145.7552
| 874 | 124.6053
| 875 | 133.5288
| 876 | 110.9377
| 877 | 161.0355
| 878 | 170.8638
| 879 | 109.1246
| 880 | 170.2979
| 881 | 96.4368
| 882 | 85.4538
| 883 | 115.2558
| 884 | 133.3678
| 885 | 110.3984
| 886 | 188.9727
| 887 | 135.8892
| 888 | 114.1478
| 889 | 107.3597
| 890 | 107.5879
| 891 | 91.9719
| 892 | 106.9187
| 893 | 169.666
| 894 | 90.9943
| 895 | 147.57
| 896 | 111.3895
| 897 | 105.9241
| 898 | 79.317
| 899 | 119.014
| 900 | 134.0681
| 901 | 108.0179
| 902 | 194.3633
| 903 | 87.2217
| 904 | 119.1434
| 905 | 131.4687
| 906 | 133.5358
| 907 | 73.225
| 908 | 197.8239
| 909 | 145.2995
| 910 | 150.4677
| 911 | 141.2308
| 912 | 132.6033
| 913 | 109.1995
| 914 | 100.0725
| 915 | 144.3236
| 916 | 158.5102
| 917 | 167.6011
| 918 | 111.4595
| 919 | 153.2277
| 920 | 125.5211
| 921 | 112.5263
| 922 | 104.167
| 923 | 97.0144
| 924 | 183.45
| 925 | 185.1391
| 926 | 89.0829
| 927 | 115.5534
| 928 | 112.58
| 929 | 127.6917
| 930 | 154.5253
| 931 | 160.0419
| 932 | 104.2735
| 933 | 196.0279
| 934 | 93.5404
| 935 | 147.4118
| 936 | 189.5216
| 937 | 133.8541
| 938 | 160.9195
| 939 | 156.9868
| 940 | 113.5466
| 941 | 178.3574
| 942 | 87.7216
| 943 | 169.9532
| 944 | 139.6518
| 945 | 130.6597
| 946 | 94.2202
| 947 | 135.8492
| 948 | 79.1964
| 949 | 143.8939
| 950 | 139.1537
| 951 | 119.7755
| 952 | 182.5264
| 953 | 115.0297
| 954 | 127.2168
| 955 | 113.0107
| 956 | 176.9278
| 957 | 114.7351
| 958 | 103.9864
| 959 | 108.593
| 960 | 103.3316
| 961 | 144.2829
| 962 | 162.4444
| 963 | 119.0412
| 964 | 153.2089
| 965 | 118.131
| 966 | 125.762
| 967 | 154.3582
| 968 | 137.2008
| 969 | 134.8552
| 970 | 143.3633
| 971 | 109.3938
| 972 | 96.9315
| 973 | 183.7819
| 974 | 129.2877
| 975 | 127.4767
| 976 | 132.0449
| 977 | 96.3453
| 978 | 125.863
| 979 | 83.8966
| 980 | 177.8272
| 981 | 132.8462
| 982 | 100.0734
| 983 | 173.2791
| 984 | 149.2745
| 985 | 126.9971
| 986 | 115.8008
| 987 | 78.2607
| 988 | 144.9337
| 989 | 183.249
| 990 | 216.9723
| 991 | 110.3188
| 992 | 167.0202
| 993 | 139.259
| 994 | 157.4341
| 995 | 137.2699
| 996 | 69.2906
| 997 | 196.8426
| 998 | 78.3203
| 999 | 176.1052
| 1000 | 131.703
| 1001 | 124.4717
| 1002 | 93.8201
| 1003 | 125.4379
| 1004 | 98.3078
| 1005 | 140.2969
| 1006 | 135.2148
| 1007 | 182.2583
| 1008 | 165.6334
| 1009 | 138.9158
| 1010 | 120.4594
| 1011 | 163.3796
| 1012 | 92.7481
| 1013 | 76.719
| 1014 | 103.8527
| 1015 | 191.9194
| 1016 | 201.9686
| 1017 | 89.2006
| 1018 | 85.728
| 1019 | 132.6895
| 1020 | 98.5056
| 1021 | 131.6135
| 1022 | 121.4523
| 1023 | 109.3995
| 1024 | 104.0792
| 1025 | 134.508
| 1026 | 106.8626
| 1027 | 140.0479
| 1028 | 135.4138
| 1029 | 106.4462
| 1030 | 104.627
| 1031 | 155.6481
| 1032 | 223.8431
| 1033 | 127.6717
| 1034 | 115.4291
| 1035 | 115.965
| 1036 | 159.9193
| 1037 | 101.5083
| 1038 | 126.4911
| 1039 | 92.3336
| 1040 | 165.8174
| 1041 | 119.802
| 1042 | 140.4861
| 1043 | 109.5238
| 1044 | 170.8197
| 1045 | 159.7598
| 1046 | 118.1884
| 1047 | 117.9146
| 1048 | 88.23
| 1049 | 126.7403
| 1050 | 92.0754
| 1051 | 114.9242
| 1052 | 157.7924
| 1053 | 127.3032
| 1054 | 164.4776
| 1055 | 144.3497
| 1056 | 120.7309
| 1057 | 166.0974
| 1058 | 103.6303
| 1059 | 179.6884
| 1060 | 147.896
| 1061 | 139.6888
| 1062 | 114.6736
| 1063 | 88.4262
| 1064 | 117.5955
| 1065 | 118.9167
| 1066 | 190.2407
| 1067 | 84.6294
| 1068 | 97.6142
| 1069 | 130.3729
| 1070 | 161.3101
| 1071 | 104.4819
| 1072 | 176.1015
| 1073 | 161.0768
| 1074 | 131.8583
| 1075 | 170.8398
| 1076 | 104.3519
| 1077 | 109.2756
| 1078 | 84.6788
| 1079 | 167.6
| 1080 | 86.0022
| 1081 | 85.7327
| 1082 | 141.4052
| 1083 | 93.7176
| 1084 | 134.6421
| 1085 | 112.773
| 1086 | 136.5255
| 1087 | 127.1475
| 1088 | 197.7147
| 1089 | 177.5468
| 1090 | 175.7021
| 1091 | 124.8244
| 1092 | 151.7736
| 1093 | 107.6195
| 1094 | 100.7069
| 1095 | 217.0205
| 1096 | 70.9739
| 1097 | 123.747
| 1098 | 114.539
| 1099 | 122.9326
| 1100 | 100.2745
| 1101 | 135.2147
| 1102 | 144.3163
| 1103 | 182.5456
| 1104 | 155.5481
| 1105 | 75.2504
| 1106 | 128.8388
| 1107 | 132.5708
| 1108 | 166.0146
| 1109 | 135.5398
| 1110 | 130.3445
| 1111 | 122.7594
| 1112 | 163.7663
| 1113 | 153.3964
| 1114 | 153.4561
| 1115 | 130.3006
| 1116 | 183.9684
| 1117 | 114.816
| 1118 | 127.5943
| 1119 | 188.6598
| 1120 | 163.3578
| 1121 | 162.332
| 1122 | 81.2199
| 1123 | 119.0502
| 1124 | 105.0851
| 1125 | 119.6632
| 1126 | 75.9801
| 1127 | 173.4114
| 1128 | 126.2512
| 1129 | 129.9585
| 1130 | 115.9753
| 1131 | 182.0741
| 1132 | 168.2727
| 1133 | 116.6157
| 1134 | 141.3496
| 1135 | 150.7176
| 1136 | 179.4221
| 1137 | 105.0817
| 1138 | 150.3185
| 1139 | 91.2059
| 1140 | 146.7819
| 1141 | 74.3786
| 1142 | 125.2036
| 1143 | 122.7053
| 1144 | 130.7555
| 1145 | 86.7337
| 1146 | 131.1882
| 1147 | 75.145
| 1148 | 173.1865
| 1149 | 130.2236
| 1150 | 120.0735
| 1151 | 140.7018
| 1152 | 107.8558
| 1153 | 167.4175
| 1154 | 119.4152
| 1155 | 174.1511
| 1156 | 84.7106
| 1157 | 82.3046
| 1158 | 135.0863
| 1159 | 75.5155
| 1160 | 130.3529
| 1161 | 175.1888
| 1162 | 110.1937
| 1163 | 171.4045
| 1164 | 113.8496
| 1165 | 105.2123
| 1166 | 168.6514
| 1167 | 171.5629
| 1168 | 158.6268
| 1169 | 180.0815
| 1170 | 90.5539
| 1171 | 111.5046
| 1172 | 138.1873
| 1173 | 137.4109
| 1174 | 126.3783
| 1175 | 100.8577
| 1176 | 79.1026
| 1177 | 135.2782
| 1178 | 88.3679
| 1179 | 148.798
| 1180 | 165.83
| 1181 | 101.7113
| 1182 | 79.3458
| 1183 | 99.3796
| 1184 | 98.4685
| 1185 | 127.7832
| 1186 | 136.181
| 1187 | 159.3832
| 1188 | 109.7468
| 1189 | 114.6323
| 1190 | 153.0278
| 1191 | 69.1551
| 1192 | 123.7038
| 1193 | 73.9893
| 1194 | 153.3814
| 1195 | 93.154
| 1196 | 114.8062
| 1197 | 159.524
| 1198 | 118.7207
| 1199 | 138.665
| 1200 | 134.5957
| 1201 | 143.2503
| 1202 | 113.605
| 1203 | 94.7422
| 1204 | 131.3678
| 1205 | 136.7403
| 1206 | 74.0549
| 1207 | 124.6243
| 1208 | 142.798
| 1209 | 122.3165
| 1210 | 113.0736
| 1211 | 144.5514
| 1212 | 144.239
| 1213 | 124.3367
| 1214 | 143.1383
| 1215 | 112.8448
| 1216 | 116.0072
| 1217 | 89.7798
| 1218 | 96.3257
| 1219 | 115.1047
| 1220 | 116.9673
| 1221 | 105.2151
| 1222 | 134.2014
| 1223 | 96.814
| 1224 | 130.0424
| 1225 | 128.632
| 1226 | 161.9253
| 1227 | 173.6336
| 1228 | 71.8848
| 1229 | 110.7603
| 1230 | 134.2932
| 1231 | 113.383
| 1232 | 186.3694
| 1233 | 135.8798
| 1234 | 106.0888
| 1235 | 161.79
| 1236 | 110.0039
| 1237 | 147.3257
| 1238 | 103.1699
| 1239 | 199.5233
| 1240 | 168.5202
| 1241 | 141.5554
| 1242 | 114.4184
| 1243 | 106.8851
| 1244 | 203.5629
| 1245 | 133.845
| 1246 | 114.4967
| 1247 | 132.2814
| 1248 | 165.5745
| 1249 | 145.5677
| 1250 | 165.7347
| 1251 | 178.3277
| 1252 | 82.9657
| 1253 | 98.2952
| 1254 | 122.1265
| 1255 | 150.6788
| 1256 | 95.6284
| 1257 | 75.3033
| 1258 | 134.0176
| 1259 | 128.8434
| 1260 | 111.947
| 1261 | 119.3042
| 1262 | 154.6665
| 1263 | 178.9625
| 1264 | 174.269
| 1265 | 151.9674
| 1266 | 113.6788
| 1267 | 119.2055
| 1268 | 107.3183
| 1269 | 164.2118
| 1270 | 112.756
| 1271 | 104.5385
| 1272 | 128.288
| 1273 | 164.7404
| 1274 | 154.4949
| 1275 | 153.1955
| 1276 | 90.1886
| 1277 | 124.8077
| 1278 | 141.2788
| 1279 | 122.1642
| 1280 | 72.6856
| 1281 | 129.8555
| 1282 | 70.8823
| 1283 | 111.0231
| 1284 | 184.0778
| 1285 | 118.2151
| 1286 | 134.025
| 1287 | 102.1712
| 1288 | 140.4593
| 1289 | 150.4983
| 1290 | 170.2369
| 1291 | 157.7136
| 1292 | 214.3996
| 1293 | 165.7104
| 1294 | 98.4314
| 1295 | 147.3857
| 1296 | 69.4676
| 1297 | 83.1725
| 1298 | 156.0937
| 1299 | 150.9993
| 1300 | 176.0242
| 1301 | 154.836
| 1302 | 151.5778
| 1303 | 158.961
| 1304 | 126.8086
| 1305 | 158.423
| 1306 | 94.2642
| 1307 | 138.7807
| 1308 | 96.9683
| 1309 | 118.5709
| 1310 | 119.0351
| 1311 | 145.8756
| 1312 | 129.1214
| 1313 | 92.192
| 1314 | 144.8637
| 1315 | 138.7844
| 1316 | 128.1176
| 1317 | 172.1423
| 1318 | 101.018
| 1319 | 189.6408
| 1320 | 78.4999
| 1321 | 101.82
| 1322 | 130.4219
| 1323 | 109.1119
| 1324 | 89.7971
| 1325 | 108.9382
| 1326 | 124.2088
| 1327 | 131.3016
| 1328 | 121.3115
| 1329 | 154.927
| 1330 | 162.5885
| 1331 | 143.3711
| 1332 | 172.4629
| 1333 | 126.2409
| 1334 | 91.4966
| 1335 | 76.8908
| 1336 | 88.2154
| 1337 | 145.2386
| 1338 | 68.0479
| 1339 | 116.722
| 1340 | 163.0384
| 1341 | 109.1951
| 1342 | 92.0111
| 1343 | 78.8457
| 1344 | 106.6617
| 1345 | 157.3194
| 1346 | 119.7431
| 1347 | 73.9422
| 1348 | 99.7887
| 1349 | 137.899
| 1350 | 154.9479
| 1351 | 97.5785
| 1352 | 78.9269
| 1353 | 140.2176
| 1354 | 106.5431
| 1355 | 93.5647
| 1356 | 102.0677
| 1357 | 63.9983
| 1358 | 80.7906
| 1359 | 132.1205
| 1360 | 149.5499
| 1361 | 146.5886
| 1362 | 85.9534
| 1363 | 144.4492
| 1364 | 128.5142
| 1365 | 104.719
| 1366 | 163.0582
| 1367 | 118.7487
| 1368 | 152.2224
| 1369 | 132.3022
| 1370 | 114.3595
| 1371 | 102.7198
| 1372 | 93.5545
| 1373 | 151.0819
| 1374 | 112.8812
| 1375 | 98.5906
| 1376 | 107.2449
| 1377 | 132.9286
| 1378 | 101.4217
| 1379 | 107.463
| 1380 | 92.8812
| 1381 | 170.6798
| 1382 | 107.0023
| 1383 | 156.9252
| 1384 | 100.1778
| 1385 | 157.2428
| 1386 | 116.7419
| 1387 | 82.9901
| 1388 | 166.8363
| 1389 | 131.9406
| 1390 | 111.1646
| 1391 | 126.7619
| 1392 | 122.2261
| 1393 | 111.4968
| 1394 | 109.1042
| 1395 | 66.5828
| 1396 | 198.5966
| 1397 | 99.8055
| 1398 | 108.3054
| 1399 | 127.3507
| 1400 | 187.358
| 1401 | 71.6127
| 1402 | 145.0218
| 1403 | 170.374
| 1404 | 121.8367
| 1405 | 146.082
| 1406 | 179.2527
| 1407 | 151.7071
| 1408 | 133.3702
| 1409 | 118.1513
| 1410 | 86.0685
| 1411 | 130.3599
| 1412 | 149.0289
| 1413 | 109.3548
| 1414 | 96.6961
| 1415 | 160.4478
| 1416 | 92.6108
| 1417 | 189.0896
| 1418 | 155.9223
| 1419 | 198.9809
| 1420 | 112.0405
| 1421 | 131.3123
| 1422 | 111.6158
| 1423 | 98.396
| 1424 | 148.1279
| 1425 | 89.5259
| 1426 | 129.3204
| 1427 | 68.602
| 1428 | 89.5713
| 1429 | 97.0279
| 1430 | 90.6615
| 1431 | 154.3152
| 1432 | 175.4933
| 1433 | 136.7584
| 1434 | 155.0466
| 1435 | 144.2613
| 1436 | 135.2186
| 1437 | 143.5214
| 1438 | 168.222
| 1439 | 125.2087
| 1440 | 170.9385
| 1441 | 189.0797
| 1442 | 133.5557
| 1443 | 95.2522
| 1444 | 115.7182
| 1445 | 113.7589
| 1446 | 108.3078
| 1447 | 121.3675
| 1448 | 119.6564
| 1449 | 186.169
| 1450 | 70.1616
| 1451 | 179.7794
| 1452 | 147.517
| 1453 | 122.657
| 1454 | 154.1459
| 1455 | 129.531
| 1456 | 110.1995
| 1457 | 97.2547
| 1458 | 93.1013
| 1459 | 112.2894
| 1460 | 114.2421
| 1461 | 87.0274
| 1462 | 82.6046
| 1463 | 164.1057
| 1464 | 98.1587
| 1465 | 97.9721
| 1466 | 93.5148
| 1467 | 145.47
| 1468 | 142.6151
| 1469 | 125.7759
| 1470 | 148.1292
| 1471 | 153.5899
| 1472 | 127.2294
| 1473 | 101.0511
| 1474 | 134.2602
| 1475 | 119.7855
| 1476 | 74.4985
| 1477 | 106.3813
| 1478 | 89.9487
| 1479 | 150.7631
| 1480 | 97.1906
| 1481 | 159.3134
| 1482 | 148.9415
| 1483 | 110.5794
| 1484 | 159.3038
| 1485 | 161.9002
| 1486 | 192.0142
| 1487 | 191.7338
| 1488 | 161.1281
| 1489 | 188.554
| 1490 | 107.6944
| 1491 | 117.7097
| 1492 | 78.339
| 1493 | 127.3572
| 1494 | 141.0319
| 1495 | 119.8572
| 1496 | 102.7328
| 1497 | 103.5657
| 1498 | 115.6459
| 1499 | 84.8483
| 1500 | 113.9511
| 1501 | 134.4754
| 1502 | 135.8208
| 1503 | 118.2326
| 1504 | 110.1814
| 1505 | 69.9321
| 1506 | 108.9656
| 1507 | 100.2604
| 1508 | 75.9357
| 1509 | 105.5243
| 1510 | 161.4939
| 1511 | 106.9925
| 1512 | 97.4613
| 1513 | 137.4685
| 1514 | 104.4015
| 1515 | 147.3649
| 1516 | 86.9858
| 1517 | 111.8665
| 1518 | 91.9978
| 1519 | 115.4295
| 1520 | 181.4194
| 1521 | 139.4018
| 1522 | 167.7295
| 1523 | 115.8524
| 1524 | 81.6574
| 1525 | 120.8401
| 1526 | 124.0814
| 1527 | 70.1646
| 1528 | 110.1813
| 1529 | 177.2154
| 1530 | 106.1122
| 1531 | 204.1704
| 1532 | 164.8712
| 1533 | 68.575
| 1534 | 123.0561
| 1535 | 125.176
| 1536 | 179.6861
| 1537 | 155.6435
| 1538 | 117.5639
| 1539 | 137.3044
| 1540 | 132.2143
| 1541 | 155.1046
| 1542 | 73.4424
| 1543 | 104.7104
| 1544 | 159.5267
| 1545 | 123.9319
| 1546 | 164.5587
| 1547 | 139.0161
| 1548 | 133.7293
| 1549 | 134.6256
| 1550 | 140.3231
| 1551 | 110.6351
| 1552 | 123.2762
| 1553 | 119.9369
| 1554 | 119.4539
| 1555 | 141.9611
| 1556 | 128.2126
| 1557 | 73.6548
| 1558 | 92.6699
| 1559 | 106.665
| 1560 | 169.2565
| 1561 | 140.1407
| 1562 | 109.2095
| 1563 | 127.0118
| 1564 | 102.5019
| 1565 | 104.8147
| 1566 | 107.5453
| 1567 | 162.8695
| 1568 | 150.9478
| 1569 | 166.6619
| 1570 | 170.6226
| 1571 | 113.6843
| 1572 | 110.0418
| 1573 | 154.5258
| 1574 | 108.4266
| 1575 | 128.0605
| 1576 | 165.9371
| 1577 | 136.0967
| 1578 | 105.0201
| 1579 | 116.6365
| 1580 | 161.8224
| 1581 | 154.9088
| 1582 | 183.0517
| 1583 | 110.1544
| 1584 | 89.7502
| 1585 | 102.5992
| 1586 | 109.899
| 1587 | 110.0147
| 1588 | 162.404
| 1589 | 131.6879
| 1590 | 89.8322
| 1591 | 195.8271
| 1592 | 81.7575
| 1593 | 78.0361
| 1594 | 121.5549
| 1595 | 110.9551
| 1596 | 88.7372
| 1597 | 159.9618
| 1598 | 117.145
| 1599 | 112.2876
| 1600 | 142.0295
| 1601 | 127.8286
| 1602 | 90.3875
| 1603 | 172.262
| 1604 | 148.6061
| 1605 | 117.1461
| 1606 | 110.0354
| 1607 | 93.6092
| 1608 | 85.3178
| 1609 | 131.7691
| 1610 | 88.7138
| 1611 | 124.93
| 1612 | 182.4995
| 1613 | 139.7073
| 1614 | 143.0937
| 1615 | 153.085
| 1616 | 117.406
| 1617 | 90.7033
| 1618 | 97.0697
| 1619 | 112.1578
| 1620 | 213.6464
| 1621 | 173.3934
| 1622 | 87.6306
| 1623 | 146.353
| 1624 | 140.9924
| 1625 | 178.7821
| 1626 | 113.119
| 1627 | 108.2232
| 1628 | 127.3524
| 1629 | 143.4902
| 1630 | 159.5936
| 1631 | 176.2849
| 1632 | 141.1243
| 1633 | 190.5003
| 1634 | 103.8444
| 1635 | 181.8679
| 1636 | 97.2494
| 1637 | 84.7914
| 1638 | 109.054
| 1639 | 106.6682
| 1640 | 100.3247
| 1641 | 165.5203
| 1642 | 80.2052
| 1643 | 142.8947
| 1644 | 172.7769
| 1645 | 120.4497
| 1646 | 137.7829
| 1647 | 136.9106
| 1648 | 122.2086
| 1649 | 113.8209
| 1650 | 150.409
| 1651 | 87.2777
| 1652 | 180.1353
| 1653 | 103.0214
| 1654 | 74.7018
| 1655 | 66.1122
| 1656 | 118.758
| 1657 | 142.8545
| 1658 | 115.1678
| 1659 | 93.1968
| 1660 | 146.9836
| 1661 | 136.2045
| 1662 | 183.1208
| 1663 | 141.9279
| 1664 | 115.2201
| 1665 | 153.1424
| 1666 | 125.8076
| 1667 | 148.7522
| 1668 | 164.885
| 1669 | 144.1718
| 1670 | 160.2484
| 1671 | 84.8327
| 1672 | 122.9873
| 1673 | 82.8323
| 1674 | 171.8917
| 1675 | 154.6484
| 1676 | 114.2636
| 1677 | 85.6008
| 1678 | 71.2258
| 1679 | 120.7734
| 1680 | 152.4781
| 1681 | 132.7424
| 1682 | 135.0207
| 1683 | 160.3904
| 1684 | 164.0078
| 1685 | 119.4408
| 1686 | 192.5753
| 1687 | 86.13
| 1688 | 135.2216
| 1689 | 126.6786
| 1690 | 96.3125
| 1691 | 131.4898
| 1692 | 145.1581
| 1693 | 140.0453
| 1694 | 82.6432
| 1695 | 125.4536
| 1696 | 116.2427
| 1697 | 94.3473
| 1698 | 167.7306
| 1699 | 116.4333
| 1700 | 105.6838
| 1701 | 154.5819
| 1702 | 186.308
| 1703 | 132.4529
| 1704 | 169.414
| 1705 | 103.2442
| 1706 | 119.5413
| 1707 | 184.2122
| 1708 | 173.8036
| 1709 | 104.5008
| 1710 | 142.1504
| 1711 | 82.7947
| 1712 | 165.461
| 1713 | 166.8271
| 1714 | 150.7296
| 1715 | 89.152
| 1716 | 148.0028
| 1717 | 168.2903
| 1718 | 109.1607
| 1719 | 124.7144
| 1720 | 138.695
| 1721 | 110.9495
| 1722 | 100.7619
| 1723 | 119.0765
| 1724 | 126.0722
| 1725 | 120.1101
| 1726 | 148.4459
| 1727 | 135.4157
| 1728 | 188.973
| 1729 | 101.157
| 1730 | 67.0569
| 1731 | 81.2459
| 1732 | 129.5659
| 1733 | 109.9466
| 1734 | 174.226
| 1735 | 95.3257
| 1736 | 181.3246
| 1737 | 87.8593
| 1738 | 87.82
| 1739 | 179.1318
| 1740 | 119.8105
| 1741 | 126.1351
| 1742 | 120.55
| 1743 | 99.2258
| 1744 | 128.6739
| 1745 | 160.3088
| 1746 | 126.6991
| 1747 | 69.3474
| 1748 | 89.3348
| 1749 | 130.6839
| 1750 | 150.4806
| 1751 | 174.8505
| 1752 | 186.7708
| 1753 | 131.0678
| 1754 | 105.6546
| 1755 | 140.7165
| 1756 | 90.098
| 1757 | 107.9507
| 1758 | 145.5284
| 1759 | 192.3284
| 1760 | 210.7092
| 1761 | 126.8576
| 1762 | 95.2207
| 1763 | 114.8167
| 1764 | 147.2778
| 1765 | 69.0636
| 1766 | 92.0781
| 1767 | 103.5454
| 1768 | 131.4421
| 1769 | 189.4127
| 1770 | 132.5044
| 1771 | 147.75
| 1772 | 93.4556
| 1773 | 80.7893
| 1774 | 169.9293
| 1775 | 120.6742
| 1776 | 131.407
| 1777 | 145.2961
| 1778 | 143.7408
| 1779 | 147.3911
| 1780 | 94.6748
| 1781 | 98.974
| 1782 | 74.0448
| 1783 | 102.3702
| 1784 | 150.7927
| 1785 | 111.6898
| 1786 | 85.4989
| 1787 | 167.011
| 1788 | 110.8166
| 1789 | 179.6635
| 1790 | 176.3607
| 1791 | 74.0932
| 1792 | 145.3938
| 1793 | 83.6428
| 1794 | 110.1432
| 1795 | 184.065
| 1796 | 94.0409
| 1797 | 135.7278
| 1798 | 167.5554
| 1799 | 114.1528
| 1800 | 124.8953
| 1801 | 80.06
| 1802 | 212.0438
| 1803 | 96.3635
| 1804 | 127.4958
| 1805 | 126.3866
| 1806 | 164.3566
| 1807 | 164.111
| 1808 | 136.2513
| 1809 | 143.8631
| 1810 | 120.5679
| 1811 | 151.4804
| 1812 | 170.1017
| 1813 | 103.5157
| 1814 | 193.2149
| 1815 | 92.6813
| 1816 | 170.6764
| 1817 | 144.9792
| 1818 | 121.5992
| 1819 | 141.6991
| 1820 | 75.9604
| 1821 | 118.6175
| 1822 | 148.3098
| 1823 | 128.011
| 1824 | 153.711
| 1825 | 201.1245
| 1826 | 112.3757
| 1827 | 153.894
| 1828 | 117.2748
| 1829 | 159.4885
| 1830 | 72.523
| 1831 | 193.1314
| 1832 | 100.8066
| 1833 | 160.0732
| 1834 | 140.8643
| 1835 | 181.6577
| 1836 | 175.2084
| 1837 | 136.4202
| 1838 | 178.5437
| 1839 | 104.2329
| 1840 | 87.2023
| 1841 | 123.0363
| 1842 | 111.8032
| 1843 | 149.3349
| 1844 | 124.6783
| 1845 | 130.9475
| 1846 | 155.6332
| 1847 | 88.8557
| 1848 | 120.1354
| 1849 | 146.5632
| 1850 | 97.6058
| 1851 | 80.262
| 1852 | 168.3007
| 1853 | 78.8317
| 1854 | 103.0728
| 1855 | 203.6772
| 1856 | 221.9115
| 1857 | 82.6828
| 1858 | 150.6831
| 1859 | 95.0179
| 1860 | 178.6136
| 1861 | 107.5327
| 1862 | 86.6066
| 1863 | 193.1339
| 1864 | 129.3291
| 1865 | 126.0199
| 1866 | 164.9602
| 1867 | 169.4123
| 1868 | 106.7375
| 1869 | 136.0912
| 1870 | 120.0025
| 1871 | 191.4405
| 1872 | 104.1816
| 1873 | 139.9627
| 1874 | 124.234
| 1875 | 135.0065
| 1876 | 156.1612
| 1877 | 183.8488
| 1878 | 124.8113
| 1879 | 159.5803
| 1880 | 86.8798
| 1881 | 160.7619
| 1882 | 106.4123
| 1883 | 97.1337
| 1884 | 119.3719
| 1885 | 110.7672
| 1886 | 165.063
| 1887 | 104.8267
| 1888 | 122.3448
| 1889 | 87.4621
| 1890 | 147.613
| 1891 | 142.9409
| 1892 | 97.6824
| 1893 | 149.0466
| 1894 | 98.594
| 1895 | 196.8705
| 1896 | 119.7004
| 1897 | 96.8633
| 1898 | 182.8751
| 1899 | 110.0734
| 1900 | 158.824
| 1901 | 139.216
| 1902 | 131.3364
| 1903 | 85.8247
| 1904 | 93.5774
| 1905 | 133.6479
| 1906 | 141.1275
| 1907 | 178.192
| 1908 | 103.0141
| 1909 | 163.5693
| 1910 | 179.2211
| 1911 | 135.6722
| 1912 | 111.7711
| 1913 | 177.1593
| 1914 | 141.236
| 1915 | 92.0813
| 1916 | 128.9296
| 1917 | 103.9201
| 1918 | 176.6868
| 1919 | 102.0491
| 1920 | 107.9774
| 1921 | 154.8041
| 1922 | 123.7785
| 1923 | 121.951
| 1924 | 159.4702
| 1925 | 154.2268
| 1926 | 121.4684
| 1927 | 108.552
| 1928 | 98.3168
| 1929 | 87.8784
| 1930 | 96.1135
| 1931 | 109.4527
| 1932 | 116.1546
| 1933 | 106.8416
| 1934 | 75.8611
| 1935 | 76.4351
| 1936 | 114.582
| 1937 | 95.4829
| 1938 | 120.2339
| 1939 | 164.1109
| 1940 | 142.2776
| 1941 | 164.2574
| 1942 | 87.6792
| 1943 | 152.585
| 1944 | 100.5726
| 1945 | 131.183
| 1946 | 120.9382
| 1947 | 154.1632
| 1948 | 157.0691
| 1949 | 172.0768
| 1950 | 99.3323
| 1951 | 100.6777
| 1952 | 129.3729
| 1953 | 98.7221
| 1954 | 153.6828
| 1955 | 129.0395
| 1956 | 83.4344
| 1957 | 104.2334
| 1958 | 150.2649
| 1959 | 115.3116
| 1960 | 162.5149
| 1961 | 108.1423
| 1962 | 87.9236
| 1963 | 113.5974
| 1964 | 107.8647
| 1965 | 95.2413
| 1966 | 161.5477
| 1967 | 127.9912
| 1968 | 148.4766
| 1969 | 159.6326
| 1970 | 153.9392
| 1971 | 109.3028
| 1972 | 108.9011
| 1973 | 142.1851
| 1974 | 94.552
| 1975 | 112.3135
| 1976 | 132.7496
| 1977 | 121.9505
| 1978 | 93.7362
| 1979 | 150.5312
| 1980 | 161.0235
| 1981 | 93.2886
| 1982 | 81.1114
| 1983 | 178.3683
| 1984 | 193.1062
| 1985 | 128.4823
| 1986 | 159.2338
| 1987 | 90.7181
| 1988 | 131.3074
| 1989 | 112.627
| 1990 | 169.3361
| 1991 | 223.7601
| 1992 | 122.9475
| 1993 | 122.1483
| 1994 | 124.8471
| 1995 | 110.9571
| 1996 | 139.3782
| 1997 | 112.7458
| 1998 | 207.0419
| 1999 | 131.6513
| 2000 | 131.8999
| 2001 | 164.7944
| 2002 | 113.1627
| 2003 | 115.5104
| 2004 | 101.485
| 2005 | 188.9549
| 2006 | 111.7532
| 2007 | 123.0582
| 2008 | 114.0724
| 2009 | 143.1709
| 2010 | 127.7322
| 2011 | 164.7335
| 2012 | 133.9938
| 2013 | 142.1131
| 2014 | 162.3307
| 2015 | 107.4332
| 2016 | 144.9228
| 2017 | 83.0314
| 2018 | 139.8938
| 2019 | 189.0159
| 2020 | 94.9906
| 2021 | 80.1964
| 2022 | 146.2023
| 2023 | 104.532
| 2024 | 130.4808
| 2025 | 134.3671
| 2026 | 86.355
| 2027 | 160.6237
| 2028 | 203.028
| 2029 | 81.0962
| 2030 | 110.9955
| 2031 | 136.1754
| 2032 | 103.3318
| 2033 | 137.1212
| 2034 | 124.8345
| 2035 | 173.2421
| 2036 | 170.4463
| 2037 | 111.8203
| 2038 | 104.2676
| 2039 | 116.6861
| 2040 | 106.842
| 2041 | 118.2251
| 2042 | 131.0994
| 2043 | 202.6973
| 2044 | 131.2206
| 2045 | 149.1099
| 2046 | 101.6975
| 2047 | 187.7351
| 2048 | 127.6008
| 2049 | 115.2977
| 2050 | 117.9821
| 2051 | 175.48
| 2052 | 110.6053
| 2053 | 135.1621
| 2054 | 98.1552
| 2055 | 136.7072
| 2056 | 76.9292
| 2057 | 131.8809
| 2058 | 183.1525
| 2059 | 120.7675
| 2060 | 183.9036
| 2061 | 111.1331
| 2062 | 80.1207
| 2063 | 92.5042
| 2064 | 90.8418
| 2065 | 107.8287
| 2066 | 88.2783
| 2067 | 173.7281
| 2068 | 107.588
| 2069 | 208.7717
| 2070 | 98.4669
| 2071 | 100.7125
| 2072 | 126.6055
| 2073 | 126.7932
| 2074 | 150.5712
| 2075 | 132.9103
| 2076 | 132.233
| 2077 | 78.0441
| 2078 | 90.3764
| 2079 | 100.8738
| 2080 | 96.2427
| 2081 | 107.3516
| 2082 | 108.0677
| 2083 | 123.2406
| 2084 | 132.4105
| 2085 | 134.8197
| 2086 | 115.5109
| 2087 | 137.4259
| 2088 | 165.8374
| 2089 | 153.3937
| 2090 | 216.7508
| 2091 | 182.7719
| 2092 | 127.8642
| 2093 | 134.6712
| 2094 | 124.9263
| 2095 | 160.5749
| 2096 | 185.5866
| 2097 | 141.3478
| 2098 | 142.208
| 2099 | 113.9413
| 2100 | 155.7467
| 2101 | 93.5178
| 2102 | 105.9554
| 2103 | 146.5904
| 2104 | 142.4357
| 2105 | 99.1322
| 2106 | 76.5483
| 2107 | 95.0807
| 2108 | 123.5776
| 2109 | 117.5139
| 2110 | 64.0204
| 2111 | 126.2485
| 2112 | 83.6179
| 2113 | 102.1839
| 2114 | 64.6493
| 2115 | 151.5044
| 2116 | 140.6661
| 2117 | 67.5981
| 2118 | 149.1976
| 2119 | 138.9757
| 2120 | 104.1964
| 2121 | 147.4909
| 2122 | 108.8661
| 2123 | 123.3353
| 2124 | 99.8486
| 2125 | 123.8632
| 2126 | 102.1224
| 2127 | 82.4696
| 2128 | 141.3271
| 2129 | 156.0361
| 2130 | 143.2227
| 2131 | 172.9172
| 2132 | 101.2141
| 2133 | 165.2733
| 2134 | 73.5279
| 2135 | 160.5648
| 2136 | 117.6796
| 2137 | 114.253
| 2138 | 102.4067
| 2139 | 134.9209
| 2140 | 156.8909
| 2141 | 115.6956
| 2142 | 183.1644
| 2143 | 77.4686
| 2144 | 93.8444
| 2145 | 177.1269
| 2146 | 153.6
| 2147 | 167.3202
| 2148 | 138.2537
| 2149 | 105.1858
| 2150 | 176.6452
| 2151 | 147.8801
| 2152 | 127.4732
| 2153 | 129.8005
| 2154 | 179.9923
| 2155 | 108.0277
| 2156 | 69.5237
| 2157 | 142.7629
| 2158 | 115.0977
| 2159 | 136.4546
| 2160 | 198.2736
| 2161 | 175.352
| 2162 | 127.5995
| 2163 | 193.1726
| 2164 | 143.709
| 2165 | 100.1101
| 2166 | 152.0463
| 2167 | 102.7209
| 2168 | 173.6987
| 2169 | 125.0186
| 2170 | 129.97
| 2171 | 112.6545
| 2172 | 86.2427
| 2173 | 80.4585
| 2174 | 134.2958
| 2175 | 111.3393
| 2176 | 121.5247
| 2177 | 133.0472
| 2178 | 128.7938
| 2179 | 167.3573
| 2180 | 139.1549
| 2181 | 182.2299
| 2182 | 164.0386
| 2183 | 129.9876
| 2184 | 122.978
| 2185 | 144.4633
| 2186 | 99.9679
| 2187 | 108.3609
| 2188 | 91.2049
| 2189 | 124.1627
| 2190 | 91.5305
| 2191 | 93.5597
| 2192 | 189.7251
| 2193 | 175.1584
| 2194 | 174.0606
| 2195 | 124.9086
| 2196 | 150.483
| 2197 | 133.1506
| 2198 | 75.267
| 2199 | 190.4246
| 2200 | 80.4507
| 2201 | 122.4501
| 2202 | 117.1866
| 2203 | 131.0909
| 2204 | 104.4108
| 2205 | 124.64
| 2206 | 146.1736
| 2207 | 79.6355
| 2208 | 140.0475
| 2209 | 146.9851
| 2210 | 96.5637
| 2211 | 114.8232
| 2212 | 156.5033
| 2213 | 104.9391
| 2214 | 138.6325
| 2215 | 166.4369
| 2216 | 87.3339
| 2217 | 78.1115
| 2218 | 92.7194
| 2219 | 146.3419
| 2220 | 124.1876
| 2221 | 99.1468
| 2222 | 130.5939
| 2223 | 151.8617
| 2224 | 132.5467
| 2225 | 148.6359
| 2226 | 125.9167
| 2227 | 129.1224
| 2228 | 69.3199
| 2229 | 118.7821
| 2230 | 126.9905
| 2231 | 121.148
| 2232 | 107.6232
| 2233 | 107.1641
| 2234 | 177.615
| 2235 | 162.1213
| 2236 | 126.6735
| 2237 | 93.4867
| 2238 | 116.5607
| 2239 | 94.0537
| 2240 | 114.2927
| 2241 | 111.7273
| 2242 | 148.3188
| 2243 | 133.2281
| 2244 | 136.4086
| 2245 | 94.7882
| 2246 | 196.3412
| 2247 | 98.1618
| 2248 | 74.9084
| 2249 | 101.4822
| 2250 | 113.4654
| 2251 | 133.2375
| 2252 | 109.1627
| 2253 | 144.7386
| 2254 | 107.4617
| 2255 | 148.0975
| 2256 | 175.3401
| 2257 | 85.7679
| 2258 | 108.8401
| 2259 | 138.5358
| 2260 | 185.9682
| 2261 | 105.8788
| 2262 | 124.3652
| 2263 | 98.5347
| 2264 | 158.4544
| 2265 | 122.371
| 2266 | 117.8309
| 2267 | 94.2561
| 2268 | 103.3105
| 2269 | 104.9438
| 2270 | 74.3576
| 2271 | 113.9287
| 2272 | 120.8508
| 2273 | 174.7316
| 2274 | 145.277
| 2275 | 105.0644
| 2276 | 88.0281
| 2277 | 67.364
| 2278 | 132.3488
| 2279 | 87.9809
| 2280 | 122.2103
| 2281 | 135.6049
| 2282 | 91.2835
| 2283 | 89.339
| 2284 | 63.9032
| 2285 | 83.6053
| 2286 | 126.3409
| 2287 | 142.8054
| 2288 | 105.7569
| 2289 | 159.5487
| 2290 | 132.7886
| 2291 | 162.3152
| 2292 | 119.4316
| 2293 | 130.7419
| 2294 | 183.5296
| 2295 | 107.0868
| 2296 | 170.4855
| 2297 | 134.865
| 2298 | 151.0291
| 2299 | 86.6889
| 2300 | 135.6008
| 2301 | 73.7803
| 2302 | 127.7474
| 2303 | 77.6192
| 2304 | 160.7841
| 2305 | 108.7153
| 2306 | 101.6793
| 2307 | 92.3951
| 2308 | 102.4596
| 2309 | 139.6019
| 2310 | 166.1733
| 2311 | 135.5756
| 2312 | 127.9158
| 2313 | 161.4268
| 2314 | 146.7934
| 2315 | 127.4657
| 2316 | 175.096
| 2317 | 89.708
| 2318 | 98.0251
| 2319 | 129.1073
| 2320 | 188.021
| 2321 | 160.7556
| 2322 | 99.496
| 2323 | 156.1518
| 2324 | 158.1945
| 2325 | 148.7652
| 2326 | 84.242
| 2327 | 84.5592
| 2328 | 135.2731
| 2329 | 148.0069
| 2330 | 131.2753
| 2331 | 107.6712
| 2332 | 86.4557
| 2333 | 103.914
| 2334 | 111.8272
| 2335 | 115.0427
| 2336 | 99.0118
| 2337 | 116.5574
| 2338 | 126.0579
| 2339 | 126.5151
| 2340 | 140.5648
| 2341 | 134.7432
| 2342 | 112.7118
| 2343 | 96.038
| 2344 | 92.3352
| 2345 | 129.8001
| 2346 | 97.208
| 2347 | 152.0637
| 2348 | 134.6799
| 2349 | 91.646
| 2350 | 74.8428
| 2351 | 141.8354
| 2352 | 116.3141
| 2353 | 113.6353
| 2354 | 165.0706
| 2355 | 108.7251
| 2356 | 193.2124
| 2357 | 161.0555
| 2358 | 152.769
| 2359 | 69.6842
| 2360 | 101.8617
| 2361 | 140.7497
| 2362 | 153.8411
| 2363 | 141.6278
| 2364 | 123.8204
| 2365 | 96.2302
| 2366 | 151.1859
| 2367 | 102.2637
| 2368 | 78.037
| 2369 | 130.7667
| 2370 | 116.9803
| 2371 | 125.3165
| 2372 | 121.879
| 2373 | 91.1478
| 2374 | 129.5439
| 2375 | 176.2277
| 2376 | 147.2381
| 2377 | 95.5487
| 2378 | 111.9872
| 2379 | 88.7935
| 2380 | 167.3553
| 2381 | 168.362
| 2382 | 116.4685
| 2383 | 126.5938
| 2384 | 138.2882
| 2385 | 100.5917
| 2386 | 137.0053
| 2387 | 129.3187
| 2388 | 133.7467
| 2389 | 94.1703
| 2390 | 111.5016
| 2391 | 176.3875
| 2392 | 155.1882
| 2393 | 120.7036
| 2394 | 152.604
| 2395 | 112.742
| 2396 | 101.6246
| 2397 | 180.7357
| 2398 | 90.1386
| 2399 | 186.3195
| 2400 | 91.0827
| 2401 | 147.6544
| 2402 | 162.4831
| 2403 | 109.8073
| 2404 | 150.8813
| 2405 | 157.5109
| 2406 | 83.3567
| 2407 | 115.2133
| 2408 | 135.2384
| 2409 | 85.2428
| 2410 | 105.2893
| 2411 | 186.5972
| 2412 | 104.203
| 2413 | 100.8972
| 2414 | 138.6192
| 2415 | 137.5095
| 2416 | 174.0117
| 2417 | 126.4768
| 2418 | 93.2834
| 2419 | 172.6514
| 2420 | 153.0654
| 2421 | 102.8527
| 2422 | 108.7509
| 2423 | 140.726
| 2424 | 101.0374
| 2425 | 111.1495
| 2426 | 177.4523
| 2427 | 188.1501
| 2428 | 137.8814
| 2429 | 162.0154
| 2430 | 136.4178
| 2431 | 202.3451
| 2432 | 122.3795
| 2433 | 119.4538
| 2434 | 75.7247
| 2435 | 157.3292
| 2436 | 76.7065
| 2437 | 134.75
| 2438 | 203.5017
| 2439 | 161.5213
| 2440 | 111.002
| 2441 | 166.5036
| 2442 | 115.5413
| 2443 | 69.7223
| 2444 | 86.505
| 2445 | 111.2361
| 2446 | 104.959
| 2447 | 90.115
| 2448 | 115.1605
| 2449 | 85.9946
| 2450 | 152.7747
| 2451 | 98.6807
| 2452 | 164.2282
| 2453 | 159.8187
| 2454 | 119.4518
| 2455 | 182.5695
| 2456 | 124.3356
| 2457 | 145.9508
| 2458 | 115.1936
| 2459 | 115.3023
| 2460 | 84.9403
| 2461 | 90.1048
| 2462 | 128.0527
| 2463 | 95.3893
| 2464 | 123.666
| 2465 | 120.3699
| 2466 | 113.4027
| 2467 | 138.1285
| 2468 | 113.5042
| 2469 | 93.3519
| 2470 | 126.313
| 2471 | 143.0746
| 2472 | 119.3679
| 2473 | 150.624
| 2474 | 100.5687
| 2475 | 137.7393
| 2476 | 139.9327
| 2477 | 163.4038
| 2478 | 160.0549
| 2479 | 80.8378
| 2480 | 97.9286
| 2481 | 141.7661
| 2482 | 146.5304
| 2483 | 110.7172
| 2484 | 119.7718
| 2485 | 100.2333
| 2486 | 144.4628
| 2487 | 136.6338
| 2488 | 118.0236
| 2489 | 108.5076
| 2490 | 108.746
| 2491 | 88.3979
| 2492 | 153.4909
| 2493 | 169.0853
| 2494 | 162.4283
| 2495 | 106.5647
| 2496 | 145.0659
| 2497 | 127.3769
| 2498 | 149.466
| 2499 | 82.6019
| 2500 | 153.0054
| 2501 | 93.0194
| 2502 | 139.138
| 2503 | 117.6399
| 2504 | 73.0199
| 2505 | 79.0396
| 2506 | 124.0935
| 2507 | 143.5877
| 2508 | 128.4574
| 2509 | 78.2558
| 2510 | 172.1645
| 2511 | 132.5959
| 2512 | 127.6918
| 2513 | 98.8437
| 2514 | 97.9625
| 2515 | 202.1369
| 2516 | 141.9071
| 2517 | 78.1922
| 2518 | 86.8077
| 2519 | 147.5253
| 2520 | 178.9655
| 2521 | 124.6554
| 2522 | 125.1867
| 2523 | 87.0969
| 2524 | 103.9136
| 2525 | 137.9614
| 2526 | 142.69
| 2527 | 107.1577
| 2528 | 112.6783
| 2529 | 191.5175
| 2530 | 126.9686
| 2531 | 153.7519
| 2532 | 98.5226
| 2533 | 154.8895
| 2534 | 87.0172
| 2535 | 78.9876
| 2536 | 159.0554
| 2537 | 168.9481
| 2538 | 84.0636
| 2539 | 87.4231
| 2540 | 138.3934
| 2541 | 117.4799
| 2542 | 98.0621
| 2543 | 120.432
| 2544 | 175.1443
| 2545 | 140.21
| 2546 | 169.2358
| 2547 | 122.7817
| 2548 | 91.3047
| 2549 | 82.5937
| 2550 | 129.8747
| 2551 | 72.5528
| 2552 | 98.1397
| 2553 | 158.3382
| 2554 | 178.5794
| 2555 | 114.2191
| 2556 | 140.1915
| 2557 | 92.3442
| 2558 | 157.8431
| 2559 | 139.4403
| 2560 | 80.6092
| 2561 | 125.4925
| 2562 | 111.684
| 2563 | 108.0168
| 2564 | 107.8987
| 2565 | 154.0717
| 2566 | 129.0225
| 2567 | 100.8274
| 2568 | 167.8439
| 2569 | 123.451
| 2570 | 99.8632
| 2571 | 124.3468
| 2572 | 135.2821
| 2573 | 149.229
| 2574 | 183.6688
| 2575 | 155.2061
| 2576 | 156.1946
| 2577 | 109.9148
| 2578 | 125.2925
| 2579 | 122.6519
| 2580 | 122.8555
| 2581 | 140.3614
| 2582 | 66.969
| 2583 | 92.1239
| 2584 | 151.1521
| 2585 | 125.2595
| 2586 | 182.9627
| 2587 | 160.5728
| 2588 | 133.8338
| 2589 | 86.2661
| 2590 | 166.0377
| 2591 | 85.6992
| 2592 | 146.0439
| 2593 | 107.7353
| 2594 | 128.6726
| 2595 | 134.0741
| 2596 | 120.1129
| 2597 | 146.025
| 2598 | 165.8899
| 2599 | 109.3024
| 2600 | 82.7653
| 2601 | 199.9438
| 2602 | 122.6105
| 2603 | 99.7832
| 2604 | 110.5463
| 2605 | 113.8949
| 2606 | 130.0073
| 2607 | 175.5873
| 2608 | 116.6135
| 2609 | 113.927
| 2610 | 72.8194
| 2611 | 156.2008
| 2612 | 93.5921
| 2613 | 148.384
| 2614 | 161.5852
| 2615 | 100.0224
| 2616 | 85.2174
| 2617 | 129.0703
| 2618 | 170.8687
| 2619 | 101.0315
| 2620 | 172.3463
| 2621 | 105.9395
| 2622 | 141.5044
| 2623 | 71.2692
| 2624 | 88.4989
| 2625 | 184.1835
| 2626 | 125.7293
| 2627 | 129.0994
| 2628 | 92.4934
| 2629 | 136.525
| 2630 | 126.5714
| 2631 | 130.4179
| 2632 | 127.33
| 2633 | 157.0912
| 2634 | 133.8635
| 2635 | 121.1762
| 2636 | 134.4169
| 2637 | 173.8804
| 2638 | 160.0284
| 2639 | 129.5172
| 2640 | 74.9616
| 2641 | 76.56
| 2642 | 158.6969
| 2643 | 119.5626
| 2644 | 175.725
| 2645 | 93.3039
| 2646 | 119.6655
| 2647 | 134.0183
| 2648 | 153.8205
| 2649 | 81.4978
| 2650 | 127.8399
| 2651 | 110.4043
| 2652 | 148.303
| 2653 | 107.0794
| 2654 | 141.1564
| 2655 | 110.8798
| 2656 | 147.8297
| 2657 | 106.9788
| 2658 | 132.1684
| 2659 | 155.5852
| 2660 | 140.9909
| 2661 | 76.0299
| 2662 | 99.8499
| 2663 | 186.4026
| 2664 | 100.8403
| 2665 | 157.2209
| 2666 | 138.8168
| 2667 | 75.5229
| 2668 | 147.5878
| 2669 | 81.1596
| 2670 | 74.1879
| 2671 | 161.7968
| 2672 | 71.7264
| 2673 | 144.8106
| 2674 | 120.4604
| 2675 | 120.3675
| 2676 | 167.7239
| 2677 | 163.1652
| 2678 | 113.4196
| 2679 | 175.3744
| 2680 | 134.4716
| 2681 | 167.9452
| 2682 | 181.6967
| 2683 | 108.4327
| 2684 | 121.2875
| 2685 | 95.2448
| 2686 | 209.4764
| 2687 | 162.8691
| 2688 | 160.2286
| 2689 | 73.0018
| 2690 | 101.052
| 2691 | 123.1755
| 2692 | 151.421
| 2693 | 91.1653
| 2694 | 78.4824
| 2695 | 107.363
| 2696 | 148.6908
| 2697 | 99.2824
| 2698 | 136.6028
| 2699 | 95.0067
| 2700 | 162.8624
| 2701 | 149.5479
| 2702 | 105.1752
| 2703 | 161.8979
| 2704 | 156.1469
| 2705 | 141.0512
| 2706 | 131.053
| 2707 | 90.0696
| 2708 | 184.8544
| 2709 | 133.7112
| 2710 | 91.6431
| 2711 | 142.4461
| 2712 | 156.6841
| 2713 | 118.232
| 2714 | 102.3684
| 2715 | 108.1243
| 2716 | 95.2325
| 2717 | 133.6332
| 2718 | 106.7119
| 2719 | 188.8536
| 2720 | 151.4151
| 2721 | 175.1155
| 2722 | 121.2251
| 2723 | 94.7049
| 2724 | 98.1531
| 2725 | 185.7849
| 2726 | 121.0019
| 2727 | 175.2949
| 2728 | 123.0079
| 2729 | 158.5123
| 2730 | 95.1
| 2731 | 128.1785
| 2732 | 105.8419
| 2733 | 107.4332
| 2734 | 177.4566
| 2735 | 141.1588
| 2736 | 145.6933
| 2737 | 136.8405
| 2738 | 143.3631
| 2739 | 144.6948
| 2740 | 80.1788
| 2741 | 132.2384
| 2742 | 149.4688
| 2743 | 103.4148
| 2744 | 168.5829
| 2745 | 180.1351
| 2746 | 152.7374
| 2747 | 62.3582
| 2748 | 141.1887
| 2749 | 148.5291
| 2750 | 121.9601
| 2751 | 102.8978
| 2752 | 155.8584
| 2753 | 169.833
| 2754 | 81.9087
| 2755 | 101.734
| 2756 | 89.0359
| 2757 | 134.699
| 2758 | 147.1998
| 2759 | 94.2773
| 2760 | 185.0449
| 2761 | 149.5218
| 2762 | 85.6979
| 2763 | 91.7117
| 2764 | 153.731
| 2765 | 65.9496
| 2766 | 115.4382
| 2767 | 93.0978
| 2768 | 170.9184
| 2769 | 147.8209
| 2770 | 125.2559
| 2771 | 95.3502
| 2772 | 105.9075
| 2773 | 144.8358
| 2774 | 67.8806
| 2775 | 75.6366
| 2776 | 94.2505
| 2777 | 160.632
| 2778 | 105.8303
| 2779 | 93.7732
| 2780 | 156.2191
| 2781 | 82.7953
| 2782 | 167.8258
| 2783 | 165.3543
| 2784 | 93.0041
| 2785 | 75.6377
| 2786 | 85.1539
| 2787 | 125.9054
| 2788 | 116.4555
| 2789 | 165.0378
| 2790 | 176.7006
| 2791 | 148.6296
| 2792 | 152.211
| 2793 | 105.1251
| 2794 | 97.0066
| 2795 | 83.3086
| 2796 | 113.9787
| 2797 | 111.4434
| 2798 | 86.3877
| 2799 | 148.0656
| 2800 | 121.7042
| 2801 | 113.1233
| 2802 | 130.2757
| 2803 | 98.0327
| 2804 | 87.2447
| 2805 | 88.279
| 2806 | 129.8952
| 2807 | 106.7793
| 2808 | 116.708
| 2809 | 145.563
| 2810 | 81.7419
| 2811 | 155.9694
| 2812 | 128.4458
| 2813 | 143.991
| 2814 | 143.6416
| 2815 | 114.2137
| 2816 | 72.9798
| 2817 | 164.0788
| 2818 | 180.6977
| 2819 | 155.9055
| 2820 | 127.0985
| 2821 | 88.4159
| 2822 | 170.6093
| 2823 | 108.2488
| 2824 | 138.5801
| 2825 | 142.0731
| 2826 | 161.5308
| 2827 | 155.4491
| 2828 | 192.9225
| 2829 | 105.9325
| 2830 | 177.5193
| 2831 | 165.1675
| 2832 | 131.8829
| 2833 | 121.1681
| 2834 | 100.3587
| 2835 | 146.266
| 2836 | 122.7397
| 2837 | 111.6978
| 2838 | 152.7464
| 2839 | 98.9437
| 2840 | 194.3652
| 2841 | 153.7412
| 2842 | 110.7144
| 2843 | 176.9434
| 2844 | 91.2436
| 2845 | 99.6564
| 2846 | 124.2557
| 2847 | 181.0461
| 2848 | 178.5596
| 2849 | 65.3156
| 2850 | 84.9123
| 2851 | 138.2559
| 2852 | 177.934
| 2853 | 133.1826
| 2854 | 127.1973
| 2855 | 102.896
| 2856 | 163.3406
| 2857 | 146.061
| 2858 | 144.0372
| 2859 | 87.9052
| 2860 | 150.6497
| 2861 | 124.7615
| 2862 | 104.5381
| 2863 | 140.3497
| 2864 | 170.5267
| 2865 | 177.4173
| 2866 | 128.3912
| 2867 | 128.0403
| 2868 | 142.903
| 2869 | 139.7299
| 2870 | 106.2171
| 2871 | 102.4885
| 2872 | 193.8767
| 2873 | 99.952
| 2874 | 117.9762
| 2875 | 125.1745
| 2876 | 160.0864
| 2877 | 100.1352
| 2878 | 115.2717
| 2879 | 173.1852
| 2880 | 136.1121
| 2881 | 131.1814
| 2882 | 160.6796
| 2883 | 93.0811
| 2884 | 190.9924
| 2885 | 132.9916
| 2886 | 90.9773
| 2887 | 72.6693
| 2888 | 152.2537
| 2889 | 99.2378
| 2890 | 100.1753
| 2891 | 118.7431
| 2892 | 189.5097
| 2893 | 70.4305
| 2894 | 97.4051
| 2895 | 85.154
| 2896 | 121.2518
| 2897 | 117.0766
| 2898 | 146.5621
| 2899 | 145.1073
| 2900 | 149.4182
| 2901 | 127.9108
| 2902 | 148.8975
| 2903 | 173.3521
| 2904 | 85.2165
| 2905 | 147.9201
| 2906 | 87.1952
| 2907 | 132.1922
| 2908 | 195.5684
| 2909 | 90.2111
| 2910 | 159.4818
| 2911 | 123.6673
| 2912 | 133.3588
| 2913 | 102.7357
| 2914 | 70.9007
| 2915 | 132.5918
| 2916 | 141.1388
| 2917 | 195.0624
| 2918 | 80.597
| 2919 | 122.3096
| 2920 | 134.3154
| 2921 | 131.1956
| 2922 | 161.5504
| 2923 | 171.5675
| 2924 | 133.8448
| 2925 | 185.0524
| 2926 | 122.1478
| 2927 | 181.2778
| 2928 | 125.8225
| 2929 | 94.1713
| 2930 | 170.5614
| 2931 | 117.562
| 2932 | 109.3963
| 2933 | 108.4105
| 2934 | 153.3008
| 2935 | 111.2808
| 2936 | 197.0048
| 2937 | 128.9059
| 2938 | 80.2129
| 2939 | 107.8611
| 2940 | 89.2999
| 2941 | 114.7838
| 2942 | 150.2935
| 2943 | 130.6055
| 2944 | 154.7654
| 2945 | 92.9719
| 2946 | 94.1049
| 2947 | 113.0237
| 2948 | 76.9131
| 2949 | 83.8972
| 2950 | 148.3113
| 2951 | 143.0903
| 2952 | 100.5377
| 2953 | 174.0038
| 2954 | 134.5286
| 2955 | 115.5318
| 2956 | 153.48
| 2957 | 110.1855
| 2958 | 172.5682
| 2959 | 144.5015
| 2960 | 166.7065
| 2961 | 115.7822
| 2962 | 184.2289
| 2963 | 90.5438
| 2964 | 154.9665
| 2965 | 90.8688
| 2966 | 103.8713
| 2967 | 106.2684
| 2968 | 141.5626
| 2969 | 90.6737
| 2970 | 103.9292
| 2971 | 165.4604
| 2972 | 202.3825
| 2973 | 157.4661
| 2974 | 135.0817
| 2975 | 140.4181
| 2976 | 141.9278
| 2977 | 94.3117
| 2978 | 145.2413
| 2979 | 96.7322
| 2980 | 169.5804
| 2981 | 131.7811
| 2982 | 194.8605
| 2983 | 109.2554
| 2984 | 102.9235
| 2985 | 154.5696
| 2986 | 114.8547
| 2987 | 125.9593
| 2988 | 108.8034
| 2989 | 84.8285
| 2990 | 151.7069
| 2991 | 111.7544
| 2992 | 91.2514
| 2993 | 84.5057
| 2994 | 82.3257
| 2995 | 127.9332
| 2996 | 144.9645
| 2997 | 105.5631
| 2998 | 72.9425
| 2999 | 109.7586
| 3000 | 160.2821
| 3001 | 109.4669
| 3002 | 194.3541
| 3003 | 100.6683
| 3004 | 162.6524
| 3005 | 189.1713
| 3006 | 138.2998
| 3007 | 107.4768
| 3008 | 179.0966
| 3009 | 170.2363
| 3010 | 108.9507
| 3011 | 150.2303
| 3012 | 123.012
| 3013 | 97.1593
| 3014 | 135.4875
| 3015 | 84.3464
| 3016 | 117.0373
| 3017 | 198.0365
| 3018 | 101.3862
| 3019 | 117.9754
| 3020 | 122.6468
| 3021 | 134.3671
| 3022 | 85.9245
| 3023 | 125.5721
| 3024 | 123.5026
| 3025 | 159.2589
| 3026 | 147.3979
| 3027 | 203.8198
| 3028 | 102.562
| 3029 | 115.7921
| 3030 | 109.6504
| 3031 | 149.0186
| 3032 | 98.2978
| 3033 | 79.8278
| 3034 | 129.7825
| 3035 | 152.7464
| 3036 | 95.8238
| 3037 | 165.669
| 3038 | 159.5778
| 3039 | 143.6954
| 3040 | 113.0972
| 3041 | 76.5553
| 3042 | 81.4289
| 3043 | 94.7248
| 3044 | 170.744
| 3045 | 104.0376
| 3046 | 127.5771
| 3047 | 98.1572
| 3048 | 98.847
| 3049 | 135.0611
| 3050 | 101.5977
| 3051 | 144.4014
| 3052 | 94.8332
| 3053 | 151.2391
| 3054 | 123.876
| 3055 | 101.0348
| 3056 | 102.2932
| 3057 | 115.1483
| 3058 | 120.1129
| 3059 | 153.7529
| 3060 | 126.3571
| 3061 | 138.6813
| 3062 | 110.5429
| 3063 | 183.2462
| 3064 | 156.8512
| 3065 | 178.405
| 3066 | 149.3516
| 3067 | 97.0777
| 3068 | 128.3636
| 3069 | 102.1708
| 3070 | 135.0629
| 3071 | 92.5765
| 3072 | 128.7242
| 3073 | 75.8605
| 3074 | 153.1092
| 3075 | 101.8929
| 3076 | 160.2832
| 3077 | 182.4131
| 3078 | 145.474
| 3079 | 162.8244
| 3080 | 147.0576
| 3081 | 82.1912
| 3082 | 197.7995
| 3083 | 153.6645
| 3084 | 108.8839
| 3085 | 130.9701
| 3086 | 152.8576
| 3087 | 87.2808
| 3088 | 67.3018
| 3089 | 157.6914
| 3090 | 176.2182
| 3091 | 151.908
| 3092 | 149.5592
| 3093 | 84.4248
| 3094 | 200.6623
| 3095 | 161.4775
| 3096 | 156.0493
| 3097 | 127.514
| 3098 | 102.1287
| 3099 | 101.7464
| 3100 | 184.0503
| 3101 | 135.7384
| 3102 | 128.6174
| 3103 | 146.363
| 3104 | 100.9305
| 3105 | 160.9633
| 3106 | 118.6358
| 3107 | 149.6741
| 3108 | 83.3147
| 3109 | 116.6377
| 3110 | 164.9734
| 3111 | 106.6839
| 3112 | 123.5954
| 3113 | 160.2097
| 3114 | 82.6363
| 3115 | 81.9123
| 3116 | 115.4681
| 3117 | 91.806
| 3118 | 132.3336
| 3119 | 125.0292
| 3120 | 89.4067
| 3121 | 89.1167
| 3122 | 143.6023
| 3123 | 128.0574
| 3124 | 83.1028
| 3125 | 67.4825
| 3126 | 99.2786
| 3127 | 144.7463
| 3128 | 158.4918
| 3129 | 107.8307
| 3130 | 178.5611
| 3131 | 154.4704
| 3132 | 123.9217
| 3133 | 125.4096
| 3134 | 157.5335
| 3135 | 152.2318
| 3136 | 153.5615
| 3137 | 134.9581
| 3138 | 89.2265
| 3139 | 190.3512
| 3140 | 120.1172
| 3141 | 151.1682
| 3142 | 116.0794
| 3143 | 149.5272
| 3144 | 178.8037
| 3145 | 112.0351
| 3146 | 116.9079
| 3147 | 101.3047
| 3148 | 85.5442
| 3149 | 96.8565
| 3150 | 153.364
| 3151 | 75.2652
| 3152 | 130.7876
| 3153 | 151.5033
| 3154 | 118.7523
| 3155 | 135.5037
| 3156 | 93.983
| 3157 | 128.1834
| 3158 | 137.1079
| 3159 | 85.686
| 3160 | 124.8495
| 3161 | 140.4551
| 3162 | 104.5207
| 3163 | 128.8326
| 3164 | 115.9028
| 3165 | 93.6477
| 3166 | 159.1731
| 3167 | 166.6195
| 3168 | 97.6783
| 3169 | 111.2383
| 3170 | 105.0048
| 3171 | 83.757
| 3172 | 116.0843
| 3173 | 99.3248
| 3174 | 139.9123
| 3175 | 143.6729
| 3176 | 104.2753
| 3177 | 161.5012
| 3178 | 129.2754
| 3179 | 98.589
| 3180 | 146.6181
| 3181 | 159.5661
| 3182 | 99.422
| 3183 | 127.0034
| 3184 | 82.338
| 3185 | 107.9167
| 3186 | 145.5449
| 3187 | 126.9774
| 3188 | 141.9813
| 3189 | 106.0346
| 3190 | 169.273
| 3191 | 144.5096
| 3192 | 111.5317
| 3193 | 183.2068
| 3194 | 120.3681
| 3195 | 144.3859
| 3196 | 153.917
| 3197 | 126.9824
| 3198 | 102.0114
| 3199 | 132.7443
| 3200 | 123.9078
| 3201 | 137.4478
| 3202 | 98.5331
| 3203 | 140.729
| 3204 | 122.5356
| 3205 | 85.3846
| 3206 | 138.4035
| 3207 | 136.1439
| 3208 | 89.1627
| 3209 | 119.3512
| 3210 | 92.6063
| 3211 | 134.1346
| 3212 | 110.1433
| 3213 | 131.4433
| 3214 | 125.575
| 3215 | 102.8767
| 3216 | 89.1128
| 3217 | 174.6233
| 3218 | 81.7919
| 3219 | 132.5928
| 3220 | 196.5887
| 3221 | 130.658
| 3222 | 110.1678
| 3223 | 129.9063
| 3224 | 181.7351
| 3225 | 111.4038
| 3226 | 119.2064
| 3227 | 140.3816
| 3228 | 160.3843
| 3229 | 98.7256
| 3230 | 151.9287
| 3231 | 210.3187
| 3232 | 115.1235
| 3233 | 189.1765
| 3234 | 115.8407
| 3235 | 169.4598
| 3236 | 131.1467
| 3237 | 78.3273
| 3238 | 145.8888
| 3239 | 142.3074
| 3240 | 126.6509
| 3241 | 156.6675
| 3242 | 167.5844
| 3243 | 155.4417
| 3244 | 133.0847
| 3245 | 120.9864
| 3246 | 151.3201
| 3247 | 136.5839
| 3248 | 100.104
| 3249 | 126.9202
| 3250 | 111.035
| 3251 | 87.1539
| 3252 | 164.9175
| 3253 | 146.3193
| 3254 | 74.0419
| 3255 | 96.7942
| 3256 | 81.8204
| 3257 | 131.2447
| 3258 | 87.4265
| 3259 | 99.625
| 3260 | 131.6292
| 3261 | 72.1499
| 3262 | 147.4577
| 3263 | 134.3934
| 3264 | 102.5457
| 3265 | 106.4069
| 3266 | 158.5118
| 3267 | 105.0816
| 3268 | 125.7451
| 3269 | 145.1195
| 3270 | 111.503
| 3271 | 179.1119
| 3272 | 112.7418
| 3273 | 116.3636
| 3274 | 102.3737
| 3275 | 90.313
| 3276 | 140.192
| 3277 | 108.9974
| 3278 | 170.4068
| 3279 | 101.2828
| 3280 | 178.5109
| 3281 | 109.0788
| 3282 | 73.418
| 3283 | 116.2921
| 3284 | 172.883
| 3285 | 174.6288
| 3286 | 127.2905
| 3287 | 141.3425
| 3288 | 128.8009
| 3289 | 143.0724
| 3290 | 66.2566
| 3291 | 106.3906
| 3292 | 98.6427
| 3293 | 131.0964
| 3294 | 88.9652
| 3295 | 230.417
| 3296 | 95.5318
| 3297 | 93.4019
| 3298 | 161.1896
| 3299 | 138.3764
| 3300 | 163.7055
| 3301 | 156.3502
| 3302 | 99.3114
| 3303 | 187.1431
| 3304 | 123.3293
| 3305 | 176.9902
| 3306 | 125.0711
| 3307 | 107.2404
| 3308 | 115.7724
| 3309 | 94.2074
| 3310 | 110.9564
| 3311 | 155.588
| 3312 | 107.6776
| 3313 | 101.3502
| 3314 | 185.222
| 3315 | 106.8198
| 3316 | 152.3698
| 3317 | 163.3284
| 3318 | 163.4141
| 3319 | 169.9742
| 3320 | 97.6609
| 3321 | 115.7951
| 3322 | 105.9476
| 3323 | 167.0714
| 3324 | 120.5409
| 3325 | 107.4705
| 3326 | 81.5144
| 3327 | 114.5741
| 3328 | 95.7329
| 3329 | 74.0948
| 3330 | 169.1453
| 3331 | 87.0537
| 3332 | 124.9417
| 3333 | 82.8727
| 3334 | 187.0009
| 3335 | 160.9691
| 3336 | 164.5194
| 3337 | 136.8744
| 3338 | 130.4276
| 3339 | 129.385
| 3340 | 71.7978
| 3341 | 82.2527
| 3342 | 82.1497
| 3343 | 131.9918
| 3344 | 128.5818
| 3345 | 161.9498
| 3346 | 92.9846
| 3347 | 104.8964
| 3348 | 152.7723
| 3349 | 134.151
| 3350 | 141.0601
| 3351 | 103.407
| 3352 | 80.5114
| 3353 | 93.0635
| 3354 | 146.0028
| 3355 | 140.1851
| 3356 | 110.335
| 3357 | 166.8653
| 3358 | 101.0609
| 3359 | 78.4469
| 3360 | 108.5678
| 3361 | 106.8846
| 3362 | 165.2493
| 3363 | 128.3003
| 3364 | 153.6269
| 3365 | 115.0716
| 3366 | 119.5096
| 3367 | 182.864
| 3368 | 127.4312
| 3369 | 146.6254
| 3370 | 86.5243
| 3371 | 178.5276
| 3372 | 91.6952
| 3373 | 114.7551
| 3374 | 122.301
| 3375 | 180.4218
| 3376 | 108.2904
| 3377 | 161.7874
| 3378 | 169.9981
| 3379 | 121.0314
| 3380 | 143.8433
| 3381 | 138.3241
| 3382 | 203.0795
| 3383 | 102.0516
| 3384 | 141.4991
| 3385 | 98.3198
| 3386 | 123.9192
| 3387 | 135.6618
| 3388 | 124.8575
| 3389 | 79.983
| 3390 | 163.1128
| 3391 | 183.8719
| 3392 | 110.067
| 3393 | 88.5466
| 3394 | 143.2726
| 3395 | 158.2449
| 3396 | 123.7037
| 3397 | 111.4621
| 3398 | 164.4627
| 3399 | 80.9003
| 3400 | 134.6916
| 3401 | 108.5364
| 3402 | 109.7247
| 3403 | 99.3741
| 3404 | 168.0901
| 3405 | 91.2707
| 3406 | 92.8373
| 3407 | 121.8829
| 3408 | 127.0163
| 3409 | 178.6149
| 3410 | 145.9766
| 3411 | 119.6036
| 3412 | 100.6029
| 3413 | 134.1437
| 3414 | 165.8842
| 3415 | 168.7682
| 3416 | 114.8206
| 3417 | 82.2335
| 3418 | 115.5401
| 3419 | 140.9457
| 3420 | 214.4332
| 3421 | 149.4042
| 3422 | 131.8116
| 3423 | 85.8741
| 3424 | 116.2293
| 3425 | 146.8609
| 3426 | 97.4506
| 3427 | 104.813
| 3428 | 100.46
| 3429 | 102.7135
| 3430 | 182.37
| 3431 | 135.8734
| 3432 | 138.3771
| 3433 | 118.8318
| 3434 | 98.9015
| 3435 | 110.7487
| 3436 | 94.8843
| 3437 | 128.2516
| 3438 | 174.4712
| 3439 | 142.7688
| 3440 | 178.0276
| 3441 | 80.0544
| 3442 | 117.8057
| 3443 | 169.3031
| 3444 | 135.4036
| 3445 | 127.2672
| 3446 | 129.322
| 3447 | 110.677
| 3448 | 96.2052
| 3449 | 179.3595
| 3450 | 157.8302
| 3451 | 93.8235
| 3452 | 119.6107
| 3453 | 185.1963
| 3454 | 84.1773
| 3455 | 113.5832
| 3456 | 92.293
| 3457 | 104.6758
| 3458 | 150.2993
| 3459 | 110.7055
| 3460 | 163.6419
| 3461 | 119.596
| 3462 | 107.4412
| 3463 | 99.4314
| 3464 | 155.1092
| 3465 | 177.8186
| 3466 | 163.9348
| 3467 | 158.4459
| 3468 | 100.4076
| 3469 | 122.2255
| 3470 | 89.754
| 3471 | 147.1411
| 3472 | 120.791
| 3473 | 163.4132
| 3474 | 100.7279
| 3475 | 119.1764
| 3476 | 147.0081
| 3477 | 131.7831
| 3478 | 95.8591
| 3479 | 84.1668
| 3480 | 107.6094
| 3481 | 106.6862
| 3482 | 102.1262
| 3483 | 72.5063
| 3484 | 86.4583
| 3485 | 141.6755
| 3486 | 130.6716
| 3487 | 71.8267
| 3488 | 95.9087
| 3489 | 180.9619
| 3490 | 155.8075
| 3491 | 166.1346
| 3492 | 91.7552
| 3493 | 89.5372
| 3494 | 169.8755
| 3495 | 92.0709
| 3496 | 161.2801
| 3497 | 165.6912
| 3498 | 114.6938
| 3499 | 137.5003
| 3500 | 139.2322
| 3501 | 117.3403
| 3502 | 160.2121
| 3503 | 154.4451
| 3504 | 192.896
| 3505 | 91.9895
| 3506 | 99.1231
| 3507 | 166.0824
| 3508 | 94.8622
| 3509 | 146.5949
| 3510 | 164.3213
| 3511 | 109.8944
| 3512 | 99.8554
| 3513 | 72.5796
| 3514 | 97.889
| 3515 | 103.6164
| 3516 | 141.9047
| 3517 | 97.3553
| 3518 | 142.1449
| 3519 | 136.6009
| 3520 | 149.1149
| 3521 | 190.6722
| 3522 | 156.2713
| 3523 | 83.7033
| 3524 | 159.668
| 3525 | 125.2798
| 3526 | 75.1391
| 3527 | 158.8301
| 3528 | 115.5548
| 3529 | 116.3602
| 3530 | 180.4016
| 3531 | 170.9884
| 3532 | 205.0914
| 3533 | 113.4583
| 3534 | 69.7431
| 3535 | 187.1815
| 3536 | 111.8041
| 3537 | 102.058
| 3538 | 142.4161
| 3539 | 122.3859
| 3540 | 118.7729
| 3541 | 156.128
| 3542 | 124.5505
| 3543 | 187.2933
| 3544 | 83.3465
| 3545 | 168.8953
| 3546 | 181.0941
| 3547 | 110.8366
| 3548 | 94.5918
| 3549 | 150.4991
| 3550 | 126.2135
| 3551 | 185.2012
| 3552 | 94.0059
| 3553 | 136.7811
| 3554 | 112.0345
| 3555 | 146.9706
| 3556 | 117.8091
| 3557 | 77.4048
| 3558 | 108.2629
| 3559 | 126.0185
| 3560 | 90.7956
| 3561 | 149.6234
| 3562 | 106.9223
| 3563 | 121.7926
| 3564 | 85.4554
| 3565 | 94.5689
| 3566 | 144.912
| 3567 | 124.3812
| 3568 | 99.1787
| 3569 | 143.1411
| 3570 | 158.6181
| 3571 | 106.6917
| 3572 | 146.7992
| 3573 | 102.9839
| 3574 | 76.8983
| 3575 | 133.0676
| 3576 | 141.1831
| 3577 | 125.9979
| 3578 | 136.5061
| 3579 | 108.7474
| 3580 | 83.8901
| 3581 | 73.7532
| 3582 | 180.381
| 3583 | 136.8963
| 3584 | 130.5842
| 3585 | 129.3576
| 3586 | 155.547
| 3587 | 163.9169
| 3588 | 123.7683
| 3589 | 99.3752
| 3590 | 112.7384
| 3591 | 165.07
| 3592 | 134.7583
| 3593 | 198.4084
| 3594 | 96.0612
| 3595 | 116.2388
| 3596 | 123.6426
| 3597 | 154.8347
| 3598 | 110.3879
| 3599 | 101.4001
| 3600 | 114.1958
| 3601 | 108.8903
| 3602 | 140.9232
| 3603 | 140.833
| 3604 | 95.5576
| 3605 | 178.6103
| 3606 | 167.0345
| 3607 | 143.4565
| 3608 | 123.7897
| 3609 | 133.4106
| 3610 | 83.5392
| 3611 | 152.0604
| 3612 | 121.7448
| 3613 | 129.881
| 3614 | 76.9436
| 3615 | 188.3948
| 3616 | 138.1639
| 3617 | 102.3072
| 3618 | 74.4773
| 3619 | 136.3374
| 3620 | 108.6806
| 3621 | 91.3457
| 3622 | 127.8994
| 3623 | 90.3815
| 3624 | 141.1259
| 3625 | 198.258
| 3626 | 96.8014
| 3627 | 105.3886
| 3628 | 117.4338
| 3629 | 152.5788
| 3630 | 143.2616
| 3631 | 144.4545
| 3632 | 142.4244
| 3633 | 160.5844
| 3634 | 117.5467
| 3635 | 125.4106
| 3636 | 105.1671
| 3637 | 92.5498
| 3638 | 121.2203
| 3639 | 170.0927
| 3640 | 108.6039
| 3641 | 108.9369
| 3642 | 137.8609
| 3643 | 100.8268
| 3644 | 101.9902
| 3645 | 128.3861
| 3646 | 92.8543
| 3647 | 141.3965
| 3648 | 103.0882
| 3649 | 152.0433
| 3650 | 73.4997
| 3651 | 133.9822
| 3652 | 147.3759
| 3653 | 106.8344
| 3654 | 132.1014
| 3655 | 124.9665
| 3656 | 99.6522
| 3657 | 162.5192
| 3658 | 121.7667
| 3659 | 172.17
| 3660 | 74.3531
| 3661 | 114.0633
| 3662 | 103.2889
| 3663 | 94.7582
| 3664 | 171.651
| 3665 | 106.163
| 3666 | 105.0584
| 3667 | 109.6949
| 3668 | 136.1074
| 3669 | 98.2868
| 3670 | 124.0082
| 3671 | 98.5656
| 3672 | 197.7218
| 3673 | 167.579
| 3674 | 172.1527
| 3675 | 146.2358
| 3676 | 144.5278
| 3677 | 89.8805
| 3678 | 145.5673
| 3679 | 96.1147
| 3680 | 136.5427
| 3681 | 127.2138
| 3682 | 69.7757
| 3683 | 159.2098
| 3684 | 149.894
| 3685 | 110.3171
| 3686 | 138.7737
| 3687 | 104.9039
| 3688 | 104.4636
| 3689 | 88.2977
| 3690 | 122.7637
| 3691 | 122.7682
| 3692 | 168.0868
| 3693 | 147.6836
| 3694 | 148.6137
| 3695 | 143.2795
| 3696 | 94.46
| 3697 | 148.8283
| 3698 | 165.4637
| 3699 | 124.7996
| 3700 | 109.0241
| 3701 | 159.1364
| 3702 | 146.2078
| 3703 | 88.7064
| 3704 | 129.9042
| 3705 | 95.2107
| 3706 | 127.6717
| 3707 | 97.3589
| 3708 | 97.3616
| 3709 | 157.2597
| 3710 | 132.685
| 3711 | 180.488
| 3712 | 82.0626
| 3713 | 139.7518
| 3714 | 109.5915
| 3715 | 94.3881
| 3716 | 122.1304
| 3717 | 197.4254
| 3718 | 156.791
| 3719 | 69.7015
| 3720 | 124.0609
| 3721 | 125.9262
| 3722 | 119.7795
| 3723 | 208.4859
| 3724 | 142.8435
| 3725 | 101.7735
| 3726 | 121.1784
| 3727 | 121.555
| 3728 | 80.3329
| 3729 | 69.657
| 3730 | 124.4603
| 3731 | 117.4586
| 3732 | 130.07
| 3733 | 167.7547
| 3734 | 147.4224
| 3735 | 149.7443
| 3736 | 110.6059
| 3737 | 161.7708
| 3738 | 128.1505
| 3739 | 143.2177
| 3740 | 123.0344
| 3741 | 110.1144
| 3742 | 123.6306
| 3743 | 139.1939
| 3744 | 122.7183
| 3745 | 112.5863
| 3746 | 123.3427
| 3747 | 115.3104
| 3748 | 172.8401
| 3749 | 180.5823
| 3750 | 123.5308
| 3751 | 90.1354
| 3752 | 108.4524
| 3753 | 127.8123
| 3754 | 121.7067
| 3755 | 93.0762
| 3756 | 159.378
| 3757 | 197.6806
| 3758 | 160.4311
| 3759 | 113.9983
| 3760 | 144.5501
| 3761 | 111.3853
| 3762 | 77.9104
| 3763 | 82.0047
| 3764 | 86.1962
| 3765 | 71.3669
| 3766 | 111.7465
| 3767 | 191.0023
| 3768 | 112.8477
| 3769 | 132.6026
| 3770 | 155.6006
| 3771 | 113.4166
| 3772 | 134.1501
| 3773 | 133.9442
| 3774 | 118.1013
| 3775 | 170.6665
| 3776 | 135.7009
| 3777 | 93.5683
| 3778 | 112.524
| 3779 | 165.4644
| 3780 | 189.6802
| 3781 | 146.75
| 3782 | 66.5938
| 3783 | 101.2026
| 3784 | 103.2564
| 3785 | 183.3432
| 3786 | 103.6442
| 3787 | 166.5046
| 3788 | 129.4346
| 3789 | 187.7804
| 3790 | 97.4277
| 3791 | 131.0648
| 3792 | 93.6861
| 3793 | 174.0869
| 3794 | 123.7335
| 3795 | 176.5076
| 3796 | 73.3627
| 3797 | 142.7312
| 3798 | 158.8222
| 3799 | 180.4662
| 3800 | 151.2932
| 3801 | 110.1705
| 3802 | 171.7705
| 3803 | 150.7242
| 3804 | 204.5493
| 3805 | 86.7571
| 3806 | 86.5887
| 3807 | 162.6058
| 3808 | 101.999
| 3809 | 111.587
| 3810 | 169.3928
| 3811 | 131.004
| 3812 | 83.6291
| 3813 | 77.4958
| 3814 | 83.4647
| 3815 | 96.0784
| 3816 | 87.1386
| 3817 | 142.3806
| 3818 | 98.4424
| 3819 | 151.4949
| 3820 | 97.8303
| 3821 | 126.5011
| 3822 | 194.9918
| 3823 | 73.146
| 3824 | 117.5296
| 3825 | 158.1456
| 3826 | 181.0586
| 3827 | 97.1814
| 3828 | 141.2456
| 3829 | 125.5028
| 3830 | 106.9192
| 3831 | 130.882
| 3832 | 175.5832
| 3833 | 181.8131
| 3834 | 65.992
| 3835 | 121.0647
| 3836 | 126.3939
| 3837 | 93.9152
| 3838 | 111.8129
| 3839 | 100.9487
| 3840 | 113.0811
| 3841 | 140.9446
| 3842 | 122.9705
| 3843 | 104.7574
| 3844 | 144.481
| 3845 | 173.4955
| 3846 | 155.2117
| 3847 | 124.9873
| 3848 | 177.3113
| 3849 | 117.6322
| 3850 | 174.7595
| 3851 | 127.8923
| 3852 | 94.2955
| 3853 | 87.523
| 3854 | 90.0797
| 3855 | 74.9852
| 3856 | 66.4647
| 3857 | 168.1686
| 3858 | 92.1018
| 3859 | 104.0796
| 3860 | 122.8535
| 3861 | 112.0395
| 3862 | 111.5078
| 3863 | 100.9767
| 3864 | 115.6148
| 3865 | 138.2203
| 3866 | 95.4533
| 3867 | 138.7822
| 3868 | 111.046
| 3869 | 156.0158
| 3870 | 169.6312
| 3871 | 148.8937
| 3872 | 149.5767
| 3873 | 109.9543
| 3874 | 71.4999
| 3875 | 116.95
| 3876 | 114.9865
| 3877 | 130.8121
| 3878 | 147.4293
| 3879 | 130.2537
| 3880 | 120.0041
| 3881 | 131.6797
| 3882 | 101.8796
| 3883 | 126.38
| 3884 | 107.9886
| 3885 | 202.7348
| 3886 | 88.6243
| 3887 | 139.7718
| 3888 | 119.5558
| 3889 | 160.2378
| 3890 | 107.3681
| 3891 | 84.7802
| 3892 | 153.8958
| 3893 | 164.0214
| 3894 | 179.1641
| 3895 | 106.7298
| 3896 | 139.1993
| 3897 | 132.1237
| 3898 | 193.8302
| 3899 | 182.341
| 3900 | 127.3457
| 3901 | 164.7933
| 3902 | 137.8375
| 3903 | 90.0491
| 3904 | 135.8632
| 3905 | 204.6407
| 3906 | 207.9501
| 3907 | 144.3838
| 3908 | 131.5173
| 3909 | 89.8322
| 3910 | 105.4004
| 3911 | 97.9526
| 3912 | 95.3584
| 3913 | 169.037
| 3914 | 202.0792
| 3915 | 123.2454
| 3916 | 116.7089
| 3917 | 169.1386
| 3918 | 152.5663
| 3919 | 124.1782
| 3920 | 141.3453
| 3921 | 145.5471
| 3922 | 79.838
| 3923 | 177.9523
| 3924 | 187.4989
| 3925 | 106.0239
| 3926 | 111.51
| 3927 | 183.6462
| 3928 | 164.0897
| 3929 | 117.373
| 3930 | 148.8792
| 3931 | 161.3615
| 3932 | 136.566
| 3933 | 165.9477
| 3934 | 121.0447
| 3935 | 154.0428
| 3936 | 162.1211
| 3937 | 102.4377
| 3938 | 132.286
| 3939 | 102.222
| 3940 | 192.0396
| 3941 | 131.1705
| 3942 | 114.9233
| 3943 | 103.5418
| 3944 | 152.1733
| 3945 | 153.3637
| 3946 | 178.0494
| 3947 | 163.3357
| 3948 | 144.3121
| 3949 | 175.0039
| 3950 | 96.9802
| 3951 | 107.1684
| 3952 | 75.2644
| 3953 | 171.9888
| 3954 | 198.0817
| 3955 | 144.7373
| 3956 | 187.9756
| 3957 | 126.9427
| 3958 | 85.3356
| 3959 | 155.8794
| 3960 | 175.9252
| 3961 | 127.2848
| 3962 | 96.0066
| 3963 | 103.3614
| 3964 | 126.8408
| 3965 | 156.3491
| 3966 | 92.4383
| 3967 | 126.7788
| 3968 | 159.0666
| 3969 | 154.8788
| 3970 | 108.9906
| 3971 | 175.3076
| 3972 | 177.7192
| 3973 | 149.6529
| 3974 | 120.1622
| 3975 | 109.4284
| 3976 | 129.678
| 3977 | 92.6891
| 3978 | 154.1578
| 3979 | 93.8305
| 3980 | 149.8857
| 3981 | 152.182
| 3982 | 141.8466
| 3983 | 140.2019
| 3984 | 96.8438
| 3985 | 85.9766
| 3986 | 165.6385
| 3987 | 109.8153
| 3988 | 152.9147
| 3989 | 205.3689
| 3990 | 117.3444
| 3991 | 112.8539
| 3992 | 161.4519
| 3993 | 147.9765
| 3994 | 125.3875
| 3995 | 105.9678
| 3996 | 109.8589
| 3997 | 133.2366
| 3998 | 91.6699
| 3999 | 149.719
| 4000 | 139.0535
| 4001 | 158.4112
| 4002 | 142.5653
| 4003 | 135.5018
| 4004 | 117.4021
| 4005 | 122.5548
| 4006 | 175.7381
| 4007 | 113.9539
| 4008 | 192.4397
| 4009 | 134.0506
| 4010 | 160.0194
| 4011 | 149.8699
| 4012 | 133.7487
| 4013 | 109.6495
| 4014 | 141.3546
| 4015 | 90.3147
| 4016 | 151.3051
| 4017 | 110.5729
| 4018 | 104.6277
| 4019 | 165.231
| 4020 | 112.4202
| 4021 | 94.3714
| 4022 | 78.8675
| 4023 | 97.4591
| 4024 | 115.273
| 4025 | 98.4109
| 4026 | 95.6351
| 4027 | 88.9639
| 4028 | 119.2906
| 4029 | 106.9091
| 4030 | 159.8724
| 4031 | 80.965
| 4032 | 162.7074
| 4033 | 102.59
| 4034 | 160.1205
| 4035 | 156.8817
| 4036 | 163.7806
| 4037 | 148.7509
| 4038 | 125.142
| 4039 | 129.9245
| 4040 | 188.654
| 4041 | 134.2019
| 4042 | 152.3418
| 4043 | 97.0306
| 4044 | 160.8684
| 4045 | 136.0472
| 4046 | 99.3841
| 4047 | 95.5317
| 4048 | 82.9601
| 4049 | 130.4627
| 4050 | 150.1844
| 4051 | 115.4863
| 4052 | 100.7008
| 4053 | 104.1367
| 4054 | 140.314
| 4055 | 105.546
| 4056 | 121.8661
| 4057 | 119.8811
| 4058 | 169.3953
| 4059 | 157.9962
| 4060 | 145.622
| 4061 | 182.6393
| 4062 | 129.0235
| 4063 | 164.4568
| 4064 | 167.1343
| 4065 | 129.5174
| 4066 | 156.9606
| 4067 | 86.8144
| 4068 | 104.596
| 4069 | 201.229
| 4070 | 117.707
| 4071 | 183.5964
| 4072 | 162.1843
| 4073 | 141.1102
| 4074 | 125.9017
| 4075 | 89.5681
| 4076 | 194.5294
| 4077 | 192.7953
| 4078 | 142.4137
| 4079 | 121.3212
| 4080 | 127.1993
| 4081 | 90.9979
| 4082 | 112.0327
| 4083 | 162.0535
| 4084 | 154.2156
| 4085 | 120.9165
| 4086 | 136.3907
| 4087 | 78.2292
| 4088 | 160.056
| 4089 | 152.5278
| 4090 | 142.0534
| 4091 | 74.2764
| 4092 | 109.0147
| 4093 | 195.2446
| 4094 | 150.446
| 4095 | 109.8957
| 4096 | 86.6439
| 4097 | 135.9281
| 4098 | 109.5887
| 4099 | 116.438
| 4100 | 175.1043
| 4101 | 102.6171
| 4102 | 123.6177
| 4103 | 108.2208
| 4104 | 137.6525
| 4105 | 149.9677
| 4106 | 111.1256
| 4107 | 133.1961
| 4108 | 165.1049
| 4109 | 203.1671
| 4110 | 74.8703
| 4111 | 148.9458
| 4112 | 100.7411
| 4113 | 101.8515
| 4114 | 179.5789
| 4115 | 181.3182
| 4116 | 88.8884
| 4117 | 121.0464
| 4118 | 110.9094
| 4119 | 112.6983
| 4120 | 109.9412
| 4121 | 107.4053
| 4122 | 133.0669
| 4123 | 134.9755
| 4124 | 111.8427
| 4125 | 147.4154
| 4126 | 96.6956
| 4127 | 172.1089
| 4128 | 111.7173
| 4129 | 135.5376
| 4130 | 133.6604
| 4131 | 140.6287
| 4132 | 111.7346
| 4133 | 89.9103
| 4134 | 118.3605
| 4135 | 152.494
| 4136 | 130.2825
| 4137 | 129.7909
| 4138 | 111.0045
| 4139 | 119.5719
| 4140 | 106.7494
| 4141 | 138.9556
| 4142 | 128.5366
| 4143 | 138.9049
| 4144 | 94.6958
| 4145 | 130.4069
| 4146 | 160.1411
| 4147 | 136.229
| 4148 | 169.0725
| 4149 | 133.711
| 4150 | 99.2779
| 4151 | 170.7304
| 4152 | 151.14
| 4153 | 140.6542
| 4154 | 196.8959
| 4155 | 142.393
| 4156 | 89.1036
| 4157 | 85.7737
| 4158 | 79.7238
| 4159 | 165.4924
| 4160 | 151.4541
| 4161 | 149.6107
| 4162 | 116.3387
| 4163 | 92.5072
| 4164 | 115.0689
| 4165 | 127.9011
| 4166 | 83.772
| 4167 | 183.6231
| 4168 | 96.4206
| 4169 | 188.5799
| 4170 | 117.8041
| 4171 | 131.1309
| 4172 | 110.8334
| 4173 | 119.5648
| 4174 | 127.36
| 4175 | 76.3977
| 4176 | 119.1928
| 4177 | 85.29
| 4178 | 151.5451
| 4179 | 120.9007
| 4180 | 141.3602
| 4181 | 196.9871
| 4182 | 99.8533
| 4183 | 145.7512
| 4184 | 102.9204
| 4185 | 121.4147
| 4186 | 180.3331
| 4187 | 110.9636
| 4188 | 76.209
| 4189 | 99.0275
| 4190 | 124.275
| 4191 | 110.8303
| 4192 | 169.0165
| 4193 | 149.8978
| 4194 | 152.238
| 4195 | 111.2292
| 4196 | 102.5273
| 4197 | 175.2115
| 4198 | 156.1413
| 4199 | 131.7891
| 4200 | 166.0238
| 4201 | 81.3985
| 4202 | 134.6855
| 4203 | 174.3272
| 4204 | 130.4202
| 4205 | 167.2002
| 4206 | 103.8311
| 4207 | 106.7273
| 4208 | 142.0816
| 4209 | 121.0576
| 4210 | 163.2683
| 4211 | 97.4437
| 4212 | 99.1439
| 4213 | 83.2613
| 4214 | 182.0499
| 4215 | 115.6159
| 4216 | 102.1461
| 4217 | 190.1249
| 4218 | 128.177
| 4219 | 176.1678
| 4220 | 110.5845
| 4221 | 169.0788
| 4222 | 158.567
| 4223 | 108.0931
| 4224 | 121.3813
| 4225 | 102.1287
| 4226 | 159.2629
| 4227 | 158.9978
| 4228 | 87.9342
| 4229 | 177.0966
| 4230 | 203.4689
| 4231 | 125.3351
| 4232 | 93.8855
| 4233 | 113.3067
| 4234 | 90.1352
| 4235 | 88.7154
| 4236 | 131.8643
| 4237 | 91.7145
| 4238 | 129.5847
| 4239 | 134.7529
| 4240 | 170.1845
| 4241 | 91.7361
| 4242 | 120.5273
| 4243 | 93.9214
| 4244 | 88.9799
| 4245 | 132.0578
| 4246 | 132.0542
| 4247 | 138.6468
| 4248 | 101.8108
| 4249 | 135.793
| 4250 | 151.159
| 4251 | 167.2337
| 4252 | 133.3204
| 4253 | 118.1469
| 4254 | 131.3849
| 4255 | 145.5379
| 4256 | 80.9298
| 4257 | 114.0794
| 4258 | 165.4727
| 4259 | 77.7349
| 4260 | 147.1687
| 4261 | 91.0174
| 4262 | 141.5228
| 4263 | 105.855
| 4264 | 91.6486
| 4265 | 129.6191
| 4266 | 127.6844
| 4267 | 95.2899
| 4268 | 136.237
| 4269 | 133.0915
| 4270 | 163.7408
| 4271 | 124.2098
| 4272 | 99.1901
| 4273 | 110.0344
| 4274 | 145.6527
| 4275 | 81.1404
| 4276 | 80.5105
| 4277 | 179.267
| 4278 | 174.0511
| 4279 | 122.4797
| 4280 | 76.0885
| 4281 | 89.5522
| 4282 | 133.7361
| 4283 | 130.3101
| 4284 | 138.2394
| 4285 | 209.7096
| 4286 | 144.8798
| 4287 | 173.8423
| 4288 | 140.367
| 4289 | 151.9721
| 4290 | 75.2457
| 4291 | 143.4737
| 4292 | 106.8905
| 4293 | 69.2998
| 4294 | 118.1821
| 4295 | 182.5637
| 4296 | 71.0504
| 4297 | 100.9664
| 4298 | 135.2405
| 4299 | 119.922
| 4300 | 124.2388
| 4301 | 130.85
| 4302 | 115.7633
| 4303 | 103.055
| 4304 | 96.2674
| 4305 | 125.6654
| 4306 | 134.704
| 4307 | 209.5118
| 4308 | 129.2746
| 4309 | 147.7129
| 4310 | 146.9331
| 4311 | 98.6722
| 4312 | 128.2735
| 4313 | 128.5648
| 4314 | 99.327
| 4315 | 168.1447
| 4316 | 177.6177
| 4317 | 85.5586
| 4318 | 101.2308
| 4319 | 127.2194
| 4320 | 104.4012
| 4321 | 132.0961
| 4322 | 135.0377
| 4323 | 79.7617
| 4324 | 109.4302
| 4325 | 85.1238
| 4326 | 105.4087
| 4327 | 141.6665
| 4328 | 177.7747
| 4329 | 147.0521
| 4330 | 84.3953
| 4331 | 145.0676
| 4332 | 182.9491
| 4333 | 179.273
| 4334 | 150.3329
| 4335 | 128.1093
| 4336 | 146.7771
| 4337 | 125.6685
| 4338 | 128.5459
| 4339 | 164.4917
| 4340 | 67.2123
| 4341 | 110.6428
| 4342 | 86.4646
| 4343 | 125.2605
| 4344 | 120.2942
| 4345 | 148.2842
| 4346 | 118.6912
| 4347 | 91.8101
| 4348 | 128.0048
| 4349 | 143.7474
| 4350 | 83.6843
| 4351 | 144.1388
| 4352 | 144.6773
| 4353 | 151.4598
| 4354 | 132.6649
| 4355 | 180.8543
| 4356 | 166.4487
| 4357 | 88.5345
| 4358 | 149.3972
| 4359 | 140.8535
| 4360 | 133.7704
| 4361 | 147.5439
| 4362 | 118.5994
| 4363 | 155.718
| 4364 | 129.8706
| 4365 | 80.9666
| 4366 | 103.3802
| 4367 | 106.7902
| 4368 | 160.4537
| 4369 | 159.4083
| 4370 | 151.0156
| 4371 | 127.939
| 4372 | 94.7581
| 4373 | 136.3967
| 4374 | 108.2856
| 4375 | 122.6441
| 4376 | 131.9995
| 4377 | 115.1955
| 4378 | 137.8678
| 4379 | 160.8354
| 4380 | 148.0334
| 4381 | 111.6445
| 4382 | 106.131
| 4383 | 115.7523
| 4384 | 173.5727
| 4385 | 80.662
| 4386 | 87.9391
| 4387 | 130.4709
| 4388 | 136.0545
| 4389 | 131.7657
| 4390 | 110.1929
| 4391 | 126.4868
| 4392 | 207.2913
| 4393 | 135.5625
| 4394 | 107.868
| 4395 | 132.6512
| 4396 | 123.3288
| 4397 | 95.002
| 4398 | 86.1999
| 4399 | 112.7436
| 4400 | 109.2035
| 4401 | 104.358
| 4402 | 164.1628
| 4403 | 140.8979
| 4404 | 131.8324
| 4405 | 132.335
| 4406 | 88.9948
| 4407 | 171.2999
| 4408 | 135.6694
| 4409 | 166.2343
| 4410 | 103.8479
| 4411 | 138.485
| 4412 | 82.1398
| 4413 | 85.8557
| 4414 | 142.4389
| 4415 | 160.3173
| 4416 | 113.7026
| 4417 | 100.0533
| 4418 | 87.5668
| 4419 | 152.9168
| 4420 | 120.9465
| 4421 | 113.2545
| 4422 | 156.2154
| 4423 | 155.1889
| 4424 | 129.6731
| 4425 | 110.2391
| 4426 | 172.0389
| 4427 | 92.327
| 4428 | 89.3111
| 4429 | 158.7338
| 4430 | 190.3964
| 4431 | 165.8503
| 4432 | 114.6495
| 4433 | 117.915
| 4434 | 139.7327
| 4435 | 108.5661
| 4436 | 76.5014
| 4437 | 92.4354
| 4438 | 76.126
| 4439 | 134.4135
| 4440 | 120.7071
| 4441 | 127.2869
| 4442 | 173.4857
| 4443 | 81.8432
| 4444 | 86.5712
| 4445 | 155.3513
| 4446 | 138.4368
| 4447 | 178.2468
| 4448 | 83.157
| 4449 | 141.4394
| 4450 | 148.7783
| 4451 | 133.9492
| 4452 | 141.9707
| 4453 | 142.0132
| 4454 | 87.314
| 4455 | 124.2293
| 4456 | 207.007
| 4457 | 129.8607
| 4458 | 80.274
| 4459 | 107.5278
| 4460 | 142.4757
| 4461 | 77.5528
| 4462 | 89.3913
| 4463 | 159.7324
| 4464 | 96.2172
| 4465 | 177.1965
| 4466 | 150.8278
| 4467 | 141.7459
| 4468 | 65.7848
| 4469 | 106.7047
| 4470 | 88.2825
| 4471 | 183.4732
| 4472 | 150.5809
| 4473 | 73.5686
| 4474 | 214.6725
| 4475 | 148.2939
| 4476 | 127.2007
| 4477 | 183.2513
| 4478 | 147.1169
| 4479 | 84.7019
| 4480 | 122.9895
| 4481 | 111.4353
| 4482 | 99.8871
| 4483 | 108.2023
| 4484 | 134.8667
| 4485 | 115.9695
| 4486 | 113.0815
| 4487 | 155.3057
| 4488 | 124.2434
| 4489 | 160.7699
| 4490 | 134.3167
| 4491 | 147.0606
| 4492 | 75.5633
| 4493 | 94.6884
| 4494 | 115.4642
| 4495 | 191.2274
| 4496 | 97.191
| 4497 | 123.9587
| 4498 | 161.7922
| 4499 | 170.5983
| 4500 | 88.2249
| 4501 | 106.8124
| 4502 | 134.3447
| 4503 | 154.3098
| 4504 | 93.3379
| 4505 | 126.18
| 4506 | 158.0096
| 4507 | 109.2531
| 4508 | 177.7027
| 4509 | 129.1894
| 4510 | 148.1834
| 4511 | 94.7537
| 4512 | 149.556
| 4513 | 124.1591
| 4514 | 166.408
| 4515 | 190.1475
| 4516 | 122.3796
| 4517 | 161.9776
| 4518 | 64.3889
| 4519 | 179.6288
| 4520 | 143.612
| 4521 | 169.2127
| 4522 | 107.49
| 4523 | 126.575
| 4524 | 79.2343
| 4525 | 141.9242
| 4526 | 135.817
| 4527 | 89.3074
| 4528 | 148.6326
| 4529 | 113.6734
| 4530 | 86.3937
| 4531 | 166.3816
| 4532 | 90.006
| 4533 | 129.7118
| 4534 | 155.3207
| 4535 | 86.809
| 4536 | 140.2691
| 4537 | 82.775
| 4538 | 117.9789
| 4539 | 181.3762
| 4540 | 106.8501
| 4541 | 130.9629
| 4542 | 158.7374
| 4543 | 119.6627
| 4544 | 135.2491
| 4545 | 73.6033
| 4546 | 82.1489
| 4547 | 125.1316
| 4548 | 125.4343
| 4549 | 138.676
| 4550 | 120.4772
| 4551 | 163.5711
| 4552 | 154.0396
| 4553 | 188.9591
| 4554 | 174.085
| 4555 | 134.0013
| 4556 | 120.4318
| 4557 | 165.8497
| 4558 | 141.1872
| 4559 | 127.8609
| 4560 | 151.7625
| 4561 | 118.7904
| 4562 | 145.5304
| 4563 | 106.2549
| 4564 | 186.7196
| 4565 | 183.3564
| 4566 | 95.8266
| 4567 | 111.6862
| 4568 | 86.7893
| 4569 | 98.5064
| 4570 | 122.5615
| 4571 | 111.5037
| 4572 | 87.9653
| 4573 | 82.1156
| 4574 | 153.0514
| 4575 | 104.936
| 4576 | 95.3831
| 4577 | 130.1691
| 4578 | 119.9722
| 4579 | 158.4612
| 4580 | 147.6376
| 4581 | 152.1174
| 4582 | 113.7028
| 4583 | 119.3445
| 4584 | 138.9715
| 4585 | 108.2975
| 4586 | 160.2682
| 4587 | 75.6132
| 4588 | 109.3552
| 4589 | 162.6685
| 4590 | 145.559
| 4591 | 203.3762
| 4592 | 143.5496
| 4593 | 115.6467
| 4594 | 147.7273
| 4595 | 155.2256
| 4596 | 123.3531
| 4597 | 191.1804
| 4598 | 165.3942
| 4599 | 125.8601
| 4600 | 92.4818
| 4601 | 100.825
| 4602 | 101.0461
| 4603 | 182.8043
| 4604 | 139.3301
| 4605 | 163.1732
| 4606 | 110.0099
| 4607 | 133.081
| 4608 | 107.7876
| 4609 | 138.9819
| 4610 | 157.7219
| 4611 | 172.8052
| 4612 | 125.9533
| 4613 | 177.3883
| 4614 | 120.4026
| 4615 | 98.3423
| 4616 | 90.367
| 4617 | 91.8021
| 4618 | 156.3278
| 4619 | 89.4561
| 4620 | 121.3714
| 4621 | 142.5039
| 4622 | 110.9511
| 4623 | 98.1385
| 4624 | 191.8554
| 4625 | 98.1217
| 4626 | 88.4506
| 4627 | 101.6665
| 4628 | 158.11
| 4629 | 154.1424
| 4630 | 94.2365
| 4631 | 138.5223
| 4632 | 126.3047
| 4633 | 132.118
| 4634 | 180.8561
| 4635 | 176.0537
| 4636 | 133.9542
| 4637 | 105.6868
| 4638 | 131.1827
| 4639 | 112.0493
| 4640 | 145.0358
| 4641 | 151.6912
| 4642 | 91.9841
| 4643 | 151.2085
| 4644 | 143.4379
| 4645 | 115.6695
| 4646 | 196.2099
| 4647 | 130.046
| 4648 | 137.8324
| 4649 | 142.5738
| 4650 | 74.6737
| 4651 | 78.1137
| 4652 | 138.0828
| 4653 | 95.152
| 4654 | 100.9976
| 4655 | 134.5356
| 4656 | 174.0385
| 4657 | 135.0408
| 4658 | 130.9313
| 4659 | 142.9613
| 4660 | 179.1788
| 4661 | 121.8391
| 4662 | 116.5631
| 4663 | 133.1983
| 4664 | 175.0721
| 4665 | 171.1106
| 4666 | 157.0812
| 4667 | 111.3898
| 4668 | 139.5531
| 4669 | 132.7852
| 4670 | 127.0916
| 4671 | 172.6771
| 4672 | 114.9363
| 4673 | 130.767
| 4674 | 149.1738
| 4675 | 79.4882
| 4676 | 155.0001
| 4677 | 144.9432
| 4678 | 153.0209
| 4679 | 107.948
| 4680 | 128.3175
| 4681 | 120.0992
| 4682 | 151.7004
| 4683 | 134.5116
| 4684 | 165.9756
| 4685 | 80.8276
| 4686 | 167.5973
| 4687 | 95.1481
| 4688 | 196.7538
| 4689 | 189.301
| 4690 | 148.1005
| 4691 | 116.3908
| 4692 | 88.4446
| 4693 | 145.1375
| 4694 | 98.2759
| 4695 | 82.7939
| 4696 | 97.0382
| 4697 | 185.556
| 4698 | 96.3304
| 4699 | 146.0305
| 4700 | 167.1064
| 4701 | 139.8299
| 4702 | 140.3165
| 4703 | 147.9826
| 4704 | 97.8585
| 4705 | 167.8443
| 4706 | 101.6346
| 4707 | 76.1399
| 4708 | 165.5263
| 4709 | 120.0574
| 4710 | 136.0725
| 4711 | 123.3461
| 4712 | 132.1689
| 4713 | 162.4763
| 4714 | 135.5831
| 4715 | 135.4958
| 4716 | 133.7484
| 4717 | 113.0885
| 4718 | 143.6211
| 4719 | 129.7046
| 4720 | 135.1641
| 4721 | 89.3972
| 4722 | 132.0873
| 4723 | 115.2715
| 4724 | 94.7472
| 4725 | 142.6509
| 4726 | 134.3061
| 4727 | 123.2553
| 4728 | 141.4781
| 4729 | 203.527
| 4730 | 146.2645
| 4731 | 112.1325
| 4732 | 86.2136
| 4733 | 84.6117
| 4734 | 154.1661
| 4735 | 179.1476
| 4736 | 164.4344
| 4737 | 182.219
| 4738 | 178.9978
| 4739 | 127.4334
| 4740 | 144.3177
| 4741 | 102.2
| 4742 | 106.3975
| 4743 | 148.5197
| 4744 | 137.8699
| 4745 | 146.2986
| 4746 | 138.2058
| 4747 | 114.2504
| 4748 | 99.7403
| 4749 | 108.6201
| 4750 | 138.3953
| 4751 | 97.2728
| 4752 | 137.107
| 4753 | 94.197
| 4754 | 119.8337
| 4755 | 138.4843
| 4756 | 126.3375
| 4757 | 151.7443
| 4758 | 131.0475
| 4759 | 113.1355
| 4760 | 136.3276
| 4761 | 138.0887
| 4762 | 78.7853
| 4763 | 77.0446
| 4764 | 133.5841
| 4765 | 132.97
| 4766 | 159.364
| 4767 | 105.2423
| 4768 | 77.6073
| 4769 | 150.8712
| 4770 | 147.292
| 4771 | 125.9558
| 4772 | 92.9885
| 4773 | 112.1359
| 4774 | 96.0144
| 4775 | 104.6709
| 4776 | 157.7241
| 4777 | 132.431
| 4778 | 73.6968
| 4779 | 153.639
| 4780 | 177.1518
| 4781 | 133.2498
| 4782 | 102.6311
| 4783 | 177.0336
| 4784 | 148.4992
| 4785 | 79.939
| 4786 | 114.4586
| 4787 | 104.1217
| 4788 | 106.8387
| 4789 | 171.8421
| 4790 | 103.7333
| 4791 | 107.7889
| 4792 | 159.5883
| 4793 | 128.0551
| 4794 | 123.2595
| 4795 | 171.6006
| 4796 | 172.9981
| 4797 | 110.2342
| 4798 | 159.9487
| 4799 | 167.5415
| 4800 | 111.4053
| 4801 | 122.2394
| 4802 | 159.9247
| 4803 | 174.3807
| 4804 | 125.9512
| 4805 | 105.4174
| 4806 | 138.2301
| 4807 | 202.6805
| 4808 | 169.2682
| 4809 | 110.3927
| 4810 | 183.1643
| 4811 | 123.818
| 4812 | 157.3331
| 4813 | 103.051
| 4814 | 154.2076
| 4815 | 101.0315
| 4816 | 104.5775
| 4817 | 136.3349
| 4818 | 84.1056
| 4819 | 120.7319
| 4820 | 137.5508
| 4821 | 83.766
| 4822 | 90.4083
| 4823 | 141.1609
| 4824 | 175.6734
| 4825 | 87.0915
| 4826 | 119.7955
| 4827 | 114.6881
| 4828 | 98.5527
| 4829 | 97.0351
| 4830 | 88.8873
| 4831 | 111.6764
| 4832 | 177.8811
| 4833 | 105.7116
| 4834 | 88.2741
| 4835 | 141.4265
| 4836 | 109.1417
| 4837 | 162.9854
| 4838 | 79.8016
| 4839 | 95.6342
| 4840 | 125.8061
| 4841 | 66.5616
| 4842 | 100.6695
| 4843 | 95.0265
| 4844 | 84.5532
| 4845 | 97.8187
| 4846 | 159.8778
| 4847 | 159.4224
| 4848 | 110.5
| 4849 | 101.2376
| 4850 | 136.5194
| 4851 | 118.0751
| 4852 | 91.0938
| 4853 | 186.4801
| 4854 | 167.7354
| 4855 | 141.2823
| 4856 | 132.4869
| 4857 | 159.5645
| 4858 | 159.4756
| 4859 | 156.327
| 4860 | 128.6525
| 4861 | 130.8461
| 4862 | 98.8475
| 4863 | 106.4275
| 4864 | 130.375
| 4865 | 100.1908
| 4866 | 109.3552
| 4867 | 144.3803
| 4868 | 89.5664
| 4869 | 143.9509
| 4870 | 95.2678
| 4871 | 109.5133
| 4872 | 86.0913
| 4873 | 122.7334
| 4874 | 153.36
| 4875 | 187.0154
| 4876 | 156.4976
| 4877 | 113.1337
| 4878 | 103.6806
| 4879 | 161.5511
| 4880 | 120.5797
| 4881 | 135.5786
| 4882 | 110.5708
| 4883 | 92.1492
| 4884 | 169.4891
| 4885 | 134.3037
| 4886 | 198.1755
| 4887 | 80.2437
| 4888 | 120.7446
| 4889 | 156.6699
| 4890 | 63.7592
| 4891 | 161.9941
| 4892 | 84.1649
| 4893 | 106.8122
| 4894 | 139.3077
| 4895 | 192.9749
| 4896 | 113.6034
| 4897 | 139.6189
| 4898 | 179.0248
| 4899 | 131.7619
| 4900 | 110.8648
| 4901 | 98.4637
| 4902 | 134.4089
| 4903 | 131.437
| 4904 | 99.477
| 4905 | 88.7655
| 4906 | 132.3927
| 4907 | 108.7485
| 4908 | 89.6981
| 4909 | 102.0771
| 4910 | 155.4486
| 4911 | 151.8191
| 4912 | 174.8024
| 4913 | 183.1598
| 4914 | 120.2158
| 4915 | 117.3019
| 4916 | 139.0736
| 4917 | 154.1812
| 4918 | 134.9693
| 4919 | 89.3705
| 4920 | 185.2452
| 4921 | 159.1607
| 4922 | 135.9589
| 4923 | 148.5377
| 4924 | 151.0137
| 4925 | 78.8372
| 4926 | 156.076
| 4927 | 109.4156
| 4928 | 101.936
| 4929 | 117.2338
| 4930 | 134.2369
| 4931 | 168.9737
| 4932 | 119.525
| 4933 | 170.6731
| 4934 | 99.4051
| 4935 | 97.0881
| 4936 | 114.3572
| 4937 | 174.7104
| 4938 | 112.94
| 4939 | 142.5403
| 4940 | 163.995
| 4941 | 112.4345
| 4942 | 92.4749
| 4943 | 126.945
| 4944 | 195.86
| 4945 | 136.3799
| 4946 | 122
| 4947 | 119.3491
| 4948 | 126.0857
| 4949 | 196.9246
| 4950 | 114.2396
| 4951 | 102.7238
| 4952 | 111.7715
| 4953 | 70.2089
| 4954 | 175.2673
| 4955 | 90.3872
| 4956 | 76.3683
| 4957 | 107.4399
| 4958 | 146.8028
| 4959 | 113.4641
| 4960 | 120.6282
| 4961 | 106.8046
| 4962 | 87.3894
| 4963 | 147.8597
| 4964 | 98.7913
| 4965 | 109.5534
| 4966 | 175.5427
| 4967 | 103.5717
| 4968 | 153.0533
| 4969 | 115.5986
| 4970 | 107.2819
| 4971 | 90.5139
| 4972 | 129.5174
| 4973 | 112.3069
| 4974 | 105.613
| 4975 | 130.6046
| 4976 | 158.7881
| 4977 | 205.0014
| 4978 | 118.0285
| 4979 | 99.5607
| 4980 | 106.3274
| 4981 | 205.1985
| 4982 | 165.4785
| 4983 | 81.6427
| 4984 | 124.95
| 4985 | 97.2972
| 4986 | 128.5263
| 4987 | 79.0701
| 4988 | 167.8473
| 4989 | 160.7608
| 4990 | 124.9759
| 4991 | 146.3953
| 4992 | 144.1154
| 4993 | 100.469
| 4994 | 120.0147
| 4995 | 112.7538
| 4996 | 86.7099
| 4997 | 118.1316
| 4998 | 121.8133
| 4999 | 121.0403
| 5000 | 96.0636
| 5001 | 107.5428
| 5002 | 102.9703
| 5003 | 114.4411
| 5004 | 149.6228
| 5005 | 111.0868
| 5006 | 172.9427
| 5007 | 86.7042
| 5008 | 132.2677
| 5009 | 86.7344
| 5010 | 176.5093
| 5011 | 109.7923
| 5012 | 182.2043
| 5013 | 74.8279
| 5014 | 113.1648
| 5015 | 119.1089
| 5016 | 202.0708
| 5017 | 138.1825
| 5018 | 92.1308
| 5019 | 119.9665
| 5020 | 100.3648
| 5021 | 160.7541
| 5022 | 155.9103
| 5023 | 194.8091
| 5024 | 114.1372
| 5025 | 162.4384
| 5026 | 184.9972
| 5027 | 91.5911
| 5028 | 133.7288
| 5029 | 138.3498
| 5030 | 114.0769
| 5031 | 124.3644
| 5032 | 128.1173
| 5033 | 137.2387
| 5034 | 126.6447
| 5035 | 136.3016
| 5036 | 110.6211
| 5037 | 204.3146
| 5038 | 127.1313
| 5039 | 135.9039
| 5040 | 135.8624
| 5041 | 115.6403
| 5042 | 114.4288
| 5043 | 182.4216
| 5044 | 139.6722
| 5045 | 115.1625
| 5046 | 161.198
| 5047 | 94.9386
| 5048 | 148.7794
| 5049 | 99.8768
| 5050 | 103.4746
| 5051 | 149.6909
| 5052 | 129.8341
| 5053 | 151.9999
| 5054 | 153.9312
| 5055 | 135.8721
| 5056 | 122.8983
| 5057 | 117.9969
| 5058 | 129.895
| 5059 | 149.6744
| 5060 | 205.4974
| 5061 | 83.7385
| 5062 | 136.5248
| 5063 | 99.5748
| 5064 | 109.3436
| 5065 | 86.689
| 5066 | 83.4771
| 5067 | 98.8121
| 5068 | 171.4403
| 5069 | 171.7331
| 5070 | 120.0408
| 5071 | 97.2691
| 5072 | 105.6649
| 5073 | 125.5889
| 5074 | 137.1905
| 5075 | 79.7391
| 5076 | 87.1489
| 5077 | 189.3831
| 5078 | 127.9377
| 5079 | 106.4164
| 5080 | 105.1766
| 5081 | 130.0726
| 5082 | 73.8895
| 5083 | 186.4027
| 5084 | 144.6046
| 5085 | 110.7441
| 5086 | 122.0738
| 5087 | 131.9781
| 5088 | 102.9182
| 5089 | 173.0204
| 5090 | 123.4115
| 5091 | 113.1371
| 5092 | 91.3766
| 5093 | 118.063
| 5094 | 161.3188
| 5095 | 116.6848
| 5096 | 182.375
| 5097 | 89.3563
| 5098 | 115.7422
| 5099 | 154.7694
| 5100 | 147.7888
| 5101 | 76.7647
| 5102 | 94.8012
| 5103 | 96.1214
| 5104 | 137.3627
| 5105 | 123.2605
| 5106 | 117.7514
| 5107 | 99.0225
| 5108 | 103.0301
| 5109 | 163.4565
| 5110 | 160.8519
| 5111 | 183.2052
| 5112 | 87.3768
| 5113 | 108.3798
| 5114 | 151.6182
| 5115 | 133.5877
| 5116 | 135.5844
| 5117 | 137.7163
| 5118 | 169.4115
| 5119 | 115.1815
| 5120 | 166.8028
| 5121 | 84.8916
| 5122 | 107.4118
| 5123 | 150.9966
| 5124 | 121.2386
| 5125 | 129.9817
| 5126 | 110.1524
| 5127 | 138.1012
| 5128 | 100.3402
| 5129 | 154.2473
| 5130 | 133.8656
| 5131 | 103.2516
| 5132 | 138.444
| 5133 | 189.1848
| 5134 | 139.8477
| 5135 | 165.218
| 5136 | 115.3315
| 5137 | 145.0199
| 5138 | 183.1468
| 5139 | 139.971
| 5140 | 113.019
| 5141 | 126.8711
| 5142 | 107.1955
| 5143 | 136.6704
| 5144 | 136.8063
| 5145 | 128.3585
| 5146 | 124.6398
| 5147 | 141.8175
| 5148 | 119.8707
| 5149 | 186.5221
| 5150 | 141.8229
| 5151 | 138.2095
| 5152 | 169.7608
| 5153 | 104.2647
| 5154 | 142.4467
| 5155 | 108.8626
| 5156 | 133.2385
| 5157 | 88.3983
| 5158 | 115.3309
| 5159 | 92.7461
| 5160 | 153.5726
| 5161 | 142.4094
| 5162 | 176.5519
| 5163 | 125.692
| 5164 | 104.1497
| 5165 | 103.1315
| 5166 | 88.0888
| 5167 | 84.2405
| 5168 | 88.8851
| 5169 | 122.0163
| 5170 | 108.4369
| 5171 | 137.8981
| 5172 | 148.821
| 5173 | 116.1339
| 5174 | 91.9952
| 5175 | 109.8105
| 5176 | 132.5676
| 5177 | 142.4658
| 5178 | 116.8358
| 5179 | 117.5267
| 5180 | 176.6258
| 5181 | 94.2054
| 5182 | 99.3015
| 5183 | 151.6982
| 5184 | 116.1636
| 5185 | 144.4216
| 5186 | 114.6219
| 5187 | 129.82
| 5188 | 137.9982
| 5189 | 116.439
| 5190 | 148.8926
| 5191 | 132.9014
| 5192 | 141.44
| 5193 | 97.5754
| 5194 | 79.2523
| 5195 | 133.0488
| 5196 | 88.9486
| 5197 | 136.1486
| 5198 | 190.2554
| 5199 | 77.9219
| 5200 | 121.386
| 5201 | 157.0798
| 5202 | 84.9371
| 5203 | 151.2396
| 5204 | 136.6105
| 5205 | 128.6034
| 5206 | 76.1169
| 5207 | 94.4965
| 5208 | 127.6713
| 5209 | 88.6251
| 5210 | 154.0919
| 5211 | 126.3219
| 5212 | 158.2212
| 5213 | 158.6057
| 5214 | 188.6091
| 5215 | 151.6889
| 5216 | 143.0908
| 5217 | 113.8426
| 5218 | 165.811
| 5219 | 191.2046
| 5220 | 122.1404
| 5221 | 92.1228
| 5222 | 142.3563
| 5223 | 120.4751
| 5224 | 156.1333
| 5225 | 135.4082
| 5226 | 81.9489
| 5227 | 150.2199
| 5228 | 129.7816
| 5229 | 81.4494
| 5230 | 78.8728
| 5231 | 171.6091
| 5232 | 119.8006
| 5233 | 96.1873
| 5234 | 74.2902
| 5235 | 182.1195
| 5236 | 118.1188
| 5237 | 113.3867
| 5238 | 135.0806
| 5239 | 168.493
| 5240 | 96.6601
| 5241 | 136.5052
| 5242 | 109.2123
| 5243 | 125.7725
| 5244 | 112.19
| 5245 | 113.8794
| 5246 | 113.2305
| 5247 | 111.878
| 5248 | 134.8654
| 5249 | 113.1647
| 5250 | 106.5084
| 5251 | 128.2085
| 5252 | 97.3349
| 5253 | 124.5598
| 5254 | 110.2137
| 5255 | 111.9168
| 5256 | 99.4224
| 5257 | 105.7182
| 5258 | 159.1882
| 5259 | 119.1956
| 5260 | 87.3769
| 5261 | 120.6636
| 5262 | 180.1872
| 5263 | 141.2451
| 5264 | 79.7417
| 5265 | 127.2181
| 5266 | 206.5364
| 5267 | 108.1883
| 5268 | 184.3627
| 5269 | 185.5794
| 5270 | 169.5211
| 5271 | 153.6725
| 5272 | 106.9581
| 5273 | 116.1074
| 5274 | 201.2712
| 5275 | 145.632
| 5276 | 132.7732
| 5277 | 122.1462
| 5278 | 133.1371
| 5279 | 161.2557
| 5280 | 99.6049
| 5281 | 153.2205
| 5282 | 168.1137
| 5283 | 103.9493
| 5284 | 113.1182
| 5285 | 88.1224
| 5286 | 125.0234
| 5287 | 138.924
| 5288 | 189.7484
| 5289 | 143.6852
| 5290 | 134.5943
| 5291 | 187.2724
| 5292 | 139.5458
| 5293 | 207.4984
| 5294 | 124.7517
| 5295 | 189.0292
| 5296 | 111.4233
| 5297 | 99.5458
| 5298 | 139.4167
| 5299 | 135.8348
| 5300 | 99.2963
| 5301 | 174.5523
| 5302 | 85.1666
| 5303 | 164.3415
| 5304 | 71.8886
| 5305 | 133.8529
| 5306 | 145.0438
| 5307 | 80.6409
| 5308 | 160.9378
| 5309 | 102.5284
| 5310 | 190.2595
| 5311 | 128.273
| 5312 | 123.8704
| 5313 | 181.3415
| 5314 | 111.5396
| 5315 | 130.6574
| 5316 | 67.3519
| 5317 | 95.8756
| 5318 | 119.8842
| 5319 | 108.29
| 5320 | 115.5008
| 5321 | 180.4894
| 5322 | 79.1785
| 5323 | 132.773
| 5324 | 95.3432
| 5325 | 82.4966
| 5326 | 144.2814
| 5327 | 132.1791
| 5328 | 137.8174
| 5329 | 84.2667
| 5330 | 118.4886
| 5331 | 186.2487
| 5332 | 104.7571
| 5333 | 148.7574
| 5334 | 80.1874
| 5335 | 135.7693
| 5336 | 140.7871
| 5337 | 101.4836
| 5338 | 177.8893
| 5339 | 187.6684
| 5340 | 146.5895
| 5341 | 123.6032
| 5342 | 122.3031
| 5343 | 117.0962
| 5344 | 80.9427
| 5345 | 153.4676
| 5346 | 127.5266
| 5347 | 124.6407
| 5348 | 147.7079
| 5349 | 153.9657
| 5350 | 125.3346
| 5351 | 168.4433
| 5352 | 129.438
| 5353 | 157.2064
| 5354 | 157.0631
| 5355 | 163.3213
| 5356 | 176.4444
| 5357 | 98.1437
| 5358 | 97.1289
| 5359 | 110.3885
| 5360 | 151.4505
| 5361 | 127.9302
| 5362 | 88.2014
| 5363 | 133.1196
| 5364 | 166.4577
| 5365 | 96.6172
| 5366 | 163.8744
| 5367 | 117.9495
| 5368 | 148.769
| 5369 | 119.8227
| 5370 | 74.9574
| 5371 | 114.1512
| 5372 | 149.8966
| 5373 | 126.0186
| 5374 | 123.4022
| 5375 | 112.3267
| 5376 | 106.5337
| 5377 | 128.2569
| 5378 | 86.3655
| 5379 | 87.3098
| 5380 | 122.3
| 5381 | 170.2429
| 5382 | 195.161
| 5383 | 93.8317
| 5384 | 88.6261
| 5385 | 146.012
| 5386 | 142.3051
| 5387 | 157.4452
| 5388 | 140.301
| 5389 | 178.7767
| 5390 | 118.5489
| 5391 | 149.3566
| 5392 | 104.4507
| 5393 | 100.5094
| 5394 | 120.8934
| 5395 | 163.2318
| 5396 | 155.6763
| 5397 | 135.9129
| 5398 | 128.5801
| 5399 | 123.425
| 5400 | 130.9524
| 5401 | 115.743
| 5402 | 110.0262
| 5403 | 132.224
| 5404 | 120.6452
| 5405 | 145.0806
| 5406 | 139.8323
| 5407 | 118.5997
| 5408 | 73.1989
| 5409 | 91.1364
| 5410 | 138.2168
| 5411 | 140.7702
| 5412 | 167.6552
| 5413 | 128.9633
| 5414 | 114.5412
| 5415 | 147.4552
| 5416 | 150.1136
| 5417 | 193.8844
| 5418 | 69.5117
| 5419 | 156.1699
| 5420 | 94.55
| 5421 | 159.1771
| 5422 | 144.1309
| 5423 | 85.2686
| 5424 | 115.8343
| 5425 | 167.5673
| 5426 | 155.3769
| 5427 | 134.5359
| 5428 | 157.9305
| 5429 | 141.1836
| 5430 | 77.1865
| 5431 | 120.557
| 5432 | 160.3533
| 5433 | 112.2848
| 5434 | 147.1935
| 5435 | 127.9383
| 5436 | 79.7219
| 5437 | 100.6246
| 5438 | 102.2188
| 5439 | 186.5036
| 5440 | 123.4749
| 5441 | 100.2026
| 5442 | 170.3443
| 5443 | 107.3233
| 5444 | 97.7266
| 5445 | 180.753
| 5446 | 86.6666
| 5447 | 125.5885
| 5448 | 81.3119
| 5449 | 84.3608
| 5450 | 152.7492
| 5451 | 155.509
| 5452 | 107.0658
| 5453 | 109.7541
| 5454 | 135.1836
| 5455 | 141.8506
| 5456 | 186.9388
| 5457 | 118.6874
| 5458 | 156.5936
| 5459 | 112.2074
| 5460 | 128.2461
| 5461 | 131.5977
| 5462 | 131.6835
| 5463 | 158.0884
| 5464 | 140.8956
| 5465 | 165.8681
| 5466 | 85.7613
| 5467 | 123.5184
| 5468 | 93.1456
| 5469 | 183.8497
| 5470 | 141.6018
| 5471 | 87.801
| 5472 | 112.3918
| 5473 | 172.4763
| 5474 | 92.2139
| 5475 | 138.7859
| 5476 | 126.4073
| 5477 | 154.9929
| 5478 | 149.8919
| 5479 | 144.6654
| 5480 | 125.647
| 5481 | 160.9998
| 5482 | 165.7003
| 5483 | 155.2218
| 5484 | 138.5749
| 5485 | 107.2617
| 5486 | 160.3402
| 5487 | 182.7969
| 5488 | 83.131
| 5489 | 154.9894
| 5490 | 174.3776
| 5491 | 79.9003
| 5492 | 137.5783
| 5493 | 141.3659
| 5494 | 118.1375
| 5495 | 141.4228
| 5496 | 77.3538
| 5497 | 88.591
| 5498 | 106.4733
| 5499 | 151.1158
| 5500 | 90.4408
| 5501 | 135.2404
| 5502 | 151.0029
| 5503 | 152.8723
| 5504 | 176.9886
| 5505 | 169.3855
| 5506 | 93.6833
| 5507 | 105.1174
| 5508 | 125.1555
| 5509 | 198.2324
| 5510 | 193.3114
| 5511 | 93.4547
| 5512 | 160.6867
| 5513 | 111.1461
| 5514 | 193.4344
| 5515 | 93.8755
| 5516 | 87.5774
| 5517 | 116.6832
| 5518 | 144.2564
| 5519 | 139.2781
| 5520 | 131.6522
| 5521 | 101.0957
| 5522 | 126.5661
| 5523 | 153.4258
| 5524 | 157.904
| 5525 | 128.1459
| 5526 | 155.4906
| 5527 | 149.0544
| 5528 | 121.1443
| 5529 | 150.6841
| 5530 | 103.3188
| 5531 | 71.6329
| 5532 | 122.8654
| 5533 | 105.2072
| 5534 | 190.0507
| 5535 | 116.586
| 5536 | 132.6604
| 5537 | 114.9946
| 5538 | 195.3046
| 5539 | 138.7143
| 5540 | 113.9246
| 5541 | 114.3485
| 5542 | 87.816
| 5543 | 127.1924
| 5544 | 105.6408
| 5545 | 163.2606
| 5546 | 189.3081
| 5547 | 166.7237
| 5548 | 156.8003
| 5549 | 127.1588
| 5550 | 108.6242
| 5551 | 138.5168
| 5552 | 185.6618
| 5553 | 154.0717
| 5554 | 100.0791
| 5555 | 72.9713
| 5556 | 144.0204
| 5557 | 184.0973
| 5558 | 182.5788
| 5559 | 107.3261
| 5560 | 94.6938
| 5561 | 132.3296
| 5562 | 87.3033
| 5563 | 103.3917
| 5564 | 164.3112
| 5565 | 149.6129
| 5566 | 116.3693
| 5567 | 102.8137
| 5568 | 104.8942
| 5569 | 155.5216
| 5570 | 176.2403
| 5571 | 168.4651
| 5572 | 171.1371
| 5573 | 154.4949
| 5574 | 144.8476
| 5575 | 150.8119
| 5576 | 155.2643
| 5577 | 88.0834
| 5578 | 137.0357
| 5579 | 125.1111
| 5580 | 94.0778
| 5581 | 112.8581
| 5582 | 211.1447
| 5583 | 129.2808
| 5584 | 174.597
| 5585 | 164.4248
| 5586 | 123.8758
| 5587 | 109.3722
| 5588 | 107.142
| 5589 | 119.9931
| 5590 | 112.6778
| 5591 | 113.6031
| 5592 | 130.5739
| 5593 | 73.9011
| 5594 | 130.3806
| 5595 | 104.1357
| 5596 | 143.5021
| 5597 | 101.3423
| 5598 | 114.8843
| 5599 | 147.5228
| 5600 | 127.7602
| 5601 | 118.7834
| 5602 | 141.8965
| 5603 | 137.7411
| 5604 | 161.1018
| 5605 | 75.6347
| 5606 | 134.2158
| 5607 | 120.4306
| 5608 | 141.5329
| 5609 | 117.3701
| 5610 | 135.8295
| 5611 | 106.2732
| 5612 | 70.6427
| 5613 | 104.4491
| 5614 | 112.2127
| 5615 | 135.7438
| 5616 | 130.4968
| 5617 | 144.1316
| 5618 | 153.5705
| 5619 | 153.9716
| 5620 | 179.2301
| 5621 | 188.3589
| 5622 | 117.0869
| 5623 | 124.3901
| 5624 | 150.3244
| 5625 | 83.7916
| 5626 | 79.8878
| 5627 | 171.2534
| 5628 | 88.1527
| 5629 | 188.6814
| 5630 | 157.5959
| 5631 | 148.0212
| 5632 | 81.0292
| 5633 | 148.0384
| 5634 | 146.5165
| 5635 | 71.5373
| 5636 | 121.3842
| 5637 | 149.774
| 5638 | 93.3562
| 5639 | 168.114
| 5640 | 141.2384
| 5641 | 110.265
| 5642 | 138.137
| 5643 | 188.7483
| 5644 | 91.2067
| 5645 | 158.6347
| 5646 | 171.1663
| 5647 | 151.7443
| 5648 | 122.7374
| 5649 | 92.5605
| 5650 | 86.5517
| 5651 | 117.0281
| 5652 | 116.483
| 5653 | 166.2407
| 5654 | 211.1091
| 5655 | 181.2987
| 5656 | 123.2866
| 5657 | 107.2969
| 5658 | 157.3362
| 5659 | 73.362
| 5660 | 180.5288
| 5661 | 149.4642
| 5662 | 150.4911
| 5663 | 77.2435
| 5664 | 86.8948
| 5665 | 143.9945
| 5666 | 156.735
| 5667 | 76.3526
| 5668 | 67.4461
| 5669 | 149.1571
| 5670 | 98.0742
| 5671 | 148.6652
| 5672 | 184.1006
| 5673 | 91.4269
| 5674 | 66.9631
| 5675 | 124.9993
| 5676 | 187.0975
| 5677 | 132.1164
| 5678 | 141.0388
| 5679 | 72.3382
| 5680 | 101.2754
| 5681 | 142.6871
| 5682 | 94.6693
| 5683 | 82.226
| 5684 | 168.4602
| 5685 | 121.9061
| 5686 | 87.2691
| 5687 | 135.4627
| 5688 | 138.4014
| 5689 | 114.0021
| 5690 | 132.9305
| 5691 | 116.9672
| 5692 | 111.1803
| 5693 | 98.4515
| 5694 | 129.0032
| 5695 | 110.2968
| 5696 | 171.4043
| 5697 | 128.789
| 5698 | 183.568
| 5699 | 144.6447
| 5700 | 189.1657
| 5701 | 203.9032
| 5702 | 117.9267
| 5703 | 70.7983
| 5704 | 132.2234
| 5705 | 113.8259
| 5706 | 163.0014
| 5707 | 118.0121
| 5708 | 173.1437
| 5709 | 168.4425
| 5710 | 115.7941
| 5711 | 123.3966
| 5712 | 138.488
| 5713 | 134.0792
| 5714 | 82.2248
| 5715 | 107.8357
| 5716 | 94.9386
| 5717 | 147.1414
| 5718 | 86.9613
| 5719 | 153.6972
| 5720 | 124.1517
| 5721 | 109.1535
| 5722 | 118.8087
| 5723 | 91.6938
| 5724 | 174.1327
| 5725 | 89.1201
| 5726 | 84.2456
| 5727 | 86.6196
| 5728 | 100.1849
| 5729 | 134.3222
| 5730 | 94.333
| 5731 | 141.6511
| 5732 | 176.02
| 5733 | 119.3325
| 5734 | 74.9873
| 5735 | 81.2634
| 5736 | 160.2696
| 5737 | 195.1402
| 5738 | 107.2314
| 5739 | 138.6595
| 5740 | 108.0511
| 5741 | 104.7659
| 5742 | 103.8638
| 5743 | 166.1114
| 5744 | 92.1132
| 5745 | 133.9015
| 5746 | 150.4758
| 5747 | 149.1303
| 5748 | 140.0538
| 5749 | 131.4502
| 5750 | 107.3185
| 5751 | 116.4242
| 5752 | 80.8837
| 5753 | 114.2839
| 5754 | 124.3666
| 5755 | 122.7517
| 5756 | 159.91
| 5757 | 104.07
| 5758 | 110.4305
| 5759 | 150.6789
| 5760 | 128.4274
| 5761 | 165.781
| 5762 | 116.4083
| 5763 | 110.4241
| 5764 | 136.3811
| 5765 | 205.0432
| 5766 | 170.3465
| 5767 | 101.8276
| 5768 | 71.912
| 5769 | 125.7105
| 5770 | 121.3825
| 5771 | 106.1404
| 5772 | 145.0259
| 5773 | 139.6656
| 5774 | 91.4661
| 5775 | 145.4082
| 5776 | 153.489
| 5777 | 142.3021
| 5778 | 90.2813
| 5779 | 113.5234
| 5780 | 140.4379
| 5781 | 84.0145
| 5782 | 137.5915
| 5783 | 177.7971
| 5784 | 85.5824
| 5785 | 142.1875
| 5786 | 137.9597
| 5787 | 85.337
| 5788 | 77.9723
| 5789 | 123.1585
| 5790 | 72.4249
| 5791 | 126.1443
| 5792 | 82.7227
| 5793 | 84.9606
| 5794 | 143.0673
| 5795 | 165.925
| 5796 | 97.3285
| 5797 | 185.9158
| 5798 | 151.5562
| 5799 | 201.9065
| 5800 | 190.6942
| 5801 | 114.3833
| 5802 | 105.8432
| 5803 | 167.4627
| 5804 | 140.6758
| 5805 | 102.4005
| 5806 | 77.7376
| 5807 | 80.1129
| 5808 | 125.7088
| 5809 | 105.0241
| 5810 | 162.1276
| 5811 | 99.1408
| 5812 | 84.0519
| 5813 | 138.9956
| 5814 | 139.4383
| 5815 | 97.6216
| 5816 | 145.5099
| 5817 | 133.7933
| 5818 | 100.6075
| 5819 | 150.5714
| 5820 | 138.529
| 5821 | 151.7698
| 5822 | 125.2873
| 5823 | 190.7772
| 5824 | 155.2201
| 5825 | 97.0148
| 5826 | 119.8297
| 5827 | 92.085
| 5828 | 144.9174
| 5829 | 127.772
| 5830 | 186.3134
| 5831 | 97.4056
| 5832 | 183.8115
| 5833 | 103.4818
| 5834 | 102.7916
| 5835 | 180.5955
| 5836 | 99.6587
| 5837 | 162.8276
| 5838 | 134.2357
| 5839 | 107.9045
| 5840 | 182.1361
| 5841 | 97.2299
| 5842 | 124.4402
| 5843 | 158.8066
| 5844 | 151.2078
| 5845 | 147.4311
| 5846 | 113.4959
| 5847 | 118.2793
| 5848 | 122.305
| 5849 | 134.6884
| 5850 | 113.5853
| 5851 | 159.5993
| 5852 | 108.3712
| 5853 | 116.4031
| 5854 | 113.1886
| 5855 | 117.2318
| 5856 | 150.9302
| 5857 | 97.4104
| 5858 | 177.7529
| 5859 | 108.208
| 5860 | 194.6142
| 5861 | 131.0823
| 5862 | 105.5238
| 5863 | 114.2558
| 5864 | 195.9665
| 5865 | 123.5021
| 5866 | 163.1326
| 5867 | 144.703
| 5868 | 168.8207
| 5869 | 115.2098
| 5870 | 100.3309
| 5871 | 104.5112
| 5872 | 119.234
| 5873 | 130.5584
| 5874 | 139.3102
| 5875 | 162.9393
| 5876 | 155.0952
| 5877 | 127.2344
| 5878 | 160.9401
| 5879 | 118.3214
| 5880 | 73.0725
| 5881 | 132.36
| 5882 | 64.4594
| 5883 | 147.4194
| 5884 | 123.8299
| 5885 | 120.4783
| 5886 | 92.0076
| 5887 | 128.6568
| 5888 | 214.8269
| 5889 | 137.8723
| 5890 | 125.8061
| 5891 | 176.1356
| 5892 | 150.2663
| 5893 | 156.669
| 5894 | 72.5251
| 5895 | 143.9264
| 5896 | 75.2403
| 5897 | 152.8082
| 5898 | 98.7679
| 5899 | 153.6033
| 5900 | 86.5444
| 5901 | 119.309
| 5902 | 146.0037
| 5903 | 161.5557
| 5904 | 134.3518
| 5905 | 109.838
| 5906 | 70.8759
| 5907 | 107.8615
| 5908 | 185.5055
| 5909 | 95.209
| 5910 | 110.5347
| 5911 | 82.329
| 5912 | 106.6125
| 5913 | 92.9491
| 5914 | 116.6352
| 5915 | 117.6906
| 5916 | 146.2222
| 5917 | 147.7642
| 5918 | 129.3373
| 5919 | 119.9599
| 5920 | 123.0655
| 5921 | 158.2774
| 5922 | 182.6902
| 5923 | 122.0536
| 5924 | 133.3822
| 5925 | 122.5112
| 5926 | 160.8255
| 5927 | 157.0295
| 5928 | 103.5036
| 5929 | 86.15
| 5930 | 169.8654
| 5931 | 133.6401
| 5932 | 106.4314
| 5933 | 135.3211
| 5934 | 86.0999
| 5935 | 135.9985
| 5936 | 77.1575
| 5937 | 176.9317
| 5938 | 149.5918
| 5939 | 132.754
| 5940 | 130.0091
| 5941 | 163.0972
| 5942 | 170.9974
| 5943 | 137.7816
| 5944 | 100.7189
| 5945 | 137.3521
| 5946 | 114.7345
| 5947 | 94.7157
| 5948 | 121.0023
| 5949 | 137.2859
| 5950 | 141.8568
| 5951 | 184.9715
| 5952 | 71.7048
| 5953 | 120.8173
| 5954 | 142.315
| 5955 | 211.9638
| 5956 | 108.3315
| 5957 | 123.3576
| 5958 | 182.1689
| 5959 | 142.1936
| 5960 | 161.1177
| 5961 | 159.6819
| 5962 | 123.8513
| 5963 | 74.6569
| 5964 | 167.3447
| 5965 | 201.1882
| 5966 | 143.7527
| 5967 | 129.1601
| 5968 | 168.6198
| 5969 | 101.3816
| 5970 | 152.7008
| 5971 | 104.7879
| 5972 | 95.6818
| 5973 | 132.9871
| 5974 | 122.9266
| 5975 | 154.7621
| 5976 | 177.3619
| 5977 | 137.2654
| 5978 | 161.9466
| 5979 | 96.5007
| 5980 | 121.1869
| 5981 | 96.8346
| 5982 | 113.3639
| 5983 | 122.8068
| 5984 | 182.9655
| 5985 | 78.7434
| 5986 | 106.8746
| 5987 | 154.7333
| 5988 | 127.4902
| 5989 | 113.8084
| 5990 | 121.9023
| 5991 | 101.1733
| 5992 | 75.5693
| 5993 | 104.0314
| 5994 | 152.1453
| 5995 | 122.5103
| 5996 | 90.872
| 5997 | 105.6149
| 5998 | 164.2799
| 5999 | 111.746
| 6000 | 125.4748
| 6001 | 106.8617
| 6002 | 88.1353
| 6003 | 185.4743
| 6004 | 117.5731
| 6005 | 77.8812
| 6006 | 113.1947
| 6007 | 122.5286
| 6008 | 72.5486
| 6009 | 125.4044
| 6010 | 170.4653
| 6011 | 107.7754
| 6012 | 141.3234
| 6013 | 195.1718
| 6014 | 131.1042
| 6015 | 224.5448
| 6016 | 86.9775
| 6017 | 183.3522
| 6018 | 163.7094
| 6019 | 142.4978
| 6020 | 104.5008
| 6021 | 120.5558
| 6022 | 165.4845
| 6023 | 121.9417
| 6024 | 130.5918
| 6025 | 137.5445
| 6026 | 217.5199
| 6027 | 79.9436
| 6028 | 119.6488
| 6029 | 111.6696
| 6030 | 112.8035
| 6031 | 117.4043
| 6032 | 185.3102
| 6033 | 204.5603
| 6034 | 206.6486
| 6035 | 168.9964
| 6036 | 121.314
| 6037 | 117.5706
| 6038 | 166.288
| 6039 | 140.183
| 6040 | 149.0292
| 6041 | 175.071
| 6042 | 127.9101
| 6043 | 172.9624
| 6044 | 137.315
| 6045 | 76.959
| 6046 | 120.9328
| 6047 | 99.6635
| 6048 | 139.6634
| 6049 | 148.7282
| 6050 | 143.0896
| 6051 | 118.8247
| 6052 | 66.379
| 6053 | 121.9325
| 6054 | 149.5769
| 6055 | 142.7618
| 6056 | 90.3837
| 6057 | 125.693
| 6058 | 88.2277
| 6059 | 99.7926
| 6060 | 91.7483
| 6061 | 118.1806
| 6062 | 107.2695
| 6063 | 172.4798
| 6064 | 121.2041
| 6065 | 131.2252
| 6066 | 101.9608
| 6067 | 107.1844
| 6068 | 81.7189
| 6069 | 130.2463
| 6070 | 116.9494
| 6071 | 200.2471
| 6072 | 174.128
| 6073 | 171.3726
| 6074 | 137.9866
| 6075 | 76.7884
| 6076 | 139.8731
| 6077 | 122.7521
| 6078 | 128.386
| 6079 | 117.9819
| 6080 | 153.7052
| 6081 | 121.7025
| 6082 | 117.8406
| 6083 | 108.261
| 6084 | 110.1543
| 6085 | 126.9292
| 6086 | 96.1692
| 6087 | 169.813
| 6088 | 93.1002
| 6089 | 133.496
| 6090 | 139.2465
| 6091 | 145.6712
| 6092 | 110.7012
| 6093 | 188.3676
| 6094 | 163.9997
| 6095 | 107.5021
| 6096 | 143.0158
| 6097 | 76.5933
| 6098 | 80.5417
| 6099 | 131.7492
| 6100 | 90.9581
| 6101 | 129.0662
| 6102 | 136.1318
| 6103 | 186.5752
| 6104 | 185.9109
| 6105 | 140.7761
| 6106 | 182.2871
| 6107 | 87.8872
| 6108 | 183.2568
| 6109 | 99.0264
| 6110 | 129.2585
| 6111 | 125.5146
| 6112 | 133.4237
| 6113 | 154.7586
| 6114 | 131.4274
| 6115 | 131.355
| 6116 | 183.3886
| 6117 | 119.617
| 6118 | 68.9551
| 6119 | 194.7759
| 6120 | 96.7459
| 6121 | 106.0794
| 6122 | 123.9473
| 6123 | 122.3971
| 6124 | 105.8732
| 6125 | 130.7404
| 6126 | 112.3124
| 6127 | 116.2876
| 6128 | 129.2048
| 6129 | 131.464
| 6130 | 128.72
| 6131 | 121.4425
| 6132 | 97.5906
| 6133 | 172.8345
| 6134 | 94.3455
| 6135 | 140.1421
| 6136 | 102.4503
| 6137 | 93.0876
| 6138 | 138.9376
| 6139 | 121.9846
| 6140 | 163.1241
| 6141 | 143.1377
| 6142 | 108.077
| 6143 | 126.787
| 6144 | 130.6684
| 6145 | 138.5228
| 6146 | 106.03
| 6147 | 70.3404
| 6148 | 141.6473
| 6149 | 187.72
| 6150 | 117.7015
| 6151 | 178.5155
| 6152 | 94.7764
| 6153 | 82.6599
| 6154 | 118.0049
| 6155 | 181.6128
| 6156 | 99.1652
| 6157 | 98.4642
| 6158 | 148.6262
| 6159 | 91.2939
| 6160 | 136.0657
| 6161 | 173.0251
| 6162 | 120.9292
| 6163 | 135.5871
| 6164 | 136.8123
| 6165 | 185.1032
| 6166 | 194.9873
| 6167 | 96.8803
| 6168 | 100.1709
| 6169 | 148.192
| 6170 | 118.2085
| 6171 | 154.756
| 6172 | 83.7753
| 6173 | 96.1346
| 6174 | 94.6622
| 6175 | 140.9767
| 6176 | 70.3162
| 6177 | 69.935
| 6178 | 190.2333
| 6179 | 132.0899
| 6180 | 82.3702
| 6181 | 103.2545
| 6182 | 141.7427
| 6183 | 88.4168
| 6184 | 164.7168
| 6185 | 144.8439
| 6186 | 139.5233
| 6187 | 137.5911
| 6188 | 138.1089
| 6189 | 97.8281
| 6190 | 85.7495
| 6191 | 112.4168
| 6192 | 162.8358
| 6193 | 130.1646
| 6194 | 144.6109
| 6195 | 87.5433
| 6196 | 143.7671
| 6197 | 105.9696
| 6198 | 128.2138
| 6199 | 157.0294
| 6200 | 183.0515
| 6201 | 113.7052
| 6202 | 152.2189
| 6203 | 105.4921
| 6204 | 83.2752
| 6205 | 156.2976
| 6206 | 98.8786
| 6207 | 126.665
| 6208 | 139.8922
| 6209 | 139.1852
| 6210 | 86.31
| 6211 | 128.4842
| 6212 | 87.2556
| 6213 | 144.2856
| 6214 | 137.1595
| 6215 | 121.4034
| 6216 | 146.2913
| 6217 | 85.9006
| 6218 | 156.2485
| 6219 | 135.0392
| 6220 | 128.8025
| 6221 | 155.7906
| 6222 | 169.4697
| 6223 | 179.2174
| 6224 | 112.0994
| 6225 | 192.2353
| 6226 | 156.8611
| 6227 | 123.0558
| 6228 | 79.2998
| 6229 | 115.3332
| 6230 | 94.2943
| 6231 | 171.4802
| 6232 | 209.6427
| 6233 | 197.5602
| 6234 | 82.5135
| 6235 | 84.0422
| 6236 | 114.5201
| 6237 | 147.1293
| 6238 | 132.3893
| 6239 | 151.4186
| 6240 | 151.8362
| 6241 | 114.3512
| 6242 | 122.7128
| 6243 | 110.5991
| 6244 | 113.3952
| 6245 | 145.8076
| 6246 | 123.2918
| 6247 | 112.983
| 6248 | 111.4125
| 6249 | 96.4838
| 6250 | 165.7805
| 6251 | 66.754
| 6252 | 127.9444
| 6253 | 168.7187
| 6254 | 114.1758
| 6255 | 138.0459
| 6256 | 171.5351
| 6257 | 87.3002
| 6258 | 206.968
| 6259 | 166.3828
| 6260 | 164.2185
| 6261 | 118.3137
| 6262 | 103.2202
| 6263 | 126.1868
| 6264 | 149.5251
| 6265 | 151.6554
| 6266 | 106.2834
| 6267 | 140.8661
| 6268 | 124.63
| 6269 | 93.3735
| 6270 | 153.6487
| 6271 | 112.5285
| 6272 | 92.1245
| 6273 | 165.4404
| 6274 | 106.2393
| 6275 | 107.595
| 6276 | 149.0767
| 6277 | 107.3732
| 6278 | 87.2897
| 6279 | 93.7574
| 6280 | 138.6885
| 6281 | 130.9343
| 6282 | 102.9128
| 6283 | 86.4925
| 6284 | 128.4936
| 6285 | 128.8898
| 6286 | 67.0114
| 6287 | 125.0977
| 6288 | 171.5436
| 6289 | 115.0236
| 6290 | 96.3834
| 6291 | 196.5871
| 6292 | 153.1217
| 6293 | 145.0822
| 6294 | 200.2151
| 6295 | 144.7015
| 6296 | 123.8461
| 6297 | 199.9309
| 6298 | 142.563
| 6299 | 164.4753
| 6300 | 174.0792
| 6301 | 153.6571
| 6302 | 101.8691
| 6303 | 114.6451
| 6304 | 172.5402
| 6305 | 141.7834
| 6306 | 159.5106
| 6307 | 100.0841
| 6308 | 127.6874
| 6309 | 100.1842
| 6310 | 99.7742
| 6311 | 160.4122
| 6312 | 174.4618
| 6313 | 107.5548
| 6314 | 102.4945
| 6315 | 115.0915
| 6316 | 127.1733
| 6317 | 79.7181
| 6318 | 148.1871
| 6319 | 148.0423
| 6320 | 146.3797
| 6321 | 133.4835
| 6322 | 77.0878
| 6323 | 77.1149
| 6324 | 92.3338
| 6325 | 184.4485
| 6326 | 82.9202
| 6327 | 87.3867
| 6328 | 124.4242
| 6329 | 108.4762
| 6330 | 113.4892
| 6331 | 86.2812
| 6332 | 175.4037
| 6333 | 152.9308
| 6334 | 130.2673
| 6335 | 104.5227
| 6336 | 112.8184
| 6337 | 138.075
| 6338 | 112.9146
| 6339 | 130.1676
| 6340 | 96.7682
| 6341 | 87.4805
| 6342 | 134.4496
| 6343 | 86.1532
| 6344 | 83.897
| 6345 | 116.7462
| 6346 | 104.2579
| 6347 | 147.451
| 6348 | 113.0484
| 6349 | 74.7042
| 6350 | 126.669
| 6351 | 125.6827
| 6352 | 119.8528
| 6353 | 107.2412
| 6354 | 115.8657
| 6355 | 68.2324
| 6356 | 135.5004
| 6357 | 109.0684
| 6358 | 148.3797
| 6359 | 80.1015
| 6360 | 91.6593
| 6361 | 172.0397
| 6362 | 95.4266
| 6363 | 142.1069
| 6364 | 142.9356
| 6365 | 178.2845
| 6366 | 156.6442
| 6367 | 98.0835
| 6368 | 167.3835
| 6369 | 124.1384
| 6370 | 101.1045
| 6371 | 158.2186
| 6372 | 154.759
| 6373 | 132.5139
| 6374 | 129.0058
| 6375 | 124.3927
| 6376 | 100.8455
| 6377 | 69.3067
| 6378 | 169.2226
| 6379 | 145.4622
| 6380 | 169.3616
| 6381 | 103.5564
| 6382 | 142.6291
| 6383 | 87.3707
| 6384 | 104.9231
| 6385 | 146.3669
| 6386 | 112.2912
| 6387 | 108.0155
| 6388 | 175.0361
| 6389 | 169.6688
| 6390 | 142.6027
| 6391 | 107.0429
| 6392 | 174.0652
| 6393 | 138.5642
| 6394 | 181.6615
| 6395 | 140.165
| 6396 | 86.1066
| 6397 | 151.2868
| 6398 | 86.5612
| 6399 | 93.1942
| 6400 | 90.1149
| 6401 | 109.6905
| 6402 | 109.7729
| 6403 | 105.5032
| 6404 | 118.3906
| 6405 | 101.8116
| 6406 | 113.6329
| 6407 | 73.2795
| 6408 | 135.7327
| 6409 | 93.1664
| 6410 | 77.6692
| 6411 | 163.9699
| 6412 | 126.2203
| 6413 | 137.1374
| 6414 | 197.4187
| 6415 | 95.1078
| 6416 | 70.8738
| 6417 | 139.8194
| 6418 | 112.8302
| 6419 | 142.3457
| 6420 | 133.4095
| 6421 | 192.4268
| 6422 | 113.0821
| 6423 | 121.3364
| 6424 | 95.8535
| 6425 | 97.6281
| 6426 | 92.9191
| 6427 | 133.6494
| 6428 | 130.1454
| 6429 | 129.5932
| 6430 | 88.5868
| 6431 | 149.4312
| 6432 | 170.0699
| 6433 | 175.5499
| 6434 | 139.0441
| 6435 | 101.8336
| 6436 | 161.1415
| 6437 | 169.5261
| 6438 | 147.7921
| 6439 | 127.2227
| 6440 | 101.2379
| 6441 | 93.4628
| 6442 | 117.9582
| 6443 | 152.4157
| 6444 | 118.1703
| 6445 | 108.582
| 6446 | 82.5412
| 6447 | 100.8186
| 6448 | 172.9822
| 6449 | 108.7384
| 6450 | 185.7317
| 6451 | 94.5142
| 6452 | 112.6578
| 6453 | 119.755
| 6454 | 94.7835
| 6455 | 163.7296
| 6456 | 160.5674
| 6457 | 149.1948
| 6458 | 147.7679
| 6459 | 125.7355
| 6460 | 138.8059
| 6461 | 106.8614
| 6462 | 158.0131
| 6463 | 111.1052
| 6464 | 125.1367
| 6465 | 120.078
| 6466 | 159.0682
| 6467 | 105.2997
| 6468 | 80.7903
| 6469 | 106.5343
| 6470 | 153.2202
| 6471 | 152.4527
| 6472 | 161.1979
| 6473 | 118.1948
| 6474 | 144.9676
| 6475 | 172.8652
| 6476 | 152.0386
| 6477 | 118.252
| 6478 | 73.9932
| 6479 | 84.2803
| 6480 | 173.354
| 6481 | 173.2029
| 6482 | 131.5633
| 6483 | 93.1162
| 6484 | 76.8556
| 6485 | 115.7296
| 6486 | 140.1848
| 6487 | 161.0102
| 6488 | 105.8386
| 6489 | 155.2015
| 6490 | 113.0769
| 6491 | 168.818
| 6492 | 121.4628
| 6493 | 179.5242
| 6494 | 168.2819
| 6495 | 145.1174
| 6496 | 95.2174
| 6497 | 140.0075
| 6498 | 123.4969
| 6499 | 112.1959
| 6500 | 82.5084
| 6501 | 105.8916
| 6502 | 79.4455
| 6503 | 116.2033
| 6504 | 128.6437
| 6505 | 136.6278
| 6506 | 131.4685
| 6507 | 156.3566
| 6508 | 157.4566
| 6509 | 120.2947
| 6510 | 157.2821
| 6511 | 107.3175
| 6512 | 144.4688
| 6513 | 97.6834
| 6514 | 99.0019
| 6515 | 110.3279
| 6516 | 148.6377
| 6517 | 106.4418
| 6518 | 81.785
| 6519 | 172.584
| 6520 | 183.4179
| 6521 | 106.586
| 6522 | 112.4335
| 6523 | 119.652
| 6524 | 139.0182
| 6525 | 66.7904
| 6526 | 188.9365
| 6527 | 129.5805
| 6528 | 123.3031
| 6529 | 178.4509
| 6530 | 69.5697
| 6531 | 117.236
| 6532 | 193.7877
| 6533 | 86.5199
| 6534 | 206.3155
| 6535 | 111.8312
| 6536 | 84.2688
| 6537 | 114.6283
| 6538 | 123.5941
| 6539 | 132.4306
| 6540 | 165.9936
| 6541 | 102.5333
| 6542 | 187.0342
| 6543 | 183.9557
| 6544 | 120.0651
| 6545 | 99.973
| 6546 | 92.8211
| 6547 | 116.0811
| 6548 | 102.5603
| 6549 | 133.0157
| 6550 | 144.6087
| 6551 | 97.663
| 6552 | 120.8958
| 6553 | 134.7813
| 6554 | 103.0015
| 6555 | 118.5878
| 6556 | 131.3277
| 6557 | 99.5556
| 6558 | 149.9242
| 6559 | 157.1756
| 6560 | 103.0154
| 6561 | 124.3435
| 6562 | 102.0746
| 6563 | 138.4817
| 6564 | 126.8843
| 6565 | 78.8952
| 6566 | 114.2661
| 6567 | 125.4834
| 6568 | 184.412
| 6569 | 109.4234
| 6570 | 131.3761
| 6571 | 84.8904
| 6572 | 121.2288
| 6573 | 89.3205
| 6574 | 102.3309
| 6575 | 99.6242
| 6576 | 150.1874
| 6577 | 102.448
| 6578 | 130.1006
| 6579 | 132.2986
| 6580 | 136.9121
| 6581 | 142.1268
| 6582 | 75.1668
| 6583 | 165.0079
| 6584 | 71.7349
| 6585 | 142.256
| 6586 | 87.3407
| 6587 | 155.3861
| 6588 | 166.6385
| 6589 | 145.6868
| 6590 | 96.8298
| 6591 | 99.6599
| 6592 | 98.5978
| 6593 | 153.3919
| 6594 | 148.9329
| 6595 | 142.58
| 6596 | 120.2818
| 6597 | 92.2637
| 6598 | 135.3949
| 6599 | 152.1987
| 6600 | 89.6619
| 6601 | 158.6787
| 6602 | 121.3555
| 6603 | 141.2228
| 6604 | 114.9196
| 6605 | 166.9827
| 6606 | 130.1477
| 6607 | 100.028
| 6608 | 139.8252
| 6609 | 143.7141
| 6610 | 124.9253
| 6611 | 183.7319
| 6612 | 186.2445
| 6613 | 113.8222
| 6614 | 119.0643
| 6615 | 118.604
| 6616 | 103.7886
| 6617 | 106.0139
| 6618 | 148.8359
| 6619 | 171.3171
| 6620 | 143.0002
| 6621 | 149.443
| 6622 | 113.1948
| 6623 | 84.2087
| 6624 | 69.7995
| 6625 | 154.7955
| 6626 | 143.1254
| 6627 | 97.8169
| 6628 | 145.8176
| 6629 | 120.7092
| 6630 | 106.4837
| 6631 | 160.8946
| 6632 | 144.1114
| 6633 | 124.7884
| 6634 | 147.599
| 6635 | 90.1421
| 6636 | 95.9452
| 6637 | 128.0245
| 6638 | 104.8755
| 6639 | 92.8775
| 6640 | 121.2101
| 6641 | 146.7325
| 6642 | 124.984
| 6643 | 165.2273
| 6644 | 90.1903
| 6645 | 160.709
| 6646 | 163.8981
| 6647 | 114.192
| 6648 | 139.7855
| 6649 | 100.9661
| 6650 | 151.2203
| 6651 | 96.4486
| 6652 | 138.4746
| 6653 | 143.4694
| 6654 | 138.7584
| 6655 | 68.6274
| 6656 | 146.4888
| 6657 | 141.9965
| 6658 | 76.8382
| 6659 | 123.1447
| 6660 | 166.9269
| 6661 | 84.2235
| 6662 | 147.2218
| 6663 | 106.9882
| 6664 | 126.0406
| 6665 | 164.964
| 6666 | 159.7754
| 6667 | 164.1069
| 6668 | 174.6434
| 6669 | 119.7205
| 6670 | 173.5348
| 6671 | 167.1061
| 6672 | 137.4268
| 6673 | 105.134
| 6674 | 164.001
| 6675 | 168.3679
| 6676 | 145.141
| 6677 | 141.4838
| 6678 | 204.2941
| 6679 | 131.4521
| 6680 | 147.7751
| 6681 | 96.9551
| 6682 | 111.9642
| 6683 | 203.0362
| 6684 | 128.4883
| 6685 | 68.9496
| 6686 | 95.6798
| 6687 | 103.8835
| 6688 | 177.8993
| 6689 | 147.5489
| 6690 | 162.8218
| 6691 | 85.245
| 6692 | 97.6584
| 6693 | 172.327
| 6694 | 136.6867
| 6695 | 137.1955
| 6696 | 121.2451
| 6697 | 183.6975
| 6698 | 111.2946
| 6699 | 144.7712
| 6700 | 168.1219
| 6701 | 160.0141
| 6702 | 160.388
| 6703 | 104.9116
| 6704 | 155.7214
| 6705 | 78.9109
| 6706 | 116.9508
| 6707 | 185.8888
| 6708 | 113.3491
| 6709 | 130.6712
| 6710 | 155.1133
| 6711 | 134.7413
| 6712 | 142.9102
| 6713 | 99.8487
| 6714 | 177.5889
| 6715 | 98.6907
| 6716 | 95.4709
| 6717 | 115.9241
| 6718 | 147.6264
| 6719 | 138.1153
| 6720 | 102.0436
| 6721 | 104.2909
| 6722 | 65.161
| 6723 | 189.8064
| 6724 | 90.6452
| 6725 | 125.0781
| 6726 | 166.0919
| 6727 | 74.4515
| 6728 | 88.239
| 6729 | 169.4244
| 6730 | 97.0291
| 6731 | 113.6581
| 6732 | 150.8658
| 6733 | 155.1705
| 6734 | 145.8368
| 6735 | 159.1977
| 6736 | 120.573
| 6737 | 109.2468
| 6738 | 151.1554
| 6739 | 167.1289
| 6740 | 166.1099
| 6741 | 113.3093
| 6742 | 189.7366
| 6743 | 73.1455
| 6744 | 208.2594
| 6745 | 154.0267
| 6746 | 103.9779
| 6747 | 130.7026
| 6748 | 82.7349
| 6749 | 104.1492
| 6750 | 108.4523
| 6751 | 68.5301
| 6752 | 164.9671
| 6753 | 115.6619
| 6754 | 89.8984
| 6755 | 114.0811
| 6756 | 170.7526
| 6757 | 95.7406
| 6758 | 159.4785
| 6759 | 155.5477
| 6760 | 85.9329
| 6761 | 97.7497
| 6762 | 147.3415
| 6763 | 155.1467
| 6764 | 131.2274
| 6765 | 185.7886
| 6766 | 125.2002
| 6767 | 84.7538
| 6768 | 132.3536
| 6769 | 111.9466
| 6770 | 128.4879
| 6771 | 180.3276
| 6772 | 92.605
| 6773 | 143.2249
| 6774 | 98.2159
| 6775 | 82.3835
| 6776 | 140.9639
| 6777 | 184.9486
| 6778 | 161.1789
| 6779 | 139.8958
| 6780 | 125.387
| 6781 | 96.0844
| 6782 | 169.0429
| 6783 | 137.2472
| 6784 | 111.5137
| 6785 | 89.9221
| 6786 | 119.5431
| 6787 | 129.3802
| 6788 | 78.5899
| 6789 | 152.9362
| 6790 | 125.7094
| 6791 | 141.5327
| 6792 | 126.5974
| 6793 | 141.1957
| 6794 | 114.4261
| 6795 | 172.3857
| 6796 | 114.4244
| 6797 | 94.063
| 6798 | 97.6548
| 6799 | 100.3595
| 6800 | 121.9713
| 6801 | 99.9791
| 6802 | 71.7204
| 6803 | 109.741
| 6804 | 119.6033
| 6805 | 81.3663
| 6806 | 171.8802
| 6807 | 117.707
| 6808 | 115.761
| 6809 | 93.0422
| 6810 | 100.6366
| 6811 | 197.0804
| 6812 | 184.699
| 6813 | 114.9206
| 6814 | 85.128
| 6815 | 98.285
| 6816 | 106.0426
| 6817 | 72.5393
| 6818 | 191.9175
| 6819 | 136.0925
| 6820 | 135.0947
| 6821 | 152.8973
| 6822 | 119.1529
| 6823 | 85.4195
| 6824 | 78.3825
| 6825 | 105.0221
| 6826 | 175.4014
| 6827 | 110.9568
| 6828 | 212.7289
| 6829 | 143.2125
| 6830 | 117.136
| 6831 | 137.0678
| 6832 | 132.6341
| 6833 | 116.6782
| 6834 | 146.0787
| 6835 | 156.1934
| 6836 | 137.1236
| 6837 | 80.0642
| 6838 | 80.7989
| 6839 | 111.8752
| 6840 | 88.8933
| 6841 | 133.0466
| 6842 | 134.7482
| 6843 | 136.7333
| 6844 | 122.5051
| 6845 | 180.2354
| 6846 | 113.3156
| 6847 | 152.0919
| 6848 | 108.5348
| 6849 | 117.5935
| 6850 | 195.8526
| 6851 | 144.3581
| 6852 | 120.292
| 6853 | 188.0038
| 6854 | 125.3395
| 6855 | 170.3342
| 6856 | 158.1072
| 6857 | 110.748
| 6858 | 149.5827
| 6859 | 131.1767
| 6860 | 153.8566
| 6861 | 84.8334
| 6862 | 144.9159
| 6863 | 142.9318
| 6864 | 77.0135
| 6865 | 147.4192
| 6866 | 145.6181
| 6867 | 165.4492
| 6868 | 84.4474
| 6869 | 138.3753
| 6870 | 122.8982
| 6871 | 103.5162
| 6872 | 192.0393
| 6873 | 122.8807
| 6874 | 114.1389
| 6875 | 121.1575
| 6876 | 116.0699
| 6877 | 110.7856
| 6878 | 123.1579
| 6879 | 147.2459
| 6880 | 128.8335
| 6881 | 212.4844
| 6882 | 143.1705
| 6883 | 136.4413
| 6884 | 116.4933
| 6885 | 139.0206
| 6886 | 148.9796
| 6887 | 136.5547
| 6888 | 119.5158
| 6889 | 106.8244
| 6890 | 141.1453
| 6891 | 93.7621
| 6892 | 145.8181
| 6893 | 124.0454
| 6894 | 143.8568
| 6895 | 77.5773
| 6896 | 117.6416
| 6897 | 120.264
| 6898 | 206.0923
| 6899 | 99.9535
| 6900 | 123.4633
| 6901 | 118.061
| 6902 | 126.1649
| 6903 | 175.2211
| 6904 | 193.6624
| 6905 | 107.7597
| 6906 | 171.606
| 6907 | 141.1895
| 6908 | 108.3732
| 6909 | 165.8618
| 6910 | 114.2303
| 6911 | 136.1929
| 6912 | 138.0378
| 6913 | 117.0802
| 6914 | 130.7653
| 6915 | 111.9659
| 6916 | 101.7369
| 6917 | 88.6618
| 6918 | 151.1318
| 6919 | 87.7826
| 6920 | 105.7614
| 6921 | 97.417
| 6922 | 144.5735
| 6923 | 162.8327
| 6924 | 144.1903
| 6925 | 153.479
| 6926 | 80.8723
| 6927 | 164.6463
| 6928 | 143.014
| 6929 | 132.0869
| 6930 | 164.6269
| 6931 | 119.0315
| 6932 | 112.4242
| 6933 | 113.6676
| 6934 | 110.2787
| 6935 | 119.7683
| 6936 | 148.2268
| 6937 | 126.6804
| 6938 | 107.7095
| 6939 | 150.7146
| 6940 | 184.7883
| 6941 | 190.3866
| 6942 | 154.4219
| 6943 | 158.3612
| 6944 | 118.5983
| 6945 | 198.1979
| 6946 | 163.7168
| 6947 | 136.8493
| 6948 | 85.346
| 6949 | 129.2199
| 6950 | 141.5552
| 6951 | 86.1731
| 6952 | 113.6958
| 6953 | 115.1101
| 6954 | 88.8052
| 6955 | 98.453
| 6956 | 164.0971
| 6957 | 102.8527
| 6958 | 146.5381
| 6959 | 109.8898
| 6960 | 122.8919
| 6961 | 100.6724
| 6962 | 126.8081
| 6963 | 112.4163
| 6964 | 188.6755
| 6965 | 90.1324
| 6966 | 129.5266
| 6967 | 89.2196
| 6968 | 124.9853
| 6969 | 79.0778
| 6970 | 143.0921
| 6971 | 139.05
| 6972 | 106.8464
| 6973 | 92.1562
| 6974 | 107.2933
| 6975 | 168.3045
| 6976 | 180.3807
| 6977 | 132.3421
| 6978 | 160.9918
| 6979 | 156.6586
| 6980 | 152.9205
| 6981 | 107.638
| 6982 | 172.149
| 6983 | 154.5174
| 6984 | 100.7189
| 6985 | 142.3935
| 6986 | 68.5775
| 6987 | 156.9888
| 6988 | 90.7483
| 6989 | 118.8186
| 6990 | 105.0941
| 6991 | 112.5475
| 6992 | 117.0831
| 6993 | 169.6896
| 6994 | 180.2498
| 6995 | 139.1694
| 6996 | 81.9591
| 6997 | 172.6269
| 6998 | 166.9103
| 6999 | 95.3588
| 7000 | 178.4825
| 7001 | 114.7651
| 7002 | 150.5613
| 7003 | 187.7635
| 7004 | 145.4313
| 7005 | 109.4682
| 7006 | 96.5389
| 7007 | 118.5384
| 7008 | 165.9006
| 7009 | 83.2069
| 7010 | 140.0949
| 7011 | 115.9515
| 7012 | 118.3734
| 7013 | 74.8961
| 7014 | 148.9751
| 7015 | 133.2107
| 7016 | 84.9382
| 7017 | 109.3338
| 7018 | 66.0224
| 7019 | 100.6918
| 7020 | 122.8519
| 7021 | 169.1325
| 7022 | 106.2711
| 7023 | 139.2343
| 7024 | 128.8541
| 7025 | 88.1345
| 7026 | 186.0058
| 7027 | 106.3886
| 7028 | 133.0317
| 7029 | 107.0576
| 7030 | 151.4202
| 7031 | 174.7226
| 7032 | 132.8316
| 7033 | 105.3139
| 7034 | 137.0898
| 7035 | 165.3266
| 7036 | 156.291
| 7037 | 127.0242
| 7038 | 203.2456
| 7039 | 81.7187
| 7040 | 138.3996
| 7041 | 109.6651
| 7042 | 130.0993
| 7043 | 122.7329
| 7044 | 163.9335
| 7045 | 99.0955
| 7046 | 161.1695
| 7047 | 158.5907
| 7048 | 125.4094
| 7049 | 157.6801
| 7050 | 142.3357
| 7051 | 150.791
| 7052 | 192.1073
| 7053 | 167.6634
| 7054 | 139.3901
| 7055 | 138.0513
| 7056 | 86.819
| 7057 | 114.7585
| 7058 | 138.1577
| 7059 | 112.879
| 7060 | 89.2467
| 7061 | 73.1982
| 7062 | 92.1526
| 7063 | 118.3104
| 7064 | 119.8308
| 7065 | 103.5759
| 7066 | 117.5808
| 7067 | 150.5385
| 7068 | 80.559
| 7069 | 187.1864
| 7070 | 144.4586
| 7071 | 185.8201
| 7072 | 93.9896
| 7073 | 126.8835
| 7074 | 106.7315
| 7075 | 108.1963
| 7076 | 91.6756
| 7077 | 91.4577
| 7078 | 136.1664
| 7079 | 115.7586
| 7080 | 157.3563
| 7081 | 147.1729
| 7082 | 114.5471
| 7083 | 98.8247
| 7084 | 90.6867
| 7085 | 79.5053
| 7086 | 148.6079
| 7087 | 127.0296
| 7088 | 90.7574
| 7089 | 151.4561
| 7090 | 154.7632
| 7091 | 107.1265
| 7092 | 109.2159
| 7093 | 93.0104
| 7094 | 114.4569
| 7095 | 72.0602
| 7096 | 131.4904
| 7097 | 177.8946
| 7098 | 121.3241
| 7099 | 161.892
| 7100 | 184.2747
| 7101 | 175.3983
| 7102 | 136.931
| 7103 | 145.0203
| 7104 | 94.3872
| 7105 | 184.4031
| 7106 | 97.6036
| 7107 | 169.0606
| 7108 | 85.5018
| 7109 | 96.1147
| 7110 | 84.5332
| 7111 | 140.2331
| 7112 | 78.2838
| 7113 | 72.5301
| 7114 | 157.8587
| 7115 | 110.0385
| 7116 | 114.975
| 7117 | 107.8755
| 7118 | 124.0791
| 7119 | 124.7679
| 7120 | 71.8547
| 7121 | 104.3976
| 7122 | 130.5761
| 7123 | 142.4393
| 7124 | 70.9319
| 7125 | 178.571
| 7126 | 145.3512
| 7127 | 165.287
| 7128 | 96.2773
| 7129 | 77.715
| 7130 | 116.4431
| 7131 | 212.3538
| 7132 | 140.4069
| 7133 | 155.7979
| 7134 | 96.1227
| 7135 | 103.122
| 7136 | 83.3511
| 7137 | 162.3674
| 7138 | 141.3107
| 7139 | 125.7775
| 7140 | 94.3165
| 7141 | 109.9674
| 7142 | 116.2631
| 7143 | 134.592
| 7144 | 167.5606
| 7145 | 116.7028
| 7146 | 101.5099
| 7147 | 174.1175
| 7148 | 167.1572
| 7149 | 92.9675
| 7150 | 131.9011
| 7151 | 165.8728
| 7152 | 88.1346
| 7153 | 143.0052
| 7154 | 170.5804
| 7155 | 87.8551
| 7156 | 152.2683
| 7157 | 165.9323
| 7158 | 147.1587
| 7159 | 118.2152
| 7160 | 67.3479
| 7161 | 140.145
| 7162 | 160.8693
| 7163 | 201.3018
| 7164 | 105.2833
| 7165 | 90.6464
| 7166 | 122.1751
| 7167 | 118.3519
| 7168 | 95.2515
| 7169 | 205.4773
| 7170 | 178.5818
| 7171 | 107.2143
| 7172 | 174.1283
| 7173 | 105.3219
| 7174 | 205.8855
| 7175 | 144.4963
| 7176 | 87.3988
| 7177 | 134.1
| 7178 | 139.1196
| 7179 | 163.204
| 7180 | 73.7357
| 7181 | 162.5498
| 7182 | 94.9429
| 7183 | 129.7026
| 7184 | 171.7066
| 7185 | 180.583
| 7186 | 105.4178
| 7187 | 170.6357
| 7188 | 93.4805
| 7189 | 110.0768
| 7190 | 158.7547
| 7191 | 85.6955
| 7192 | 139.5128
| 7193 | 89.4077
| 7194 | 109.0633
| 7195 | 148.362
| 7196 | 198.5929
| 7197 | 106.8785
| 7198 | 106.9966
| 7199 | 126.6857
| 7200 | 140.6676
| 7201 | 96.7629
| 7202 | 154.079
| 7203 | 121.0618
| 7204 | 134.3842
| 7205 | 113.459
| 7206 | 110.3819
| 7207 | 134.0424
| 7208 | 140.7355
| 7209 | 150.2606
| 7210 | 121.316
| 7211 | 114.4001
| 7212 | 82.6172
| 7213 | 181.2773
| 7214 | 68.5519
| 7215 | 87.7433
| 7216 | 161.922
| 7217 | 80.2899
| 7218 | 98.0966
| 7219 | 147.7671
| 7220 | 101.5345
| 7221 | 197.51
| 7222 | 95.1503
| 7223 | 80.9181
| 7224 | 110.7965
| 7225 | 75.1855
| 7226 | 122.2391
| 7227 | 135.0717
| 7228 | 144.2258
| 7229 | 120.4086
| 7230 | 137.3418
| 7231 | 170.0953
| 7232 | 100.8994
| 7233 | 186.696
| 7234 | 131.4311
| 7235 | 84.6542
| 7236 | 126.4163
| 7237 | 136.5356
| 7238 | 129.5209
| 7239 | 92.8884
| 7240 | 166.3484
| 7241 | 169.4339
| 7242 | 97.0003
| 7243 | 118.7362
| 7244 | 129.8523
| 7245 | 115.8232
| 7246 | 95.486
| 7247 | 118.2748
| 7248 | 116.6895
| 7249 | 129.9444
| 7250 | 96.0622
| 7251 | 126.1854
| 7252 | 108.5829
| 7253 | 119.4223
| 7254 | 141.5224
| 7255 | 115.288
| 7256 | 108.8345
| 7257 | 125.8305
| 7258 | 113.5583
| 7259 | 104.6679
| 7260 | 106.9924
| 7261 | 121.7786
| 7262 | 182.0617
| 7263 | 181.4723
| 7264 | 125.4494
| 7265 | 121.8235
| 7266 | 108.8858
| 7267 | 80.4187
| 7268 | 112.7451
| 7269 | 99.6639
| 7270 | 110.5499
| 7271 | 115.3636
| 7272 | 103.6236
| 7273 | 121.1874
| 7274 | 159.0863
| 7275 | 123.6544
| 7276 | 127.4823
| 7277 | 144.3559
| 7278 | 113.2418
| 7279 | 147.877
| 7280 | 141.3919
| 7281 | 99.7619
| 7282 | 159.5835
| 7283 | 137.3471
| 7284 | 127.7943
| 7285 | 115.1792
| 7286 | 111.9135
| 7287 | 158.2858
| 7288 | 88.3145
| 7289 | 122.242
| 7290 | 103.6578
| 7291 | 111.7075
| 7292 | 160.055
| 7293 | 140.5035
| 7294 | 85.1841
| 7295 | 142.8184
| 7296 | 90.6613
| 7297 | 94.75
| 7298 | 100.0939
| 7299 | 111.311
| 7300 | 149.489
| 7301 | 138.6703
| 7302 | 106.7569
| 7303 | 190.9373
| 7304 | 150.836
| 7305 | 162.0324
| 7306 | 129.6651
| 7307 | 88.7745
| 7308 | 171.4785
| 7309 | 144.4699
| 7310 | 164.3782
| 7311 | 124.5728
| 7312 | 114.438
| 7313 | 76.4756
| 7314 | 143.6467
| 7315 | 81.9709
| 7316 | 84.5807
| 7317 | 175.7092
| 7318 | 166.6329
| 7319 | 142.0578
| 7320 | 174.5306
| 7321 | 95.2367
| 7322 | 89.8917
| 7323 | 153.2773
| 7324 | 150.0804
| 7325 | 151.2379
| 7326 | 149.8716
| 7327 | 117.04
| 7328 | 180.5641
| 7329 | 72.7952
| 7330 | 104.4544
| 7331 | 137.3969
| 7332 | 170.6432
| 7333 | 85.5919
| 7334 | 124.4872
| 7335 | 138.5209
| 7336 | 106.7055
| 7337 | 178.2699
| 7338 | 95.8212
| 7339 | 145.842
| 7340 | 150.0788
| 7341 | 171.2464
| 7342 | 117.8085
| 7343 | 202.325
| 7344 | 106.6393
| 7345 | 177.0956
| 7346 | 142.9946
| 7347 | 186.9324
| 7348 | 158.1024
| 7349 | 174.3796
| 7350 | 161.7822
| 7351 | 153.3075
| 7352 | 139.7297
| 7353 | 86.4756
| 7354 | 96.433
| 7355 | 163.5685
| 7356 | 138.4476
| 7357 | 117.3985
| 7358 | 148.3194
| 7359 | 88.4233
| 7360 | 179.4223
| 7361 | 102.4667
| 7362 | 95.7144
| 7363 | 157.6965
| 7364 | 115.8664
| 7365 | 155.6595
| 7366 | 122.0763
| 7367 | 179.8599
| 7368 | 177.4622
| 7369 | 84.6483
| 7370 | 149.1682
| 7371 | 65.9495
| 7372 | 82.2804
| 7373 | 155.8933
| 7374 | 100.5115
| 7375 | 75.448
| 7376 | 108.6795
| 7377 | 174.2635
| 7378 | 113.7494
| 7379 | 145.7952
| 7380 | 165.661
| 7381 | 132.7751
| 7382 | 158.4204
| 7383 | 88.2602
| 7384 | 106.3974
| 7385 | 87.2537
| 7386 | 92.4721
| 7387 | 131.4589
| 7388 | 150.6514
| 7389 | 88.6881
| 7390 | 133.408
| 7391 | 121.5787
| 7392 | 90.9686
| 7393 | 109.5558
| 7394 | 106.9991
| 7395 | 124.3587
| 7396 | 84.9944
| 7397 | 156.3965
| 7398 | 78.2048
| 7399 | 98.0766
| 7400 | 66.6994
| 7401 | 142.3197
| 7402 | 139.5566
| 7403 | 122.2474
| 7404 | 172.2467
| 7405 | 166.4201
| 7406 | 92.8662
| 7407 | 125.1717
| 7408 | 91.1911
| 7409 | 120.0503
| 7410 | 82.3458
| 7411 | 107.8511
| 7412 | 109.5747
| 7413 | 117.2435
| 7414 | 151.9524
| 7415 | 84.9927
| 7416 | 172.2305
| 7417 | 101.4152
| 7418 | 157.7522
| 7419 | 128.532
| 7420 | 109.6694
| 7421 | 120.0219
| 7422 | 125.571
| 7423 | 90.8807
| 7424 | 144.4541
| 7425 | 117.884
| 7426 | 166.5774
| 7427 | 155.7437
| 7428 | 129.5722
| 7429 | 133.3825
| 7430 | 155.6536
| 7431 | 148.2653
| 7432 | 83.8795
| 7433 | 168.6846
| 7434 | 196.3012
| 7435 | 162.4596
| 7436 | 133.7497
| 7437 | 178.0541
| 7438 | 131.5856
| 7439 | 151.373
| 7440 | 81.9232
| 7441 | 138.4079
| 7442 | 139.3787
| 7443 | 117.9023
| 7444 | 169.7239
| 7445 | 86.6456
| 7446 | 135.3752
| 7447 | 197.7217
| 7448 | 168.9567
| 7449 | 201.1835
| 7450 | 141.5765
| 7451 | 82.2913
| 7452 | 149.6425
| 7453 | 107.2455
| 7454 | 170.847
| 7455 | 124.0502
| 7456 | 153.5353
| 7457 | 101.5018
| 7458 | 80.4148
| 7459 | 92.8281
| 7460 | 90.9616
| 7461 | 80.6835
| 7462 | 179.5241
| 7463 | 73.7887
| 7464 | 123.2013
| 7465 | 90.4206
| 7466 | 86.9511
| 7467 | 129.47
| 7468 | 146.5243
| 7469 | 156.1013
| 7470 | 89.7714
| 7471 | 87.3538
| 7472 | 163.9672
| 7473 | 139.3795
| 7474 | 75.9933
| 7475 | 205.6174
| 7476 | 82.6094
| 7477 | 120.1212
| 7478 | 126.3843
| 7479 | 79.6764
| 7480 | 131.5882
| 7481 | 128.4675
| 7482 | 95.5463
| 7483 | 115.3203
| 7484 | 127.8325
| 7485 | 173.2172
| 7486 | 123.8814
| 7487 | 138.1785
| 7488 | 190.4821
| 7489 | 99.8085
| 7490 | 92.7898
| 7491 | 135.7493
| 7492 | 105.85
| 7493 | 121.8505
| 7494 | 84.9601
| 7495 | 111.6304
| 7496 | 165.4915
| 7497 | 90.7401
| 7498 | 108.8932
| 7499 | 126.3863
| 7500 | 115.8845
| 7501 | 84.8787
| 7502 | 177.6257
| 7503 | 79.4413
| 7504 | 125.2098
| 7505 | 87.8143
| 7506 | 149.9931
| 7507 | 137.7186
| 7508 | 141.2761
| 7509 | 104.6009
| 7510 | 83.1829
| 7511 | 130.7996
| 7512 | 101.3938
| 7513 | 137.8002
| 7514 | 104.8057
| 7515 | 126.6852
| 7516 | 108.1261
| 7517 | 152.7226
| 7518 | 115.6211
| 7519 | 107.7226
| 7520 | 106.6263
| 7521 | 158.3863
| 7522 | 156.8906
| 7523 | 139.6133
| 7524 | 129.1211
| 7525 | 180.1583
| 7526 | 101.6661
| 7527 | 191.0047
| 7528 | 127.1012
| 7529 | 187.2263
| 7530 | 135.0235
| 7531 | 142.269
| 7532 | 118.6382
| 7533 | 114.3913
| 7534 | 170.9526
| 7535 | 164.8589
| 7536 | 162.7786
| 7537 | 111.3771
| 7538 | 123.8602
| 7539 | 95.759
| 7540 | 109.4376
| 7541 | 173.8343
| 7542 | 83.7786
| 7543 | 127.904
| 7544 | 99.9119
| 7545 | 142.007
| 7546 | 123.9164
| 7547 | 123.714
| 7548 | 117.4352
| 7549 | 124.4436
| 7550 | 174.3443
| 7551 | 187.8593
| 7552 | 106.4227
| 7553 | 105.2745
| 7554 | 100.8407
| 7555 | 179.2197
| 7556 | 132.8895
| 7557 | 156.756
| 7558 | 90.7498
| 7559 | 153.5367
| 7560 | 123.7214
| 7561 | 177.3178
| 7562 | 124.7324
| 7563 | 137.4909
| 7564 | 140.4917
| 7565 | 136.0918
| 7566 | 125.1819
| 7567 | 105.2947
| 7568 | 147.6887
| 7569 | 118.0588
| 7570 | 119.0175
| 7571 | 163.3581
| 7572 | 119.3453
| 7573 | 102.892
| 7574 | 155.7405
| 7575 | 139.0342
| 7576 | 109.0679
| 7577 | 217.3334
| 7578 | 128.6361
| 7579 | 215.1257
| 7580 | 107.1248
| 7581 | 103.0874
| 7582 | 130.6682
| 7583 | 184.2136
| 7584 | 127.2881
| 7585 | 172.3185
| 7586 | 133.5334
| 7587 | 109.7359
| 7588 | 101.6474
| 7589 | 95.7925
| 7590 | 139.0551
| 7591 | 134.9433
| 7592 | 143.4308
| 7593 | 97.6092
| 7594 | 101.1585
| 7595 | 118.3561
| 7596 | 83.3594
| 7597 | 105.2727
| 7598 | 174.4674
| 7599 | 137.8525
| 7600 | 152.4446
| 7601 | 73.5083
| 7602 | 139.9458
| 7603 | 113.0188
| 7604 | 152.1338
| 7605 | 183.9327
| 7606 | 129.9235
| 7607 | 87.9304
| 7608 | 69.9497
| 7609 | 109.6793
| 7610 | 113.9037
| 7611 | 179.8615
| 7612 | 115.4516
| 7613 | 104.1598
| 7614 | 131.0481
| 7615 | 126.4962
| 7616 | 115.5185
| 7617 | 183.8787
| 7618 | 147.2024
| 7619 | 117.5894
| 7620 | 143.7239
| 7621 | 83.1408
| 7622 | 92.5405
| 7623 | 97.9526
| 7624 | 169.6671
| 7625 | 150.5072
| 7626 | 159.7317
| 7627 | 109.3817
| 7628 | 121.9116
| 7629 | 115.9741
| 7630 | 128.4879
| 7631 | 138.8121
| 7632 | 129.2709
| 7633 | 144.6304
| 7634 | 91.7652
| 7635 | 89.2386
| 7636 | 133.8529
| 7637 | 135.0916
| 7638 | 182.378
| 7639 | 100.7154
| 7640 | 185.3621
| 7641 | 91.377
| 7642 | 128.6518
| 7643 | 152.8902
| 7644 | 71.1327
| 7645 | 93.1346
| 7646 | 101.8503
| 7647 | 149.3282
| 7648 | 118.0803
| 7649 | 144.0342
| 7650 | 81.3527
| 7651 | 134.8773
| 7652 | 82.6186
| 7653 | 139.2319
| 7654 | 133.7217
| 7655 | 101.8292
| 7656 | 101.3175
| 7657 | 131.5632
| 7658 | 195.6142
| 7659 | 165.7838
| 7660 | 89.0554
| 7661 | 144.4651
| 7662 | 92.315
| 7663 | 108.7362
| 7664 | 153.7746
| 7665 | 152.5496
| 7666 | 155.6234
| 7667 | 163.8364
| 7668 | 187.057
| 7669 | 81.0402
| 7670 | 111.1197
| 7671 | 82.4066
| 7672 | 97.475
| 7673 | 96.1774
| 7674 | 110.2527
| 7675 | 102.0541
| 7676 | 87.8658
| 7677 | 88.7467
| 7678 | 125.7045
| 7679 | 153.7226
| 7680 | 98.5824
| 7681 | 101.2645
| 7682 | 141.0924
| 7683 | 139.5427
| 7684 | 105.6395
| 7685 | 158.911
| 7686 | 135.3966
| 7687 | 106.5072
| 7688 | 111.8461
| 7689 | 71.9843
| 7690 | 95.7363
| 7691 | 103.0722
| 7692 | 139.1102
| 7693 | 84.7155
| 7694 | 175.8123
| 7695 | 136.4125
| 7696 | 135.7435
| 7697 | 149.8815
| 7698 | 106.6955
| 7699 | 140.969
| 7700 | 101.2615
| 7701 | 112.5738
| 7702 | 131.3664
| 7703 | 112.0353
| 7704 | 95.294
| 7705 | 91.6652
| 7706 | 100.3471
| 7707 | 105.3761
| 7708 | 126.0419
| 7709 | 152.3759
| 7710 | 168.6126
| 7711 | 134.4105
| 7712 | 115.3481
| 7713 | 100.332
| 7714 | 118.3531
| 7715 | 95.9722
| 7716 | 150.3848
| 7717 | 137.7983
| 7718 | 161.0111
| 7719 | 125.1589
| 7720 | 161.1104
| 7721 | 76.4499
| 7722 | 96.0155
| 7723 | 115.8953
| 7724 | 94.2456
| 7725 | 161.742
| 7726 | 94.1403
| 7727 | 198.7265
| 7728 | 145.7246
| 7729 | 133.8957
| 7730 | 148.5493
| 7731 | 93.6288
| 7732 | 111.0076
| 7733 | 146.7823
| 7734 | 194.1881
| 7735 | 88.7875
| 7736 | 157.9136
| 7737 | 191.8155
| 7738 | 151.3566
| 7739 | 168.9805
| 7740 | 111.4028
| 7741 | 105.7738
| 7742 | 152.064
| 7743 | 138.9361
| 7744 | 116.479
| 7745 | 99.7369
| 7746 | 168.7058
| 7747 | 95.6977
| 7748 | 119.3489
| 7749 | 101.2679
| 7750 | 173.755
| 7751 | 91.6105
| 7752 | 113.026
| 7753 | 137.0259
| 7754 | 124.8486
| 7755 | 107.3986
| 7756 | 138.4955
| 7757 | 147.3281
| 7758 | 93.0967
| 7759 | 139.0797
| 7760 | 101.605
| 7761 | 118.966
| 7762 | 187.0098
| 7763 | 136.3944
| 7764 | 100.0459
| 7765 | 159.5868
| 7766 | 81.1615
| 7767 | 156.4694
| 7768 | 127.9806
| 7769 | 94.871
| 7770 | 136.5481
| 7771 | 87.9992
| 7772 | 144.129
| 7773 | 151.0198
| 7774 | 144.1922
| 7775 | 94.0484
| 7776 | 164.3251
| 7777 | 121.203
| 7778 | 130.9316
| 7779 | 123.774
| 7780 | 126.3475
| 7781 | 134.5501
| 7782 | 147.8082
| 7783 | 109.1672
| 7784 | 97.1975
| 7785 | 99.7377
| 7786 | 89.6985
| 7787 | 114.3615
| 7788 | 180.4079
| 7789 | 85.1192
| 7790 | 89.8992
| 7791 | 174.0972
| 7792 | 103.3909
| 7793 | 129.7066
| 7794 | 164.1602
| 7795 | 133.9104
| 7796 | 99.9098
| 7797 | 131.6481
| 7798 | 90.1248
| 7799 | 163.1151
| 7800 | 181.7778
| 7801 | 120.9889
| 7802 | 99.0178
| 7803 | 175.5753
| 7804 | 102.1665
| 7805 | 135.2373
| 7806 | 186.3991
| 7807 | 95.8291
| 7808 | 208.8929
| 7809 | 130.7805
| 7810 | 127.5284
| 7811 | 117.794
| 7812 | 111.8723
| 7813 | 189.4611
| 7814 | 173.4405
| 7815 | 125.0215
| 7816 | 140.8462
| 7817 | 95.9569
| 7818 | 105.8498
| 7819 | 182.065
| 7820 | 85.8376
| 7821 | 184.706
| 7822 | 125.9942
| 7823 | 140.8488
| 7824 | 117.9849
| 7825 | 89.1178
| 7826 | 134.279
| 7827 | 155.4792
| 7828 | 88.0233
| 7829 | 103.5562
| 7830 | 140.0386
| 7831 | 152.9199
| 7832 | 122.7425
| 7833 | 130.4968
| 7834 | 115.2975
| 7835 | 102.0461
| 7836 | 166.571
| 7837 | 104.0857
| 7838 | 83.6676
| 7839 | 171.4236
| 7840 | 202.6919
| 7841 | 96.1314
| 7842 | 100.7885
| 7843 | 122.6461
| 7844 | 100.2163
| 7845 | 179.4041
| 7846 | 138.9545
| 7847 | 144.5976
| 7848 | 128.63
| 7849 | 112.056
| 7850 | 81.5786
| 7851 | 120.3889
| 7852 | 147.1002
| 7853 | 125.0173
| 7854 | 147.7971
| 7855 | 150.0539
| 7856 | 179.5829
| 7857 | 123.3981
| 7858 | 111.6408
| 7859 | 149.1899
| 7860 | 163.551
| 7861 | 125.3611
| 7862 | 123.2791
| 7863 | 92.9193
| 7864 | 166.0406
| 7865 | 100.5586
| 7866 | 140.4329
| 7867 | 100.8173
| 7868 | 91.6783
| 7869 | 127.338
| 7870 | 120.9572
| 7871 | 146.2107
| 7872 | 71.9039
| 7873 | 116.1715
| 7874 | 174.8653
| 7875 | 149.2009
| 7876 | 94.3581
| 7877 | 134.7849
| 7878 | 149.472
| 7879 | 138.0817
| 7880 | 98.5757
| 7881 | 87.105
| 7882 | 166.4507
| 7883 | 92.5882
| 7884 | 166.1061
| 7885 | 135.7449
| 7886 | 99.0318
| 7887 | 185.5501
| 7888 | 107.773
| 7889 | 73.0343
| 7890 | 129.7431
| 7891 | 95.78
| 7892 | 135.4808
| 7893 | 126.1063
| 7894 | 186.6651
| 7895 | 107.8925
| 7896 | 156.4299
| 7897 | 133.3197
| 7898 | 73.8914
| 7899 | 125.6462
| 7900 | 137.2339
| 7901 | 123.4709
| 7902 | 162.0532
| 7903 | 115.0701
| 7904 | 114.3099
| 7905 | 109.8186
| 7906 | 115.6951
| 7907 | 102.6692
| 7908 | 89.4642
| 7909 | 153.4339
| 7910 | 153.3239
| 7911 | 109.4661
| 7912 | 122.3418
| 7913 | 85.6098
| 7914 | 99.8038
| 7915 | 164.914
| 7916 | 139.5754
| 7917 | 110.4711
| 7918 | 125.1642
| 7919 | 130.3064
| 7920 | 164.5493
| 7921 | 144.6068
| 7922 | 156.98
| 7923 | 160.9701
| 7924 | 196.1887
| 7925 | 121.5875
| 7926 | 164.0023
| 7927 | 176.8674
| 7928 | 151.5106
| 7929 | 125.1252
| 7930 | 183.2432
| 7931 | 129.065
| 7932 | 192.8386
| 7933 | 81.492
| 7934 | 72.1199
| 7935 | 148.0231
| 7936 | 83.6076
| 7937 | 97.1259
| 7938 | 101.2301
| 7939 | 111.6159
| 7940 | 159.1618
| 7941 | 171.767
| 7942 | 113.5681
| 7943 | 159.6651
| 7944 | 104.5379
| 7945 | 113.2489
| 7946 | 89.0045
| 7947 | 152.5594
| 7948 | 105.4987
| 7949 | 88.503
| 7950 | 128.666
| 7951 | 136.5981
| 7952 | 142.6843
| 7953 | 63.6948
| 7954 | 126.2594
| 7955 | 145.9565
| 7956 | 200.1239
| 7957 | 137.3437
| 7958 | 81.3261
| 7959 | 121.3644
| 7960 | 103.6626
| 7961 | 115.218
| 7962 | 135.5929
| 7963 | 151.1622
| 7964 | 158.955
| 7965 | 85.792
| 7966 | 109.1948
| 7967 | 124.205
| 7968 | 176.4668
| 7969 | 111.409
| 7970 | 113.8076
| 7971 | 76.2366
| 7972 | 111.7188
| 7973 | 124.2903
| 7974 | 162.7693
| 7975 | 122.3272
| 7976 | 79.7335
| 7977 | 115.8093
| 7978 | 135.8939
| 7979 | 95.9793
| 7980 | 67.6494
| 7981 | 168.1155
| 7982 | 144.11
| 7983 | 97.8094
| 7984 | 169.0981
| 7985 | 101.043
| 7986 | 114.9884
| 7987 | 103.0773
| 7988 | 165.6626
| 7989 | 65.252
| 7990 | 108.4315
| 7991 | 122.7795
| 7992 | 178.0115
| 7993 | 69.1357
| 7994 | 100.3644
| 7995 | 145.6079
| 7996 | 173.1122
| 7997 | 150.368
| 7998 | 103.9115
| 7999 | 191.7047
| 8000 | 97.8634
| 8001 | 92.4728
| 8002 | 81.1663
| 8003 | 172.8617
| 8004 | 202.3081
| 8005 | 144.7033
| 8006 | 151.085
| 8007 | 133.2906
| 8008 | 152.0946
| 8009 | 183.635
| 8010 | 110.7753
| 8011 | 139.8989
| 8012 | 66.8505
| 8013 | 158.1678
| 8014 | 82.0532
| 8015 | 186.6366
| 8016 | 110.3463
| 8017 | 110.9895
| 8018 | 119.4018
| 8019 | 150.4848
| 8020 | 91.738
| 8021 | 74.1748
| 8022 | 114.4835
| 8023 | 130.0694
| 8024 | 119.321
| 8025 | 122.7919
| 8026 | 100.6253
| 8027 | 132.7544
| 8028 | 183.1317
| 8029 | 175.1268
| 8030 | 107.717
| 8031 | 101.861
| 8032 | 98.901
| 8033 | 177.0467
| 8034 | 116.0235
| 8035 | 106.444
| 8036 | 170.5779
| 8037 | 104.3342
| 8038 | 167.0393
| 8039 | 95.6896
| 8040 | 130.5255
| 8041 | 179.0997
| 8042 | 186.0667
| 8043 | 133.7532
| 8044 | 140.0324
| 8045 | 116.0413
| 8046 | 154.3696
| 8047 | 78.8986
| 8048 | 146.9213
| 8049 | 132.817
| 8050 | 123.2101
| 8051 | 92.2211
| 8052 | 139.9305
| 8053 | 209.4321
| 8054 | 66.259
| 8055 | 135.5114
| 8056 | 174.0354
| 8057 | 150.6006
| 8058 | 195.246
| 8059 | 70.059
| 8060 | 149.3988
| 8061 | 143.7054
| 8062 | 123.2605
| 8063 | 112.8505
| 8064 | 124.7941
| 8065 | 114.7925
| 8066 | 134.1851
| 8067 | 139.2074
| 8068 | 148.334
| 8069 | 139.7773
| 8070 | 118.029
| 8071 | 203.8703
| 8072 | 159.3543
| 8073 | 139.6724
| 8074 | 112.0211
| 8075 | 206.7681
| 8076 | 141.192
| 8077 | 97.2147
| 8078 | 216.1395
| 8079 | 118.0172
| 8080 | 99.4698
| 8081 | 149.4244
| 8082 | 200.6804
| 8083 | 167.0125
| 8084 | 136.9069
| 8085 | 120.0208
| 8086 | 87.3016
| 8087 | 110.0459
| 8088 | 93.0122
| 8089 | 136.9611
| 8090 | 74.8197
| 8091 | 157.9791
| 8092 | 184.1001
| 8093 | 136.3378
| 8094 | 150.6973
| 8095 | 98.7603
| 8096 | 129.6935
| 8097 | 120.0163
| 8098 | 136.7259
| 8099 | 199.7531
| 8100 | 145.9186
| 8101 | 78.1167
| 8102 | 88.8751
| 8103 | 173.6261
| 8104 | 84.8028
| 8105 | 109.992
| 8106 | 67.726
| 8107 | 161.7111
| 8108 | 141.6807
| 8109 | 168.381
| 8110 | 114.7363
| 8111 | 176.782
| 8112 | 116.8066
| 8113 | 173.6184
| 8114 | 167.5796
| 8115 | 126.5173
| 8116 | 134.6339
| 8117 | 178.1817
| 8118 | 64.3619
| 8119 | 110.7223
| 8120 | 110.0315
| 8121 | 124.8659
| 8122 | 83.9047
| 8123 | 83.6179
| 8124 | 94.1304
| 8125 | 124.5168
| 8126 | 160.9954
| 8127 | 139.1402
| 8128 | 152.0653
| 8129 | 183.3728
| 8130 | 98.3087
| 8131 | 102.2319
| 8132 | 126.0962
| 8133 | 151.1813
| 8134 | 141.0314
| 8135 | 142.8105
| 8136 | 176.0077
| 8137 | 83.2698
| 8138 | 89.7096
| 8139 | 132.9668
| 8140 | 90.2855
| 8141 | 169.3125
| 8142 | 117.1459
| 8143 | 84.2317
| 8144 | 160.1428
| 8145 | 135.7815
| 8146 | 132.7593
| 8147 | 163.1892
| 8148 | 158.4702
| 8149 | 145.7608
| 8150 | 130.5113
| 8151 | 188.8164
| 8152 | 165.8387
| 8153 | 171.871
| 8154 | 174.5565
| 8155 | 156.6349
| 8156 | 97.7352
| 8157 | 71.205
| 8158 | 164.4614
| 8159 | 175.028
| 8160 | 192.1485
| 8161 | 157.3186
| 8162 | 171.2675
| 8163 | 157.2596
| 8164 | 108.3607
| 8165 | 153.0092
| 8166 | 105.8523
| 8167 | 124.3072
| 8168 | 77.5992
| 8169 | 112.0854
| 8170 | 169.2325
| 8171 | 147.1962
| 8172 | 170.9957
| 8173 | 112.9472
| 8174 | 75.801
| 8175 | 154.7584
| 8176 | 85.6775
| 8177 | 139.19
| 8178 | 152.5912
| 8179 | 128.2091
| 8180 | 133.0108
| 8181 | 178.6302
| 8182 | 185.2383
| 8183 | 182.6116
| 8184 | 122.8081
| 8185 | 159.8654
| 8186 | 112.2539
| 8187 | 117.3422
| 8188 | 86.5326
| 8189 | 133.5528
| 8190 | 175.8129
| 8191 | 118.7054
| 8192 | 137.9828
| 8193 | 122.8736
| 8194 | 128.7359
| 8195 | 145.6722
| 8196 | 146.0678
| 8197 | 129.2949
| 8198 | 183.5038
| 8199 | 106.41
| 8200 | 160.2786
| 8201 | 96.2138
| 8202 | 111.1611
| 8203 | 168.9014
| 8204 | 153.4757
| 8205 | 86.833
| 8206 | 96.7435
| 8207 | 116.6228
| 8208 | 189.5456
| 8209 | 164.241
| 8210 | 146.9678
| 8211 | 88.8756
| 8212 | 114.5736
| 8213 | 108.4074
| 8214 | 110.223
| 8215 | 165.9282
| 8216 | 204.8313
| 8217 | 104.428
| 8218 | 130.9678
| 8219 | 161.6303
| 8220 | 130.1015
| 8221 | 103.6108
| 8222 | 164.5195
| 8223 | 109.7862
| 8224 | 92.2133
| 8225 | 100.2307
| 8226 | 100.0766
| 8227 | 109.3632
| 8228 | 182.2249
| 8229 | 126.6788
| 8230 | 128.4879
| 8231 | 147.6387
| 8232 | 115.4462
| 8233 | 153.1994
| 8234 | 119.1139
| 8235 | 174.9423
| 8236 | 157.3779
| 8237 | 97.511
| 8238 | 108.9328
| 8239 | 110.3506
| 8240 | 128.3545
| 8241 | 180.3064
| 8242 | 101.7457
| 8243 | 95.9084
| 8244 | 103.3255
| 8245 | 109.5438
| 8246 | 110.891
| 8247 | 169.9459
| 8248 | 157.0369
| 8249 | 79.8768
| 8250 | 134.8376
| 8251 | 88.4507
| 8252 | 69.1499
| 8253 | 116.4798
| 8254 | 95.9097
| 8255 | 139.4612
| 8256 | 123.6981
| 8257 | 107.4907
| 8258 | 121.7167
| 8259 | 99.2969
| 8260 | 157.2461
| 8261 | 116.9609
| 8262 | 93.0088
| 8263 | 119.9824
| 8264 | 117.5343
| 8265 | 188.8318
| 8266 | 185.5251
| 8267 | 103.206
| 8268 | 88.4919
| 8269 | 147.3394
| 8270 | 167.4846
| 8271 | 102.724
| 8272 | 144.1625
| 8273 | 107.8903
| 8274 | 127.9056
| 8275 | 88.7899
| 8276 | 108.4564
| 8277 | 143.1877
| 8278 | 150.3223
| 8279 | 112.4344
| 8280 | 77.5445
| 8281 | 121.0352
| 8282 | 183.2991
| 8283 | 95.7705
| 8284 | 115.9652
| 8285 | 209.3588
| 8286 | 143.5711
| 8287 | 135.0582
| 8288 | 103.2119
| 8289 | 94.7334
| 8290 | 128.654
| 8291 | 130.6856
| 8292 | 151.4817
| 8293 | 86.3889
| 8294 | 152.7458
| 8295 | 107.7076
| 8296 | 152.4112
| 8297 | 104.5113
| 8298 | 123.8562
| 8299 | 202.0784
| 8300 | 88.04
| 8301 | 120.251
| 8302 | 108.2628
| 8303 | 109.5137
| 8304 | 104.3813
| 8305 | 127.228
| 8306 | 94.8019
| 8307 | 81.8509
| 8308 | 104.8699
| 8309 | 101.0346
| 8310 | 154.7848
| 8311 | 160.6764
| 8312 | 144.8498
| 8313 | 120.2166
| 8314 | 104.3239
| 8315 | 130.7363
| 8316 | 142.3684
| 8317 | 104.9281
| 8318 | 140.8046
| 8319 | 94.7243
| 8320 | 113.2555
| 8321 | 90.2248
| 8322 | 159.5978
| 8323 | 168.7186
| 8324 | 170.7269
| 8325 | 123.2946
| 8326 | 151.1408
| 8327 | 106.0782
| 8328 | 116.9581
| 8329 | 146.5693
| 8330 | 117.7523
| 8331 | 122.713
| 8332 | 134.5455
| 8333 | 118.6092
| 8334 | 91.674
| 8335 | 185.9207
| 8336 | 125.9402
| 8337 | 105.8742
| 8338 | 162.9251
| 8339 | 128.9875
| 8340 | 110.3899
| 8341 | 157.3021
| 8342 | 128.7325
| 8343 | 161.8242
| 8344 | 168.3961
| 8345 | 144.2547
| 8346 | 114.3641
| 8347 | 78.2747
| 8348 | 168.0348
| 8349 | 141.5999
| 8350 | 88.9573
| 8351 | 132.3516
| 8352 | 92.1749
| 8353 | 142.7004
| 8354 | 126.0046
| 8355 | 100.4758
| 8356 | 166.9997
| 8357 | 176.5718
| 8358 | 82.4141
| 8359 | 144.3313
| 8360 | 107.6915
| 8361 | 132.0997
| 8362 | 127.2555
| 8363 | 152.4993
| 8364 | 106.2442
| 8365 | 101.3521
| 8366 | 93.2135
| 8367 | 80.3882
| 8368 | 83.3449
| 8369 | 174.8501
| 8370 | 124.8114
| 8371 | 126.3843
| 8372 | 215.4361
| 8373 | 164.0353
| 8374 | 118.4774
| 8375 | 134.4619
| 8376 | 90.0601
| 8377 | 121.6308
| 8378 | 95.2053
| 8379 | 89.549
| 8380 | 94.272
| 8381 | 105.5919
| 8382 | 160.9879
| 8383 | 134.3209
| 8384 | 89.5905
| 8385 | 124.9522
| 8386 | 174.5003
| 8387 | 143.5372
| 8388 | 95.105
| 8389 | 150.7528
| 8390 | 169.2445
| 8391 | 77.3225
| 8392 | 216.0348
| 8393 | 73.332
| 8394 | 140.431
| 8395 | 133.4818
| 8396 | 125.8018
| 8397 | 136.4844
| 8398 | 129.7892
| 8399 | 86.1936
| 8400 | 95.0921
| 8401 | 128.6971
| 8402 | 147.9588
| 8403 | 165.5782
| 8404 | 120.7823
| 8405 | 144.1861
| 8406 | 132.0475
| 8407 | 136.6416
| 8408 | 86.1587
| 8409 | 83.9259
| 8410 | 158.1309
| 8411 | 181.7211
| 8412 | 116.8871
| 8413 | 114.6479
| 8414 | 129.4784
| 8415 | 89.3609
| 8416 | 144.8765
| 8417 | 143.3092
| 8418 | 141.4436
| 8419 | 186.9142
| 8420 | 117.741
| 8421 | 130.7232
| 8422 | 101.3512
| 8423 | 90.9939
| 8424 | 102.7622
| 8425 | 190.0569
| 8426 | 172.575
| 8427 | 158.9305
| 8428 | 90.3834
| 8429 | 91.6268
| 8430 | 151.9325
| 8431 | 168.327
| 8432 | 138.4695
| 8433 | 140.2304
| 8434 | 151.6214
| 8435 | 150.2265
| 8436 | 122.2432
| 8437 | 103.7566
| 8438 | 97.4339
| 8439 | 116.5638
| 8440 | 136.9074
| 8441 | 140.2206
| 8442 | 111.8649
| 8443 | 96.2774
| 8444 | 83.8498
| 8445 | 192.5709
| 8446 | 196.6137
| 8447 | 147.6468
| 8448 | 104.3174
| 8449 | 144.1386
| 8450 | 167.505
| 8451 | 132.1488
| 8452 | 134.0774
| 8453 | 122.9515
| 8454 | 152.8361
| 8455 | 168.2335
| 8456 | 129.3833
| 8457 | 124.1428
| 8458 | 111.8458
| 8459 | 111.2888
| 8460 | 135.3309
| 8461 | 151.0765
| 8462 | 168.1549
| 8463 | 97.4886
| 8464 | 118.1894
| 8465 | 115.511
| 8466 | 136.0717
| 8467 | 144.8836
| 8468 | 114.2008
| 8469 | 112.1839
| 8470 | 183.9094
| 8471 | 115.5464
| 8472 | 130.18
| 8473 | 135.6016
| 8474 | 99.0607
| 8475 | 96.317
| 8476 | 123.4021
| 8477 | 86.959
| 8478 | 83.1144
| 8479 | 196.4651
| 8480 | 176.3345
| 8481 | 137.2933
| 8482 | 106.1398
| 8483 | 181.7437
| 8484 | 172.6431
| 8485 | 80.6523
| 8486 | 137.005
| 8487 | 200.2495
| 8488 | 65.8119
| 8489 | 95.7484
| 8490 | 200.6543
| 8491 | 104.5441
| 8492 | 157.5219
| 8493 | 208.8492
| 8494 | 151.618
| 8495 | 132.419
| 8496 | 110.1854
| 8497 | 124.9895
| 8498 | 88.6728
| 8499 | 153.0124
| 8500 | 116.387
| 8501 | 149.3734
| 8502 | 168.6008
| 8503 | 132.9471
| 8504 | 118.3612
| 8505 | 109.759
| 8506 | 135.3315
| 8507 | 139.1363
| 8508 | 154.8603
| 8509 | 144.1517
| 8510 | 171.2127
| 8511 | 80.0894
| 8512 | 111.8981
| 8513 | 212.8143
| 8514 | 181.7414
| 8515 | 136.5202
| 8516 | 109.6226
| 8517 | 195.8906
| 8518 | 81.2132
| 8519 | 70.2316
| 8520 | 111.0573
| 8521 | 98.4386
| 8522 | 131.465
| 8523 | 77.6423
| 8524 | 98.5892
| 8525 | 214.6457
| 8526 | 193.9154
| 8527 | 199.1975
| 8528 | 131.6736
| 8529 | 106.3834
| 8530 | 126.0723
| 8531 | 199.3378
| 8532 | 139.3862
| 8533 | 129.7418
| 8534 | 154.513
| 8535 | 78.6903
| 8536 | 74.5095
| 8537 | 125.4619
| 8538 | 145.1973
| 8539 | 105.014
| 8540 | 114.0517
| 8541 | 93.8671
| 8542 | 108.5504
| 8543 | 165.346
| 8544 | 110.9844
| 8545 | 132.2245
| 8546 | 156.7962
| 8547 | 100.006
| 8548 | 141.0419
| 8549 | 127.347
| 8550 | 144.0126
| 8551 | 143.425
| 8552 | 121.9678
| 8553 | 111.1045
| 8554 | 146.4499
| 8555 | 82.9005
| 8556 | 197.6074
| 8557 | 137.3417
| 8558 | 131.9277
| 8559 | 131.325
| 8560 | 178.9105
| 8561 | 146.8417
| 8562 | 175.6595
| 8563 | 173.6206
| 8564 | 81.7168
| 8565 | 103.5959
| 8566 | 158.1683
| 8567 | 187.9184
| 8568 | 157.5213
| 8569 | 185.1492
| 8570 | 100.1325
| 8571 | 89.6064
| 8572 | 172.6356
| 8573 | 105.0448
| 8574 | 212.9735
| 8575 | 148.4734
| 8576 | 127.7934
| 8577 | 172.962
| 8578 | 123.2219
| 8579 | 112.3789
| 8580 | 101.1238
| 8581 | 105.7567
| 8582 | 163.3441
| 8583 | 154.6998
| 8584 | 84.4503
| 8585 | 139.8228
| 8586 | 98.0556
| 8587 | 151.1725
| 8588 | 116.555
| 8589 | 116.7197
| 8590 | 102.0507
| 8591 | 120.584
| 8592 | 115.6783
| 8593 | 174.1955
| 8594 | 152.1816
| 8595 | 118.3219
| 8596 | 96.2654
| 8597 | 168.6841
| 8598 | 119.8934
| 8599 | 164.6342
| 8600 | 88.6882
| 8601 | 158.8434
| 8602 | 147.5766
| 8603 | 149.1365
| 8604 | 130.2595
| 8605 | 154.4215
| 8606 | 147.1739
| 8607 | 92.7063
| 8608 | 109.9137
| 8609 | 93.8912
| 8610 | 113.0717
| 8611 | 179.2924
| 8612 | 109.517
| 8613 | 129.8671
| 8614 | 102.1483
| 8615 | 93.833
| 8616 | 72.3699
| 8617 | 143.1562
| 8618 | 130.6796
| 8619 | 140.6262
| 8620 | 94.1854
| 8621 | 191.5738
| 8622 | 115.66
| 8623 | 141.1709
| 8624 | 72.186
| 8625 | 128.5146
| 8626 | 128.2032
| 8627 | 143.0917
| 8628 | 129.4524
| 8629 | 113.0818
| 8630 | 143.6503
| 8631 | 116.9941
| 8632 | 194.4473
| 8633 | 146.1717
| 8634 | 121.7529
| 8635 | 86.923
| 8636 | 119.0846
| 8637 | 95.2647
| 8638 | 75.4449
| 8639 | 131.1896
| 8640 | 128.3007
| 8641 | 117.7154
| 8642 | 154.235
| 8643 | 97.8762
| 8644 | 84.2728
| 8645 | 151.3092
| 8646 | 98.9386
| 8647 | 90.365
| 8648 | 146.1289
| 8649 | 179.9496
| 8650 | 84.1441
| 8651 | 144.8341
| 8652 | 120.1565
| 8653 | 82.6777
| 8654 | 135.4267
| 8655 | 98.7885
| 8656 | 139.617
| 8657 | 124.1741
| 8658 | 107.795
| 8659 | 188.4312
| 8660 | 152.3406
| 8661 | 142.1665
| 8662 | 140.867
| 8663 | 153.5354
| 8664 | 181.8888
| 8665 | 168.6365
| 8666 | 199.0539
| 8667 | 106.3399
| 8668 | 102.2908
| 8669 | 163.4577
| 8670 | 154.7208
| 8671 | 105.729
| 8672 | 108.4962
| 8673 | 83.3099
| 8674 | 80.5754
| 8675 | 154.9825
| 8676 | 96.7589
| 8677 | 89.9244
| 8678 | 168.6078
| 8679 | 147.3503
| 8680 | 89.4933
| 8681 | 97.3625
| 8682 | 109.0661
| 8683 | 123.9839
| 8684 | 152.5808
| 8685 | 120.8047
| 8686 | 148.6075
| 8687 | 93.35
| 8688 | 156.2082
| 8689 | 75.5957
| 8690 | 102.1759
| 8691 | 78.0145
| 8692 | 116.2529
| 8693 | 148.8618
| 8694 | 79.3773
| 8695 | 162.6048
| 8696 | 116.6231
| 8697 | 196.1492
| 8698 | 154.0886
| 8699 | 116.276
| 8700 | 107.7969
| 8701 | 125.049
| 8702 | 182.0722
| 8703 | 128.169
| 8704 | 122.6731
| 8705 | 110.731
| 8706 | 200.5695
| 8707 | 138.4947
| 8708 | 101.0599
| 8709 | 120.855
| 8710 | 167.2346
| 8711 | 101.1358
| 8712 | 165.5045
| 8713 | 83.6846
| 8714 | 103.3826
| 8715 | 131.2573
| 8716 | 134.2498
| 8717 | 143.0721
| 8718 | 139.2666
| 8719 | 98.499
| 8720 | 151.9792
| 8721 | 103.9336
| 8722 | 86.0975
| 8723 | 188.6857
| 8724 | 140.6107
| 8725 | 116.3643
| 8726 | 77.4704
| 8727 | 140.083
| 8728 | 109.5886
| 8729 | 121.1549
| 8730 | 144.9781
| 8731 | 85.7006
| 8732 | 89.1538
| 8733 | 104.2534
| 8734 | 113.0023
| 8735 | 73.348
| 8736 | 87.5029
| 8737 | 111.2935
| 8738 | 144.7024
| 8739 | 128.5464
| 8740 | 117.6703
| 8741 | 141.9889
| 8742 | 111.2823
| 8743 | 135.4665
| 8744 | 124.9063
| 8745 | 160.6705
| 8746 | 119.1885
| 8747 | 76.0349
| 8748 | 148.3893
| 8749 | 119.4321
| 8750 | 162.436
| 8751 | 151.3651
| 8752 | 158.0422
| 8753 | 102.215
| 8754 | 127.064
| 8755 | 113.7095
| 8756 | 136.2365
| 8757 | 130.381
| 8758 | 151.0598
| 8759 | 178.4306
| 8760 | 123.9287
| 8761 | 137.8969
| 8762 | 128.8894
| 8763 | 164.5129
| 8764 | 148.0828
| 8765 | 90.2397
| 8766 | 166.9462
| 8767 | 190.8634
| 8768 | 120.9204
| 8769 | 112.8997
| 8770 | 110.6209
| 8771 | 196.869
| 8772 | 87.9877
| 8773 | 143.4071
| 8774 | 72.4528
| 8775 | 100.7527
| 8776 | 143.7904
| 8777 | 94.1912
| 8778 | 122.0368
| 8779 | 106.1025
| 8780 | 69.1273
| 8781 | 120.0641
| 8782 | 132.2365
| 8783 | 119.9931
| 8784 | 189.7106
| 8785 | 115.0976
| 8786 | 119.2321
| 8787 | 95.7808
| 8788 | 154.6098
| 8789 | 140.7603
| 8790 | 107.9815
| 8791 | 150.0866
| 8792 | 175.7682
| 8793 | 175.1742
| 8794 | 158.2212
| 8795 | 79.2043
| 8796 | 141.6912
| 8797 | 88.2631
| 8798 | 96.6088
| 8799 | 119.851
| 8800 | 168.8417
| 8801 | 82.0067
| 8802 | 184.8074
| 8803 | 150.7908
| 8804 | 116.6887
| 8805 | 120.7886
| 8806 | 183.2375
| 8807 | 167.5572
| 8808 | 134.3178
| 8809 | 182.2893
| 8810 | 85.6214
| 8811 | 107.5802
| 8812 | 68.4261
| 8813 | 171.4926
| 8814 | 138.0779
| 8815 | 75.133
| 8816 | 100.0545
| 8817 | 130.1617
| 8818 | 171.4207
| 8819 | 95.6666
| 8820 | 115.1357
| 8821 | 104.8938
| 8822 | 142.608
| 8823 | 176.0322
| 8824 | 139.5779
| 8825 | 149.8199
| 8826 | 99.9369
| 8827 | 175.0804
| 8828 | 118.8673
| 8829 | 105.3108
| 8830 | 136.0861
| 8831 | 112.3994
| 8832 | 132.1882
| 8833 | 121.7245
| 8834 | 136.9512
| 8835 | 138.6222
| 8836 | 171.7589
| 8837 | 99.2797
| 8838 | 209.2101
| 8839 | 100.0814
| 8840 | 134.9143
| 8841 | 137.4608
| 8842 | 105.0423
| 8843 | 191.9487
| 8844 | 118.3439
| 8845 | 95.6122
| 8846 | 123.2037
| 8847 | 128.1519
| 8848 | 178.6549
| 8849 | 135.5167
| 8850 | 190.6479
| 8851 | 111.9173
| 8852 | 87.3283
| 8853 | 129.213
| 8854 | 123.2096
| 8855 | 137.6582
| 8856 | 157.2638
| 8857 | 161.0117
| 8858 | 144.6586
| 8859 | 102.8202
| 8860 | 138.7225
| 8861 | 90.0004
| 8862 | 135.8203
| 8863 | 206.5004
| 8864 | 163.1139
| 8865 | 126.2691
| 8866 | 77.1428
| 8867 | 81.762
| 8868 | 99.0556
| 8869 | 154.4531
| 8870 | 113.5322
| 8871 | 106.6365
| 8872 | 88.2833
| 8873 | 111.9225
| 8874 | 76.1629
| 8875 | 97.41
| 8876 | 195.9933
| 8877 | 163.3545
| 8878 | 179.4192
| 8879 | 69.7432
| 8880 | 136.0826
| 8881 | 94.2852
| 8882 | 209.2814
| 8883 | 144.7611
| 8884 | 127.3157
| 8885 | 106.7231
| 8886 | 92.3322
| 8887 | 93.4026
| 8888 | 84.0884
| 8889 | 109.682
| 8890 | 66.4409
| 8891 | 108.7123
| 8892 | 136.0796
| 8893 | 143.2387
| 8894 | 189.5575
| 8895 | 136.3957
| 8896 | 147.6433
| 8897 | 157.8277
| 8898 | 88.8092
| 8899 | 200.9054
| 8900 | 88.4089
| 8901 | 91.0353
| 8902 | 136.0803
| 8903 | 123.8844
| 8904 | 151.9954
| 8905 | 118.091
| 8906 | 128.3826
| 8907 | 125.3658
| 8908 | 88.8789
| 8909 | 105.2842
| 8910 | 129.4365
| 8911 | 163.3583
| 8912 | 115.9235
| 8913 | 154.953
| 8914 | 189.8936
| 8915 | 156.5452
| 8916 | 90.7142
| 8917 | 107.8023
| 8918 | 119.9048
| 8919 | 126.092
| 8920 | 102.0858
| 8921 | 192.2002
| 8922 | 77.5319
| 8923 | 177.81
| 8924 | 92.671
| 8925 | 71.5629
| 8926 | 126.8141
| 8927 | 75.0409
| 8928 | 181.2795
| 8929 | 161.7291
| 8930 | 139.0764
| 8931 | 115.4403
| 8932 | 193.1163
| 8933 | 147.5279
| 8934 | 164.5635
| 8935 | 68.4616
| 8936 | 219.2517
| 8937 | 145.4736
| 8938 | 136.3545
| 8939 | 107.2081
| 8940 | 87.6468
| 8941 | 126.4721
| 8942 | 119.3932
| 8943 | 79.0516
| 8944 | 127.9438
| 8945 | 102.9791
| 8946 | 95.3589
| 8947 | 76.1698
| 8948 | 166.8808
| 8949 | 144.8969
| 8950 | 116.3615
| 8951 | 108.3744
| 8952 | 98.0739
| 8953 | 114.211
| 8954 | 179.0111
| 8955 | 160.2201
| 8956 | 183.2449
| 8957 | 85.7416
| 8958 | 120.6128
| 8959 | 173.1159
| 8960 | 109.9436
| 8961 | 161.1388
| 8962 | 139.1809
| 8963 | 139.8525
| 8964 | 178.7726
| 8965 | 177.9808
| 8966 | 130.1211
| 8967 | 108.768
| 8968 | 115.0013
| 8969 | 187.5007
| 8970 | 97.2546
| 8971 | 107.6951
| 8972 | 152.9534
| 8973 | 110.786
| 8974 | 91.53
| 8975 | 116.6587
| 8976 | 110.6713
| 8977 | 112.8717
| 8978 | 106.3143
| 8979 | 86.1646
| 8980 | 96.677
| 8981 | 157.8202
| 8982 | 113.178
| 8983 | 87.5154
| 8984 | 166.994
| 8985 | 201.2817
| 8986 | 70.0111
| 8987 | 84.8437
| 8988 | 101.7854
| 8989 | 98.4035
| 8990 | 148.5577
| 8991 | 89.7014
| 8992 | 123.162
| 8993 | 98.0935
| 8994 | 107.8483
| 8995 | 111.8831
| 8996 | 167.9724
| 8997 | 156.9007
| 8998 | 76.9259
| 8999 | 113.1478
| 9000 | 134.8516
| 9001 | 108.1362
| 9002 | 104.2737
| 9003 | 114.2786
| 9004 | 83.7421
| 9005 | 153.9041
| 9006 | 125.4652
| 9007 | 117.0224
| 9008 | 133.8655
| 9009 | 176.3635
| 9010 | 143.1146
| 9011 | 94.2494
| 9012 | 107.6371
| 9013 | 113.4052
| 9014 | 127.8726
| 9015 | 117.1435
| 9016 | 129.6016
| 9017 | 125.0214
| 9018 | 168.1814
| 9019 | 80.2266
| 9020 | 137.473
| 9021 | 147.8476
| 9022 | 126.4953
| 9023 | 179.1506
| 9024 | 123.468
| 9025 | 123.0202
| 9026 | 130.3338
| 9027 | 140.0395
| 9028 | 160.6037
| 9029 | 155.0888
| 9030 | 97.6554
| 9031 | 210.1138
| 9032 | 109.4503
| 9033 | 108.2702
| 9034 | 117.1624
| 9035 | 98.7141
| 9036 | 152.0828
| 9037 | 70.1912
| 9038 | 138.7971
| 9039 | 122.0201
| 9040 | 147.5426
| 9041 | 84.3498
| 9042 | 63.7932
| 9043 | 96.0397
| 9044 | 147.7565
| 9045 | 138.8807
| 9046 | 128.7534
| 9047 | 111.1314
| 9048 | 94.178
| 9049 | 165.7379
| 9050 | 92.9499
| 9051 | 117.3563
| 9052 | 125.5393
| 9053 | 91.386
| 9054 | 84.0984
| 9055 | 134.4389
| 9056 | 158.4469
| 9057 | 74.3018
| 9058 | 110.8929
| 9059 | 120.0093
| 9060 | 87.2897
| 9061 | 101.5697
| 9062 | 143.7958
| 9063 | 92.6215
| 9064 | 131.647
| 9065 | 113.4047
| 9066 | 107.9618
| 9067 | 111.2614
| 9068 | 147.7339
| 9069 | 100.225
| 9070 | 129.328
| 9071 | 136.7647
| 9072 | 105.2199
| 9073 | 142.746
| 9074 | 124.5828
| 9075 | 124.8737
| 9076 | 138.3184
| 9077 | 157.7976
| 9078 | 133.2511
| 9079 | 151.6163
| 9080 | 76.3211
| 9081 | 112.7011
| 9082 | 123.3122
| 9083 | 95.4545
| 9084 | 75.6541
| 9085 | 186.9122
| 9086 | 119.8237
| 9087 | 160.7181
| 9088 | 170.5571
| 9089 | 71.6484
| 9090 | 156.4156
| 9091 | 169.2947
| 9092 | 168.9241
| 9093 | 128.8978
| 9094 | 174.7264
| 9095 | 133.5432
| 9096 | 173.073
| 9097 | 189.1629
| 9098 | 111.0796
| 9099 | 130.2704
| 9100 | 123
| 9101 | 131.7538
| 9102 | 110.893
| 9103 | 149.6934
| 9104 | 119.8486
| 9105 | 123.425
| 9106 | 118.0883
| 9107 | 126.6545
| 9108 | 106.9934
| 9109 | 96.2505
| 9110 | 115.7171
| 9111 | 148.6441
| 9112 | 174.7698
| 9113 | 107.3472
| 9114 | 143.7079
| 9115 | 117.9595
| 9116 | 74.7689
| 9117 | 124.3034
| 9118 | 187.8026
| 9119 | 115.9939
| 9120 | 92.8167
| 9121 | 100.1921
| 9122 | 82.3015
| 9123 | 116.8101
| 9124 | 109.4704
| 9125 | 88.5981
| 9126 | 101.1142
| 9127 | 117.5577
| 9128 | 180.711
| 9129 | 93.3451
| 9130 | 139.8287
| 9131 | 94.2028
| 9132 | 90.0182
| 9133 | 154.2263
| 9134 | 127.3695
| 9135 | 131.6156
| 9136 | 87.9129
| 9137 | 83.9576
| 9138 | 96.1938
| 9139 | 113.8483
| 9140 | 158.8537
| 9141 | 94.6158
| 9142 | 160.1211
| 9143 | 94.5318
| 9144 | 140.2989
| 9145 | 111.8054
| 9146 | 152.8266
| 9147 | 85.3706
| 9148 | 97.6489
| 9149 | 154.531
| 9150 | 153.4184
| 9151 | 108.8934
| 9152 | 159.1689
| 9153 | 105.5218
| 9154 | 102.0497
| 9155 | 138.1227
| 9156 | 172.6928
| 9157 | 102.7949
| 9158 | 147.2431
| 9159 | 192.3372
| 9160 | 171.0153
| 9161 | 174.645
| 9162 | 135.7087
| 9163 | 132.8705
| 9164 | 181.2131
| 9165 | 104.7839
| 9166 | 151.5215
| 9167 | 135.7915
| 9168 | 122.1015
| 9169 | 89.4651
| 9170 | 167.3742
| 9171 | 201.4839
| 9172 | 96.4244
| 9173 | 182.1859
| 9174 | 129.3371
| 9175 | 130.0328
| 9176 | 151.8376
| 9177 | 84.1406
| 9178 | 175.242
| 9179 | 116.1518
| 9180 | 120.2637
| 9181 | 154.5518
| 9182 | 116.8148
| 9183 | 101.8217
| 9184 | 90.1787
| 9185 | 113.4219
| 9186 | 184.2244
| 9187 | 153.3852
| 9188 | 88.0545
| 9189 | 106.7735
| 9190 | 83.9214
| 9191 | 89.9965
| 9192 | 110.351
| 9193 | 111.5127
| 9194 | 115.4473
| 9195 | 92.4565
| 9196 | 133.8501
| 9197 | 161.941
| 9198 | 133.2252
| 9199 | 86.6375
| 9200 | 82.0585
| 9201 | 128.506
| 9202 | 138.7867
| 9203 | 86.9074
| 9204 | 194.887
| 9205 | 132.8021
| 9206 | 102.6662
| 9207 | 106.291
| 9208 | 131.9301
| 9209 | 181.7531
| 9210 | 173.0323
| 9211 | 77.1041
| 9212 | 116.2408
| 9213 | 182.3101
| 9214 | 128.1893
| 9215 | 173.4917
| 9216 | 207.9955
| 9217 | 152.3051
| 9218 | 164.4095
| 9219 | 163.5877
| 9220 | 133.7205
| 9221 | 92.1455
| 9222 | 84.7116
| 9223 | 134.0886
| 9224 | 153.8765
| 9225 | 147.8274
| 9226 | 153.6129
| 9227 | 126.9451
| 9228 | 155.3854
| 9229 | 128.6242
| 9230 | 164.9625
| 9231 | 166.0969
| 9232 | 106.6802
| 9233 | 132.6774
| 9234 | 77.8069
| 9235 | 175.5501
| 9236 | 93.9784
| 9237 | 120.4982
| 9238 | 140.4197
| 9239 | 121.4226
| 9240 | 83.296
| 9241 | 117.9418
| 9242 | 135.9007
| 9243 | 183.4447
| 9244 | 109.3676
| 9245 | 138.2382
| 9246 | 101.9743
| 9247 | 125.0115
| 9248 | 118.7765
| 9249 | 82.9039
| 9250 | 121.0342
| 9251 | 117.1549
| 9252 | 114.6709
| 9253 | 96.8769
| 9254 | 144.6104
| 9255 | 163.7536
| 9256 | 167.2297
| 9257 | 202.8932
| 9258 | 95.3072
| 9259 | 84.4838
| 9260 | 131.1004
| 9261 | 150.6085
| 9262 | 88.0248
| 9263 | 71.1
| 9264 | 138.621
| 9265 | 146.0118
| 9266 | 143.6931
| 9267 | 144.2495
| 9268 | 137.6861
| 9269 | 79.699
| 9270 | 177.8538
| 9271 | 116.7751
| 9272 | 126.0509
| 9273 | 114.9373
| 9274 | 91.9529
| 9275 | 130.7028
| 9276 | 96.9621
| 9277 | 120.6046
| 9278 | 160.9996
| 9279 | 82.6596
| 9280 | 126.4831
| 9281 | 153.9693
| 9282 | 111.0024
| 9283 | 141.5589
| 9284 | 149.9128
| 9285 | 121.1754
| 9286 | 135.5234
| 9287 | 103.236
| 9288 | 98.572
| 9289 | 103.1249
| 9290 | 91.1867
| 9291 | 115.7971
| 9292 | 168.113
| 9293 | 145.1362
| 9294 | 150.4377
| 9295 | 160.7959
| 9296 | 146.7071
| 9297 | 160.7995
| 9298 | 185.4488
| 9299 | 121.4518
| 9300 | 190.4015
| 9301 | 69.1946
| 9302 | 70.8657
| 9303 | 191.236
| 9304 | 88.958
| 9305 | 107.6402
| 9306 | 111.6154
| 9307 | 122.4815
| 9308 | 161.656
| 9309 | 128.3738
| 9310 | 117.9086
| 9311 | 128.497
| 9312 | 153.6164
| 9313 | 140.7587
| 9314 | 117.4644
| 9315 | 136.5237
| 9316 | 111.4522
| 9317 | 115.1358
| 9318 | 100.401
| 9319 | 115.3591
| 9320 | 159.8938
| 9321 | 135.3134
| 9322 | 112.3382
| 9323 | 94.3341
| 9324 | 210.868
| 9325 | 139.7697
| 9326 | 168.7358
| 9327 | 161.3486
| 9328 | 114.8999
| 9329 | 112.4588
| 9330 | 205.7545
| 9331 | 178.4791
| 9332 | 135.4667
| 9333 | 109.6874
| 9334 | 114.0447
| 9335 | 142.7476
| 9336 | 149.5387
| 9337 | 136.8053
| 9338 | 157.0831
| 9339 | 140.1373
| 9340 | 116.0721
| 9341 | 187.8946
| 9342 | 160.1559
| 9343 | 141.8419
| 9344 | 124.1924
| 9345 | 116.1252
| 9346 | 107.8422
| 9347 | 181.6417
| 9348 | 91.0682
| 9349 | 144.7194
| 9350 | 144.4935
| 9351 | 95.1927
| 9352 | 140.7774
| 9353 | 113.8054
| 9354 | 139.8969
| 9355 | 132.2478
| 9356 | 169.6113
| 9357 | 125.5271
| 9358 | 127.0414
| 9359 | 86.5057
| 9360 | 97.5309
| 9361 | 140.9879
| 9362 | 222.76
| 9363 | 110.2703
| 9364 | 104.8812
| 9365 | 160.1523
| 9366 | 121.7005
| 9367 | 122.7517
| 9368 | 166.9621
| 9369 | 117.2412
| 9370 | 139.932
| 9371 | 101.7921
| 9372 | 125.3529
| 9373 | 116.1898
| 9374 | 97.2971
| 9375 | 202.3086
| 9376 | 101.0127
| 9377 | 141.4006
| 9378 | 127.9713
| 9379 | 151.0098
| 9380 | 144.0741
| 9381 | 192.4447
| 9382 | 97.5701
| 9383 | 79.1786
| 9384 | 110.5108
| 9385 | 180.1341
| 9386 | 144.1132
| 9387 | 141.3095
| 9388 | 118.6334
| 9389 | 107.1631
| 9390 | 96.127
| 9391 | 110.294
| 9392 | 74.7364
| 9393 | 68.0319
| 9394 | 161.4782
| 9395 | 94.0769
| 9396 | 128.9266
| 9397 | 102.8714
| 9398 | 80.919
| 9399 | 121.1304
| 9400 | 98.872
| 9401 | 81.0378
| 9402 | 113.4116
| 9403 | 97.5401
| 9404 | 193.0664
| 9405 | 163.1188
| 9406 | 138.3966
| 9407 | 83.2368
| 9408 | 167.331
| 9409 | 82.2529
| 9410 | 112.0672
| 9411 | 137.1442
| 9412 | 104.0634
| 9413 | 127.1377
| 9414 | 186.7585
| 9415 | 126.67
| 9416 | 149.1411
| 9417 | 117.9028
| 9418 | 134.4311
| 9419 | 211.3807
| 9420 | 158.3305
| 9421 | 99.1715
| 9422 | 95.3882
| 9423 | 124.62
| 9424 | 165.5754
| 9425 | 166.6873
| 9426 | 146.9749
| 9427 | 80.9018
| 9428 | 128.2006
| 9429 | 98.9797
| 9430 | 104.6473
| 9431 | 166.57
| 9432 | 126.3888
| 9433 | 120.2778
| 9434 | 123.1283
| 9435 | 95.7058
| 9436 | 170.3444
| 9437 | 107.7742
| 9438 | 100.7167
| 9439 | 120.8025
| 9440 | 101.7992
| 9441 | 85.0431
| 9442 | 99.2043
| 9443 | 124.9638
| 9444 | 121.3051
| 9445 | 111.3462
| 9446 | 207.0905
| 9447 | 158.4088
| 9448 | 164.0327
| 9449 | 131.6096
| 9450 | 102.4659
| 9451 | 166.2938
| 9452 | 170.6759
| 9453 | 102.2261
| 9454 | 150.9357
| 9455 | 145.2322
| 9456 | 112.1728
| 9457 | 132.4451
| 9458 | 138.9338
| 9459 | 161.2018
| 9460 | 175.2901
| 9461 | 104.4427
| 9462 | 132.1748
| 9463 | 85.1665
| 9464 | 194.0252
| 9465 | 83.6593
| 9466 | 119.7542
| 9467 | 122.5428
| 9468 | 101.728
| 9469 | 155.7987
| 9470 | 184.2385
| 9471 | 124.3897
| 9472 | 88.5709
| 9473 | 143.1009
| 9474 | 173.648
| 9475 | 168.9738
| 9476 | 113.8534
| 9477 | 94.7727
| 9478 | 189.2132
| 9479 | 104.682
| 9480 | 133.5375
| 9481 | 202.5029
| 9482 | 130.1492
| 9483 | 161.8559
| 9484 | 120.1563
| 9485 | 173.7201
| 9486 | 165.6947
| 9487 | 103.4539
| 9488 | 87.12
| 9489 | 107.261
| 9490 | 165.416
| 9491 | 154.4209
| 9492 | 72.8617
| 9493 | 117.6545
| 9494 | 168.3538
| 9495 | 115.0453
| 9496 | 126.8203
| 9497 | 110.4252
| 9498 | 162.7724
| 9499 | 155.4981
| 9500 | 110.3776
| 9501 | 84.8411
| 9502 | 143.429
| 9503 | 172.2375
| 9504 | 74.2523
| 9505 | 132.4098
| 9506 | 135.1634
| 9507 | 96.669
| 9508 | 77.1704
| 9509 | 111.5032
| 9510 | 102.1341
| 9511 | 126.7612
| 9512 | 141.2734
| 9513 | 82.7967
| 9514 | 121.5017
| 9515 | 123.9917
| 9516 | 82.4493
| 9517 | 113.1472
| 9518 | 198.3203
| 9519 | 120.1306
| 9520 | 111.6559
| 9521 | 157.6936
| 9522 | 138.4208
| 9523 | 154.529
| 9524 | 102.1187
| 9525 | 123.611
| 9526 | 161.1374
| 9527 | 124.4892
| 9528 | 183.746
| 9529 | 93.6628
| 9530 | 205.1898
| 9531 | 123.7103
| 9532 | 125.4047
| 9533 | 78.8195
| 9534 | 188.5985
| 9535 | 99.2048
| 9536 | 137.0181
| 9537 | 138.8167
| 9538 | 133.4405
| 9539 | 171.8103
| 9540 | 124.0049
| 9541 | 166.2586
| 9542 | 121.3705
| 9543 | 168.6682
| 9544 | 113.9771
| 9545 | 75.2534
| 9546 | 104.4353
| 9547 | 101.2786
| 9548 | 76.7159
| 9549 | 129.6459
| 9550 | 128.3918
| 9551 | 99.5069
| 9552 | 150.7357
| 9553 | 126.3002
| 9554 | 186.8417
| 9555 | 101.4996
| 9556 | 146.2565
| 9557 | 82.3212
| 9558 | 104.2757
| 9559 | 177.7749
| 9560 | 111.2312
| 9561 | 115.7494
| 9562 | 142.6345
| 9563 | 81.6134
| 9564 | 119.2213
| 9565 | 63.8073
| 9566 | 117.5318
| 9567 | 107.6023
| 9568 | 121.2841
| 9569 | 138.5071
| 9570 | 111.6367
| 9571 | 111.7145
| 9572 | 131.9162
| 9573 | 107.13
| 9574 | 118.4855
| 9575 | 68.6944
| 9576 | 185.6705
| 9577 | 129.6888
| 9578 | 112.381
| 9579 | 141.46
| 9580 | 134.0434
| 9581 | 160.4635
| 9582 | 88.3119
| 9583 | 112.4955
| 9584 | 159.0427
| 9585 | 68.9589
| 9586 | 139.1745
| 9587 | 179.6778
| 9588 | 141.2362
| 9589 | 102.4074
| 9590 | 128.9715
| 9591 | 109.2919
| 9592 | 85.6465
| 9593 | 142.9899
| 9594 | 127.5384
| 9595 | 100.8251
| 9596 | 103.9154
| 9597 | 118.6612
| 9598 | 136.4453
| 9599 | 103.4398
| 9600 | 126.8107
| 9601 | 148.2912
| 9602 | 160.9165
| 9603 | 121.2819
| 9604 | 169.3411
| 9605 | 116.2258
| 9606 | 121.1367
| 9607 | 148.0647
| 9608 | 132.251
| 9609 | 127.6469
| 9610 | 98.0361
| 9611 | 84.1885
| 9612 | 101.9236
| 9613 | 112.9165
| 9614 | 137.9905
| 9615 | 129.9358
| 9616 | 186.2687
| 9617 | 155.0456
| 9618 | 201.3908
| 9619 | 127.2716
| 9620 | 122.4268
| 9621 | 117.182
| 9622 | 111.0845
| 9623 | 93.1198
| 9624 | 169.3683
| 9625 | 132.9671
| 9626 | 117.9165
| 9627 | 185.8605
| 9628 | 113.0178
| 9629 | 128.4746
| 9630 | 84.6577
| 9631 | 111.1286
| 9632 | 95.4404
| 9633 | 161.3641
| 9634 | 119.9908
| 9635 | 160.6032
| 9636 | 112.2435
| 9637 | 125.7533
| 9638 | 176.4183
| 9639 | 171.9449
| 9640 | 100.5755
| 9641 | 204.5348
| 9642 | 157.7441
| 9643 | 105.917
| 9644 | 133.5063
| 9645 | 141.6497
| 9646 | 127.4081
| 9647 | 107.1309
| 9648 | 169.9275
| 9649 | 188.9442
| 9650 | 189.9483
| 9651 | 121.5729
| 9652 | 99.5004
| 9653 | 114.3687
| 9654 | 110.8013
| 9655 | 92.4931
| 9656 | 71.073
| 9657 | 119.2582
| 9658 | 142.5511
| 9659 | 114.774
| 9660 | 94.9079
| 9661 | 168.2295
| 9662 | 163.9332
| 9663 | 84.4909
| 9664 | 125.6249
| 9665 | 92.007
| 9666 | 99.253
| 9667 | 174.8742
| 9668 | 95.8884
| 9669 | 125.8232
| 9670 | 156.6783
| 9671 | 130.7248
| 9672 | 82.7427
| 9673 | 110.3174
| 9674 | 106.1134
| 9675 | 91.0432
| 9676 | 139.2759
| 9677 | 205.5517
| 9678 | 130.1222
| 9679 | 96.6197
| 9680 | 81.0461
| 9681 | 111.9003
| 9682 | 141.4896
| 9683 | 116.9213
| 9684 | 96.9911
| 9685 | 104.6586
| 9686 | 113.4995
| 9687 | 116.826
| 9688 | 105.0826
| 9689 | 95.3032
| 9690 | 91.2153
| 9691 | 173.1018
| 9692 | 125.792
| 9693 | 138.7072
| 9694 | 93.2712
| 9695 | 92.7257
| 9696 | 96.1418
| 9697 | 86.0875
| 9698 | 188.0576
| 9699 | 180.9593
| 9700 | 143.9336
| 9701 | 120.8105
| 9702 | 119.7777
| 9703 | 162.9818
| 9704 | 82.7144
| 9705 | 107.9627
| 9706 | 152.0814
| 9707 | 77.952
| 9708 | 148.3729
| 9709 | 110.9736
| 9710 | 81.1715
| 9711 | 82.2314
| 9712 | 174.5611
| 9713 | 195.7614
| 9714 | 89.9489
| 9715 | 105.7125
| 9716 | 127.4209
| 9717 | 124.4908
| 9718 | 124.9642
| 9719 | 99.7607
| 9720 | 96.4094
| 9721 | 132.1061
| 9722 | 87.5545
| 9723 | 98.9804
| 9724 | 145.3028
| 9725 | 71.0293
| 9726 | 120.7514
| 9727 | 99.9113
| 9728 | 154.1468
| 9729 | 138.0625
| 9730 | 142.7601
| 9731 | 117.8899
| 9732 | 73.6461
| 9733 | 154.887
| 9734 | 159.2582
| 9735 | 214.8664
| 9736 | 110.3746
| 9737 | 113.1263
| 9738 | 129.1385
| 9739 | 187.6315
| 9740 | 111.309
| 9741 | 79.9453
| 9742 | 148.4321
| 9743 | 103.732
| 9744 | 144.0904
| 9745 | 83.8654
| 9746 | 108.9844
| 9747 | 169.5297
| 9748 | 108.2441
| 9749 | 121.5938
| 9750 | 95.5304
| 9751 | 111.1144
| 9752 | 123.1532
| 9753 | 106.3281
| 9754 | 117.2103
| 9755 | 148.6561
| 9756 | 214.1509
| 9757 | 156.2399
| 9758 | 102.3161
| 9759 | 136.7553
| 9760 | 100.2239
| 9761 | 110.011
| 9762 | 106.7525
| 9763 | 146.632
| 9764 | 102.4484
| 9765 | 177.8135
| 9766 | 177.1679
| 9767 | 152.2384
| 9768 | 110.1899
| 9769 | 152.3891
| 9770 | 94.2953
| 9771 | 129.6582
| 9772 | 149.9851
| 9773 | 97.0967
| 9774 | 136.2005
| 9775 | 145.2278
| 9776 | 168.9354
| 9777 | 194.6589
| 9778 | 119.2893
| 9779 | 104.4433
| 9780 | 144.3019
| 9781 | 144.5184
| 9782 | 141.3904
| 9783 | 157.9945
| 9784 | 130.2208
| 9785 | 157.7152
| 9786 | 132.796
| 9787 | 134.3117
| 9788 | 160.0443
| 9789 | 167.015
| 9790 | 107.3275
| 9791 | 75.757
| 9792 | 153.0083
| 9793 | 120.0654
| 9794 | 116.0798
| 9795 | 125.5134
| 9796 | 124.3077
| 9797 | 151.6447
| 9798 | 96.5476
| 9799 | 122.5303
| 9800 | 94.6568
| 9801 | 198.5363
| 9802 | 126.0138
| 9803 | 164.3188
| 9804 | 144.5448
| 9805 | 127.961
| 9806 | 108.7213
| 9807 | 79.4904
| 9808 | 109.4322
| 9809 | 98.9046
| 9810 | 159.0148
| 9811 | 147.8707
| 9812 | 78.4515
| 9813 | 107.0977
| 9814 | 123.8734
| 9815 | 113.199
| 9816 | 133.1443
| 9817 | 97.2524
| 9818 | 157.7443
| 9819 | 95.4269
| 9820 | 138.5522
| 9821 | 188.5875
| 9822 | 159.0712
| 9823 | 191.5015
| 9824 | 110.1071
| 9825 | 124.8336
| 9826 | 108.1931
| 9827 | 95.7179
| 9828 | 70.6424
| 9829 | 162.4238
| 9830 | 116.3159
| 9831 | 129.6105
| 9832 | 99.6239
| 9833 | 99.6384
| 9834 | 153.7137
| 9835 | 136.6139
| 9836 | 151.8398
| 9837 | 157.6644
| 9838 | 163.8627
| 9839 | 72.5905
| 9840 | 125.6644
| 9841 | 158.0258
| 9842 | 108.6841
| 9843 | 71.1453
| 9844 | 139.7096
| 9845 | 104.6397
| 9846 | 138.9346
| 9847 | 134.7454
| 9848 | 136.4021
| 9849 | 112.9684
| 9850 | 112.8179
| 9851 | 157.0786
| 9852 | 172.9009
| 9853 | 95.3758
| 9854 | 128.07
| 9855 | 163.7476
| 9856 | 161.3494
| 9857 | 136.5838
| 9858 | 97.5135
| 9859 | 159.8005
| 9860 | 105.8017
| 9861 | 131.6095
| 9862 | 137.4588
| 9863 | 164.2291
| 9864 | 100.8976
| 9865 | 118.3479
| 9866 | 122.5907
| 9867 | 119.7534
| 9868 | 103.9993
| 9869 | 77.0903
| 9870 | 139.335
| 9871 | 127.6927
| 9872 | 75.2535
| 9873 | 79.0044
| 9874 | 123.9724
| 9875 | 105.2467
| 9876 | 112.0761
| 9877 | 165.6028
| 9878 | 134.7475
| 9879 | 120.1072
| 9880 | 78.7235
| 9881 | 108.3827
| 9882 | 116.8402
| 9883 | 128.6359
| 9884 | 139.1931
| 9885 | 129.6616
| 9886 | 105.8324
| 9887 | 81.7889
| 9888 | 173.9731
| 9889 | 149.1948
| 9890 | 121.5298
| 9891 | 177.266
| 9892 | 163.1475
| 9893 | 105.2091
| 9894 | 112.7958
| 9895 | 73.4709
| 9896 | 114.3863
| 9897 | 134.1646
| 9898 | 100.283
| 9899 | 165.4134
| 9900 | 165.1784
| 9901 | 141.894
| 9902 | 188.9328
| 9903 | 91.2363
| 9904 | 209.0123
| 9905 | 73.6451
| 9906 | 133.5902
| 9907 | 109.4213
| 9908 | 122.5179
| 9909 | 134.2511
| 9910 | 181.478
| 9911 | 139.8222
| 9912 | 98.0775
| 9913 | 146.3131
| 9914 | 108.1384
| 9915 | 165.5732
| 9916 | 106.9011
| 9917 | 163.1376
| 9918 | 134.409
| 9919 | 138.7887
| 9920 | 135.1901
| 9921 | 70.3923
| 9922 | 126.977
| 9923 | 120.3019
| 9924 | 142.4575
| 9925 | 136.9762
| 9926 | 176.9673
| 9927 | 156.2264
| 9928 | 151.6838
| 9929 | 217.5059
| 9930 | 118.9352
| 9931 | 109.9507
| 9932 | 74.6379
| 9933 | 198.8761
| 9934 | 126.3484
| 9935 | 123.6902
| 9936 | 151.8454
| 9937 | 162.898
| 9938 | 141.7661
| 9939 | 82.5412
| 9940 | 157.6861
| 9941 | 138.8827
| 9942 | 122.909
| 9943 | 121.1019
| 9944 | 128.7103
| 9945 | 128.4272
| 9946 | 100.6783
| 9947 | 126.7106
| 9948 | 105.9364
| 9949 | 137.0028
| 9950 | 145.9807
| 9951 | 99.7112
| 9952 | 93.3815
| 9953 | 130.3325
| 9954 | 170.7519
| 9955 | 208.27
| 9956 | 100.6296
| 9957 | 82.2208
| 9958 | 161.2422
| 9959 | 161.4223
| 9960 | 162.6287
| 9961 | 77.1264
| 9962 | 114.2582
| 9963 | 71.9847
| 9964 | 177.9735
| 9965 | 152.642
| 9966 | 182.258
| 9967 | 138.5434
| 9968 | 107.9783
| 9969 | 199.3485
| 9970 | 172.8286
| 9971 | 101.3131
| 9972 | 196.1778
| 9973 | 183.5937
| 9974 | 142.0912
| 9975 | 129.6037
| 9976 | 122.2474
| 9977 | 120.367
| 9978 | 131.964
| 9979 | 125.3483
| 9980 | 77.8835
| 9981 | 79.2937
| 9982 | 116.6425
| 9983 | 170.27
| 9984 | 193.4151
| 9985 | 159.2745
| 9986 | 160.7956
| 9987 | 173.9903
| 9988 | 127.3268
| 9989 | 181.7983
| 9990 | 119.8748
| 9991 | 153.4585
| 9992 | 122.3763
| 9993 | 164.1165
| 9994 | 84.8038
| 9995 | 101.5793
| 9996 | 123.4001
| 9997 | 162.402
| 9998 | 159.9597
| 9999 | 99.721
| 10000 | 102.139
Note on T2: You may optionally enter a planning estimate for each uncertainty you enter, and see its cumulative probability result in the 'SPERT Probability' column. The cumulative probability is the likelihood your planning estimate will be EQUAL TO or GREATER THAN the uncertainty you are estimating. Choosing a larger planning estimate will increase the cumulative probability, and choosing a smaller planning estimate will decrease the cumulative probability.
Note on U2: The SPERT Probability shows the cumulative probability of each Planning Estimate you entered in column R. If you select 'Show Left-Side Area' in cell R1, this column shows the likelihood that your Planning Estimate will be EQUAL TO or GREATER THAN the uncertainty you are estimating. If you select 'Show Right-Side Area' in cell R1, this column shows the likelihood that the uncertainty will EXCEED your Planning Estimate in column R.
Note on B3: The Minimum point-estimate represents the smallest value that is feasible, but highly improbable.
Note on C3: he Most Likely point-estimate represents the value you believe will most likely occur for each uncertainty, although many other possible outcomes exist between the Minimum and Maximum point-estimates.
Note on D3: The Maximum point-estimate represents the largest value that is feasible, but highly improbable
Note on E3: This checks that a proper 3-point estimate was entered: Minimum value must be > 0 and =< Most Likely Most Likely must be >= Minimum and =< Maximum Maximum must be >= Most Likely
Note on K3: The shape of the bell-curve is heavily influenced by how confident you believe the Most Likely outcome will occur relative to other, possible outcomes between the Minimum and Maximum point-estimates. When you are more confident in the Most Likely outcome, the bell-curve grows taller, and there is a shrinking likelihood of other occurrences near the Minimum and Maximum point-estimates. Conversely, when you are less confident in the Most Likely outcome, the bell-curve grows flatter, and there is a rising likelihood of other occurrences near the Minimum and Maximum point-estimates. (You can add to, remove, or modify the dropdown control options using the VLookups worksheet).
Note on S3: The trial outcome is used to build a data table of 10,000 trials
Note on B9: On the Formulas menu, under the Calculation group, press the Calculation Options button and select "Automatic Except for Data Tables" to increase the speed and performance of all Excel spreadsheets. This is an application-level setting change.
Click for help
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## SPERT® Beta - Agile Forecast
Statistical PERT® (SPERT®) Beta Edition Agile Forecast
| Scenario 1 |  | Scenario 2 |  | Scenario 3 | For Scenarios 1, 2, and 3, enter input values into all the brighter, yellow-shaded cells; the faded yellow-shaded cells are optional
The starting date for our next release is | 2020-06-01 | 2020-06-02 | 2020-06-01 |  | 2020-06-01
We'll use | 2 | 2 | 2 |  | 2 | week iterations or sprints
We'll most likely complete about | 40 | 40 | 40 |  | 40 | story points (or user stories or features) per sprint
We have | Low Confidence | Low Confidence | Medium Confidence |  | High Confidence | that the most likely outcome will regularly occur
In a worst-case scenario, we would complete only | 10 | 10 | 10 |  | 10 | story points (or user stories or features)
In a best-case scenario, we might possibly complete | 70 | 70 | 70 |  | 70 | story points (or user stories or features)
| 1 |  | 1 |  | 1 | Be sure there is a green checkmark; otherwise, check your 3-point estimate for correctness
Our Product Backlog or next release represents about | 255 |  | 255 |  | 255 | story points of effort (or user stories or features)
We desire | 80% |  | 80% |  | 80% | confidence in each sprint iteration
| No skew |  | No skew |  | No skew
| 50 |  | 50 |  | 50
| EQ |  | EQ |  | EQ
| 1 |  | 1 |  | 1
| 40 |  | 40 |  | 40
| 8 |  | 6 |  | 4
The alpha shape argument is | 2 |  | 4 |  | 7
The beta shape argument is | 2 |  | 4 |  | 7
| Show Right-Side Area |  | Show Right-Side Area |  | Show Right-Side Area
| Do not show currency formatting |  | Do not show currency formatting |  | Do not show currency formatting
The bell-curve distribution looks like this
So, on average, we expect each sprint will finish | 40 |  | 40 |  | 40 | story points (or user stories or features) per sprint
For this uncertainty, the SPERT standard deviation is | 13.416 |  | 10.002 |  | 7.5
Given this, we forecast that we'll complete at least | 27.2284 |  | 31.0056 |  | 33.2201 | story points (or user stories or features) each sprint (for the confidence level expressed in cell C6)
We'll need | 9.3652 |  | 8.2243 |  | 7.6761 | sprints to do all the work of the Product Backlog or the next release
Optional: Choose a rounding decimal between 0.1 and 0.9 | 0.3 |  | 0.3 |  | 0.3 | You can round up or down the number of weeks needed based upon the fractional amount of sprints required
So, we'll need about | 20 |  | 18 |  | 16 | business weeks
Optional: During this time, there is/are | [5 empty] | extra days (working and non-working) to add to the date calculation
In total, the number of days needed are | 140 |  | 126 |  | 112 | which includes both working + non-working days
So, we will complete the Product Backlog or next release by | 2020-10-19 |  | 2020-10-05 |  | 2020-09-21 | © 2015-2020, William W. Davis, MSPM, PMP
Version 3.0.s – © 2015-2020, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Subscribe to the SPERT® newsletter for monthly tips, free webinars, and new release notifications
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).
X-axis increments | 0.6 | X-axis increments | 0.6 | X-axis increments | 0.6 | This, along with the grayed-out table below, is only used to create a Sparkline
10 | 1.6666e-06 | 10 | 1.0802e-14 | 10 | 4.2906e-27
10.6 | 0.00099 | 10.6 | 2.264e-06 | 10.6 | 1.8848e-10
11.2 | 0.00196 | 11.2 | 1.7569e-05 | 11.2 | 1.135e-08
11.8 | 0.00291 | 11.8 | 5.7498e-05 | 11.8 | 1.2157e-07
12.4 | 0.00384 | 12.4 | 0.00013212 | 12.4 | 6.4188e-07
13 | 0.00475 | 13 | 0.00025007 | 13 | 2.2995e-06
13.6 | 0.00564 | 13.6 | 0.00041861 | 13.6 | 6.4438e-06
14.2 | 0.00651 | 14.2 | 0.00064375 | 14.2 | 1.5239e-05
14.8 | 0.00736 | 14.8 | 0.00093027 | 14.8 | 3.1822e-05
15.4 | 0.00819 | 15.4 | 0.0012818 | 15.4 | 6.0418e-05
16 | 0.009 | 16 | 0.001701 | 16 | 0.00010639
16.6 | 0.00979 | 16.6 | 0.0021894 | 16.6 | 0.00017626
17.2 | 0.01056 | 17.2 | 0.0027477 | 17.2 | 0.00027762
17.8 | 0.01131 | 17.8 | 0.0033757 | 17.8 | 0.00041902
18.4 | 0.01204 | 18.4 | 0.0040725 | 18.4 | 0.00060985
19 | 0.01275 | 19 | 0.0048362 | 19 | 0.00086005
19.6 | 0.01344 | 19.6 | 0.0056647 | 19.6 | 0.0011799
20.2 | 0.01411 | 20.2 | 0.0065548 | 20.2 | 0.0015799
20.8 | 0.01476 | 20.8 | 0.007503 | 20.8 | 0.0020701
21.4 | 0.01539 | 21.4 | 0.0085054 | 21.4 | 0.0026601
22 | 0.016 | 22 | 0.0095573 | 22 | 0.0033588
22.6 | 0.01659 | 22.6 | 0.010654 | 22.6 | 0.0041739
23.2 | 0.01716 | 23.2 | 0.01179 | 23.2 | 0.0051117
23.8 | 0.01771 | 23.8 | 0.012961 | 23.8 | 0.006177
24.4 | 0.01824 | 24.4 | 0.01416 | 24.4 | 0.0073725
25 | 0.01875 | 25 | 0.015381 | 25 | 0.008699
25.6 | 0.01924 | 25.6 | 0.016619 | 25.6 | 0.010155
26.2 | 0.01971 | 26.2 | 0.017866 | 26.2 | 0.011738
26.8 | 0.02016 | 26.8 | 0.019118 | 26.8 | 0.01344
27.4 | 0.02059 | 27.4 | 0.020368 | 27.4 | 0.015255
28 | 0.021 | 28 | 0.021609 | 28 | 0.01717
28.6 | 0.02139 | 28.6 | 0.022835 | 28.6 | 0.019175
29.2 | 0.02176 | 29.2 | 0.024041 | 29.2 | 0.021253
29.8 | 0.02211 | 29.8 | 0.02522 | 29.8 | 0.023388
30.4 | 0.02244 | 30.4 | 0.026366 | 30.4 | 0.025562
31 | 0.02275 | 31 | 0.027474 | 31 | 0.027756
31.6 | 0.02304 | 31.6 | 0.028538 | 31.6 | 0.029947
32.2 | 0.02331 | 32.2 | 0.029553 | 32.2 | 0.032116
32.8 | 0.02356 | 32.8 | 0.030514 | 32.8 | 0.034239
33.4 | 0.02379 | 33.4 | 0.031417 | 33.4 | 0.036294
34 | 0.024 | 34 | 0.032256 | 34 | 0.038259
34.6 | 0.02419 | 34.6 | 0.033028 | 34.6 | 0.040112
35.2 | 0.02436 | 35.2 | 0.033729 | 35.2 | 0.041834
35.8 | 0.02451 | 35.8 | 0.034356 | 35.8 | 0.043403
36.4 | 0.02464 | 36.4 | 0.034906 | 36.4 | 0.044803
37 | 0.02475 | 37 | 0.035375 | 37 | 0.046017
37.6 | 0.02484 | 37.6 | 0.035763 | 37.6 | 0.04703
38.2 | 0.02491 | 38.2 | 0.036066 | 38.2 | 0.047831
38.8 | 0.02496 | 38.8 | 0.036284 | 38.8 | 0.04841
39.4 | 0.02499 | 39.4 | 0.036415 | 39.4 | 0.04876
40 | 0.025 | 40 | 0.036458 | 40 | 0.048877
40.6 | 0.02499 | 40.6 | 0.036415 | 40.6 | 0.04876
41.2 | 0.02496 | 41.2 | 0.036284 | 41.2 | 0.04841
41.8 | 0.02491 | 41.8 | 0.036066 | 41.8 | 0.047831
42.4 | 0.02484 | 42.4 | 0.035763 | 42.4 | 0.04703
43 | 0.02475 | 43 | 0.035375 | 43 | 0.046017
43.6 | 0.02464 | 43.6 | 0.034906 | 43.6 | 0.044803
44.2 | 0.02451 | 44.2 | 0.034356 | 44.2 | 0.043403
44.8 | 0.02436 | 44.8 | 0.033729 | 44.8 | 0.041834
45.4 | 0.02419 | 45.4 | 0.033028 | 45.4 | 0.040112
46 | 0.024 | 46 | 0.032256 | 46 | 0.038259
46.6 | 0.02379 | 46.6 | 0.031417 | 46.6 | 0.036294
47.2 | 0.02356 | 47.2 | 0.030514 | 47.2 | 0.034239
47.8 | 0.02331 | 47.8 | 0.029553 | 47.8 | 0.032116
48.4 | 0.02304 | 48.4 | 0.028538 | 48.4 | 0.029947
49 | 0.02275 | 49 | 0.027474 | 49 | 0.027756
49.6 | 0.02244 | 49.6 | 0.026366 | 49.6 | 0.025562
50.2 | 0.02211 | 50.2 | 0.02522 | 50.2 | 0.023388
50.8 | 0.02176 | 50.8 | 0.024041 | 50.8 | 0.021253
51.4 | 0.02139 | 51.4 | 0.022835 | 51.4 | 0.019175
52 | 0.021 | 52 | 0.021609 | 52 | 0.01717
52.6 | 0.02059 | 52.6 | 0.020368 | 52.6 | 0.015255
53.2 | 0.02016 | 53.2 | 0.019118 | 53.2 | 0.01344
53.8 | 0.01971 | 53.8 | 0.017866 | 53.8 | 0.011738
54.4 | 0.01924 | 54.4 | 0.016619 | 54.4 | 0.010155
55 | 0.01875 | 55 | 0.015381 | 55 | 0.008699
55.6 | 0.01824 | 55.6 | 0.01416 | 55.6 | 0.0073725
56.2 | 0.01771 | 56.2 | 0.012961 | 56.2 | 0.006177
56.8 | 0.01716 | 56.8 | 0.01179 | 56.8 | 0.0051117
57.4 | 0.01659 | 57.4 | 0.010654 | 57.4 | 0.0041739
58 | 0.016 | 58 | 0.0095573 | 58 | 0.0033588
58.6 | 0.01539 | 58.6 | 0.0085054 | 58.6 | 0.0026601
59.2 | 0.01476 | 59.2 | 0.007503 | 59.2 | 0.0020701
59.8 | 0.01411 | 59.8 | 0.0065548 | 59.8 | 0.0015799
60.4 | 0.01344 | 60.4 | 0.0056647 | 60.4 | 0.0011799
61 | 0.01275 | 61 | 0.0048362 | 61 | 0.00086005
61.6 | 0.01204 | 61.6 | 0.0040725 | 61.6 | 0.00060985
62.2 | 0.01131 | 62.2 | 0.0033757 | 62.2 | 0.00041902
62.8 | 0.01056 | 62.8 | 0.0027477 | 62.8 | 0.00027762
63.4 | 0.00979 | 63.4 | 0.0021894 | 63.4 | 0.00017626
64 | 0.009 | 64 | 0.001701 | 64 | 0.00010639
64.6 | 0.00819 | 64.6 | 0.0012818 | 64.6 | 6.0418e-05
65.2 | 0.00736 | 65.2 | 0.00093027 | 65.2 | 3.1822e-05
65.8 | 0.00651 | 65.8 | 0.00064375 | 65.8 | 1.5239e-05
66.4 | 0.00564 | 66.4 | 0.00041861 | 66.4 | 6.4438e-06
67 | 0.00475 | 67 | 0.00025007 | 67 | 2.2995e-06
67.6 | 0.00384 | 67.6 | 0.00013212 | 67.6 | 6.4188e-07
68.2 | 0.00291 | 68.2 | 5.7498e-05 | 68.2 | 1.2157e-07
68.8 | 0.00196 | 68.8 | 1.7569e-05 | 68.8 | 1.135e-08
69.4 | 0.00099 | 69.4 | 2.264e-06 | 69.4 | 1.8848e-10
70 | 1.6666e-06 | 70 | 1.0802e-14 | 70 | 4.2906e-27
↑ Rows 61 through 163 are hidden; they are used to create the bell-curve Sparkline
Formulas:
Scenario 1 = IF(OR(C3="",[Scenario 1, row above]=""),"",C3+[Scenario 1, row above])
Scenario 2 = IF(OR(E3="",[Scenario 2, row above]=""),"",E3+[Scenario 2, row above])
Scenario 3 = IF(OR(G3="",[Scenario 3, row above]=""),"",G3+[Scenario 3, row above])
Click for help

## Skew
Statistical PERT® (SPERT®) Beta Edition List of Skew Analysis Categories
No skew | 50 | 45.8335
Very slight skew | 45.8335 | 37.5005
Slight skew | 37.5005 | 31.2505
Very low skew | 31.2505 | 27.0835
Low skew | 27.0835 | 23.75
Medium-low skew | 23.75 | 21.25
Medium skew | 21.25 | 19.1668
Medium-high skew | 19.1668 | 17.5003
High skew | 17.5003 | 15.6253
Very high skew | 15.6253 | 13.5418
Severe skew | 13.5418 | 11.875
Very severe skew | 11.875 | 10.625
Extremely severe skew | 10.625 | 8
Near Triangular | 8 | 4
Triangular | 4 | 0
© 2015-2020, William W. Davis, MSPM, PMP
Version 3.0.s – © 2015-2020, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Subscribe to the SPERT® newsletter for monthly tips, free webinars, and new release notifications
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).

## Confidence
Statistical PERT® (SPERT®) Beta Edition List of Most Likely Confidence Judgments
Near Certainty
Extremely High Confidence
Very High Confidence
High Confidence
Medium-High Confidence
Medium Confidence
Medium-Low Confidence
Low Confidence
Very Low Confidence
Guesstimate
© 2015-2020, William W. Davis, MSPM, PMP
Version 3.0.s – © 2015-2020, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Subscribe to the SPERT® newsletter for monthly tips, free webinars, and new release notifications
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).

## Alpha-Beta
Statistical PERT® (SPERT®) Beta Edition List of Alpha and Beta Function Arguments
ALPHA |  | Near Certainty | Extremely High | Very High | High | Medium-High | Medium | Medium-Low | Low | Very Low | Guesstimate
| No skew | 25 | 15 | 10 | 7 | 5 | 4 | 3 | 2 | 1.5 | 1.25
| Very slight skew | 19 | 11.5 | 7.75 | 5.5 | 4 | 3.25 | 2.5 | 1.75 | 1.375 | 1.1875
| Slight skew | 13 | 8 | 5.5 | 4 | 3 | 2.5 | 2 | 1.5 | 1.25 | 1.125
| Very low skew | 11 | 6.835 | 4.75 | 3.5 | 2.675 | 2.25 | 1.835 | 1.415 | 1.21 | 1.104
| Low skew | 9 | 5.67 | 4 | 3 | 2.35 | 2 | 1.67 | 1.33 | 1.17 | 1.083
| Medium-low skew | 8 | 5.085 | 3.625 | 2.75 | 2.175 | 1.875 | 1.585 | 1.29 | 1.1475 | 1.0728
| Medium skew | 7 | 4.5 | 3.25 | 2.5 | 2 | 1.75 | 1.5 | 1.25 | 1.125 | 1.0625
| Medium-high skew | 6.4 | 4.15 | 3.025 | 2.35 | 1.9 | 1.675 | 1.45 | 1.225 | 1.1125 | 1.0562
| High skew | 5.8 | 3.8 | 2.8 | 2.2 | 1.8 | 1.6 | 1.4 | 1.2 | 1.1 | 1.05
| Very high skew | 5.115 | 3.4 | 2.5425 | 2.0285 | 1.6875 | 1.5125 | 1.3425 | 1.1725 | 1.085 | 1.0425
| Severe skew | 4.43 | 3 | 2.285 | 1.857 | 1.575 | 1.425 | 1.285 | 1.145 | 1.07 | 1.035
| Very severe skew | 4.05 | 2.78 | 2.1425 | 1.762 | 1.5125 | 1.375 | 1.255 | 1.1275 | 1.0625 | 1.03
| Extremely severe skew | 3.67 | 2.56 | 2 | 1.667 | 1.45 | 1.325 | 1.225 | 1.11 | 1.055 | 1.025
| Near Triangular | 2.335 | 1.78 | 1.5 | 1.3335 | 1.225 | 1.1625 | 1.1125 | 1.055 | 1.0275 | 1.0125
| Triangular | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
BETA |  | Near Certainty | Extremely High | Very High | High | Medium-High | Medium | Medium-Low | Low | Very Low | Guesstimate
| No skew | 25 | 15 | 10 | 7 | 5 | 4 | 3 | 2 | 1.5 | 1.25
| Very slight skew | 25 | 15 | 10 | 7 | 5 | 4 | 3 | 2 | 1.5 | 1.25
| Slight skew | 25 | 15 | 10 | 7 | 5 | 4 | 3 | 2 | 1.5 | 1.25
| Very low skew | 25 | 15 | 10 | 7 | 5 | 4 | 3 | 2 | 1.5 | 1.25
| Low skew | 25 | 15 | 10 | 7 | 5 | 4 | 3 | 2 | 1.5 | 1.25
| Medium-low skew | 25 | 15 | 10 | 7 | 5 | 4 | 3 | 2 | 1.5 | 1.25
| Medium skew | 25 | 15 | 10 | 7 | 5 | 4 | 3 | 2 | 1.5 | 1.25
| Medium-high skew | 25 | 15 | 10 | 7 | 5 | 4 | 3 | 2 | 1.5 | 1.25
| High skew | 25 | 15 | 10 | 7 | 5 | 4 | 3 | 2 | 1.5 | 1.25
| Very high skew | 25 | 15 | 10 | 7 | 5 | 4 | 3 | 2 | 1.5 | 1.25
| Severe skew | 25 | 15 | 10 | 7 | 5 | 4 | 3 | 2 | 1.5 | 1.25
| Very severe skew | 25 | 15 | 10 | 7 | 5 | 4 | 3 | 2 | 1.5 | 1.25
| Extremely severe skew | 25 | 15 | 10 | 7 | 5 | 4 | 3 | 2 | 1.5 | 1.25
| Near Triangular | 25 | 15 | 10 | 7 | 5 | 4 | 3 | 2 | 1.5 | 1.25
| Triangular | 25 | 15 | 10 | 7 | 5 | 4 | 3 | 2 | 1.5 | 1.25
© 2015-2020, William W. Davis, MSPM, PMP
Version 3.0.s – © 2015-2020, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Subscribe to the SPERT® newsletter for monthly tips, free webinars, and new release notifications
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).

## Standard Deviation Ratios
Statistical PERT® (SPERT®) Beta Edition List of Standard Deviation Ratios
| Near Certainty | Extremely High | Very High | High | Medium-High | Medium | Medium-Low | Low | Very Low | Guesstimate
No skew | 0.07 | 0.0898 | 0.1091 | 0.125 | 0.1508 | 0.1667 | 0.189 | 0.2236 | 0.25 | 0.2673
Very slight skew | 0.073 | 0.0935 | 0.11345 | 0.13195 | 0.1561 | 0.17215 | 0.1945 | 0.22845 | 0.25355 | 0.26955
Slight skew | 0.076 | 0.0972 | 0.1178 | 0.1389 | 0.1614 | 0.1776 | 0.2 | 0.2333 | 0.2571 | 0.2718
Very low skew | 0.0753 | 0.0965 | 0.1172 | 0.13855 | 0.1614 | 0.1779 | 0.20065 | 0.23435 | 0.258 | 0.2725
Low skew | 0.0746 | 0.0958 | 0.1166 | 0.1382 | 0.1614 | 0.1782 | 0.2013 | 0.2354 | 0.2589 | 0.2732
Medium-low skew | 0.0733 | 0.09445 | 0.1153 | 0.13705 | 0.16055 | 0.17765 | 0.20115 | 0.2357 | 0.2594 | 0.2735
Medium skew | 0.072 | 0.0931 | 0.114 | 0.1359 | 0.1597 | 0.1771 | 0.201 | 0.236 | 0.2599 | 0.2738
Medium-high skew | 0.07065 | 0.0917 | 0.11265 | 0.13475 | 0.15885 | 0.17645 | 0.2007 | 0.2361 | 0.26015 | 0.274
High skew | 0.0693 | 0.0903 | 0.1113 | 0.1336 | 0.158 | 0.1758 | 0.2004 | 0.2362 | 0.2604 | 0.2742
Very high skew | 0.06705 | 0.0879 | 0.10905 | 0.13165 | 0.15655 | 0.1747 | 0.19985 | 0.23625 | 0.26065 | 0.2744
Severe skew | 0.0648 | 0.0855 | 0.1068 | 0.1297 | 0.1551 | 0.1736 | 0.1993 | 0.2363 | 0.2609 | 0.2746
Very severe skew | 0.06305 | 0.08375 | 0.1051 | 0.12825 | 0.154 | 0.17275 | 0.1989 | 0.2363 | 0.261 | 0.27475
Extremely severe skew | 0.0613 | 0.082 | 0.1034 | 0.1268 | 0.1529 | 0.1719 | 0.1985 | 0.2363 | 0.2611 | 0.2749
Near Triangular | 0.04915 | 0.07035 | 0.0932 | 0.1185 | 0.1469 | 0.1676 | 0.19605 | 0.236 | 0.2615 | 0.27525
Triangular | 0.037 | 0.0587 | 0.083 | 0.1102 | 0.1409 | 0.1633 | 0.1936 | 0.2357 | 0.2619 | 0.2756
© 2015-2020, William W. Davis, MSPM, PMP
Version 3.0.s – © 2015-2020, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Subscribe to the SPERT® newsletter for monthly tips, free webinars, and new release notifications
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).

## Mean Ratios
Statistical PERT® (SPERT®) Beta Edition List of Mean Ratios
| Near Certainty | Extremely High | Very High | High | Medium-High | Medium | Medium-Low | Low | Very Low | Guesstimate
No skew | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Very slight skew | 0.42105 | 0.4239 | 0.4274 | 0.4318 | 0.4375 | 0.4423 | 0.45 | 0.46425 | 0.47725 | 0.4868
Slight skew | 0.3421 | 0.3478 | 0.3548 | 0.3636 | 0.375 | 0.3846 | 0.4 | 0.4285 | 0.4545 | 0.4736
Very low skew | 0.3034 | 0.31105 | 0.32025 | 0.3318 | 0.34735 | 0.35895 | 0.3788 | 0.4139 | 0.44635 | 0.4689
Low skew | 0.2647 | 0.2743 | 0.2857 | 0.3 | 0.3197 | 0.3333 | 0.3576 | 0.3993 | 0.4382 | 0.4642
Medium-low skew | 0.24175 | 0.25255 | 0.2655 | 0.2816 | 0.3027 | 0.3188 | 0.34545 | 0.39195 | 0.43335 | 0.4618
Medium skew | 0.2188 | 0.2308 | 0.2453 | 0.2632 | 0.2857 | 0.3043 | 0.3333 | 0.3846 | 0.4285 | 0.4594
Medium-high skew | 0.20355 | 0.21645 | 0.23205 | 0.25115 | 0.2752 | 0.295 | 0.3257 | 0.3798 | 0.42575 | 0.45795
High skew | 0.1883 | 0.2021 | 0.2188 | 0.2391 | 0.2647 | 0.2857 | 0.3181 | 0.375 | 0.423 | 0.4565
Very high skew | 0.1694 | 0.1844 | 0.2024 | 0.2244 | 0.2521 | 0.2742 | 0.29245 | 0.36955 | 0.41965 | 0.45475
Severe skew | 0.1505 | 0.1667 | 0.186 | 0.2097 | 0.2395 | 0.2627 | 0.2668 | 0.3641 | 0.4163 | 0.453
Very severe skew | 0.13925 | 0.15625 | 0.17635 | 0.201 | 0.23215 | 0.25575 | 0.27835 | 0.3605 | 0.4146 | 0.45175
Extremely severe skew | 0.128 | 0.1458 | 0.1667 | 0.1923 | 0.2248 | 0.2488 | 0.2899 | 0.3569 | 0.4129 | 0.4505
Near Triangular | 0.08325 | 0.10415 | 0.1288 | 0.15865 | 0.19575 | 0.2244 | 0.26995 | 0.3451 | 0.40645 | 0.44745
Triangular | 0.0385 | 0.0625 | 0.0909 | 0.125 | 0.1667 | 0.2 | 0.25 | 0.3333 | 0.4 | 0.4444
© 2015-2020, William W. Davis, MSPM, PMP
Version 3.0.s – © 2015-2020, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Subscribe to the SPERT® newsletter for monthly tips, free webinars, and new release notifications
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).

## VLookups
Statistical PERT® (SPERT®) Beta Edition VLOOKUP lists of values
These are the Minimum heuristic percentages used in the 'SPERT Beta (1-Point entry)' and 'SPERT Beta (Mixed entry)' worksheets to create a minimum value for a 3-point estimate. You can add to, remove, or change this list. | -5%
-10%
-15%
-20%
-25%
-30%
-35%
-40%
-50%
-60%
-70%
These are the Maximum heuristic percentages used in the 'SPERT Beta (1-Point entry)' and 'SPERT Beta (Mixed entry)' worksheets to create a maximum value for a 3-point estimate. You can add to, remove, or change this list. | 10%
20%
30%
40%
50%
75%
100%
125%
150%
175%
200%
Choose which side of the probability curve to display
Show Left-Side Area | FALSE | Show the likelihood that the SPERT estimates will be EQUAL TO or GREATER THAN an uncertainty | Show the percentage of simulated trials that were EQUAL TO or LESS THAN the SPERT estimates above
Show Right-Side Area | TRUE | Show the likelihood that an uncertainty will EXCEED the SPERT estimates shown below | Show the percentage of simulated trials that EXCEEDED the SPERT estimates above
Choose whether to show currency formatting
Show currency formatting | TRUE
Do not show currency formatting | FALSE
© 2015-2020, William W. Davis, MSPM, PMP
Version 3.0.s – © 2015-2020, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Subscribe to the SPERT® newsletter for monthly tips, free webinars, and new release notifications
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).

## Collabinart®
Collabinart® Experience Collaboration through Interpretive Art™
At the 2018 PMI Global Conference,
attendees experienced Collabinart®.
Collabinart is a freely-licensed
team-building and training
framework to build collaboration
skills using masterpiece artworks.
Use Collabinart at any point in a
team's journey together. Develop
team camaraderie, active listening
skills, and collaboration skills.
It's fun, free, and effective.
Visit the Collabinart website
to learn more.
The Young Shepherdess (1865)
William-Adolphe Bouguereau
San Diego Museum of Art

## Change Log
Statistical PERT® (SPERT®) Beta Edition Change Log
Date | Version | Description
2020-04-28 | 3.0.s | Minor tweaks to label descriptions and cell heading notes.
2020-04-28 | 3.0.r | Easter egg copyright notification
2020-04-28 | 3.0.q | Update (and in some cases, correct) the cell notes on the Scheduler worksheet.
2020-04-27 | 3.0.p | Added schedule contigency field on Scheduler. Add notes to explain cells in the Scheduler worksheet. Add Parkinson's Law calculation.
2020-04-26 | 3.0.n | Added table to MC tab for incremental probabilities and values. Tweaked VLOOKUP values for MCS. Added MCS compare to SPERT on MCS sheet.
2020-04-26 | 3.0.m | Tweaked MC label for "10,000 trials…". Fixed newsletter footer link.
2020-04-26 | 3.0.k | Added median, mode, and standard deviation summary statistics to the MC Simulation worksheet
2020-04-25 | 3.0.j | Added sum total to theh SPERT Scheduler Duration column.
2020-04-25 | 3.0.i | The SPERT Scheduler is called the "Scheduler & Mixed Entry" worksheet. Minor tweaks
2020-04-25 | 3.0.h | Formatting the new SPERT Scheduler
2020-04-25 | 3.0.g | Converted Mixed Entry to include the new SPERT Scheduler
2020-04-25 | 3.0.f | Updated Welcome! Worksheet.
2020-04-25 | 3.0.e | Finished up MC Sim worksheet and added the README worksheet.
2020-04-25 | 3.0.d | Continue Monte Carlo sim worksheet. Added histogram, made formatting changes, fixed MCS summary stat formulas
2020-04-25 | 3.0.c | Added Monte Carlo worksheet with a data table
2020-04-25 | 3.0.b | Added rounding function on Agile Forecast tab, and modified the label formatting and row heights
2020-04-25 | 3.0.a | Added Scenarios 2 & 3 on the Agile Forecast tab
2020-04-23 | 2.1.1 | Replaced Twitter footer link with a SPERT Newsletter link, other minor changes
2020-02-15 | 2.1 | Added tab headings to tabs that didn't have them. Added "Click for help" buttons and formatting for the VLookups which are user-changeable.
2019-07-13 | 2.0 | Add tri-color combo charts and pie charts, line Sparklines, an Agile Forecast tab (1 scenario only), and minor formatting updates
2019-03-19 | 1.2 | Update the bottom page links, license instructions, and no-warranty disclaimer
2018-09-22 | 1.1 | Update the copyright to use a function
2017-03-01 | 1.0 | Initial release which includes a new Beginners worksheet, and fixes to pie charts linked to the wrong worksheet

## GNU GPL
GNU GENERAL PUBLIC LICENSE
Version 3, 29 June 2007
Copyright (C) 2007 Free Software Foundation, Inc. <https://fsf.org/>
Everyone is permitted to copy and distribute verbatim copies
of this license document, but changing it is not allowed.
Preamble
The GNU General Public License is a free, copyleft license for
software and other kinds of works.
The licenses for most software and other practical works are designed
to take away your freedom to share and change the works. By contrast,
the GNU General Public License is intended to guarantee your freedom to
share and change all versions of a program--to make sure it remains free
software for all its users. We, the Free Software Foundation, use the
GNU General Public License for most of our software; it applies also to
any other work released this way by its authors. You can apply it to
your programs, too.
When we speak of free software, we are referring to freedom, not
price. Our General Public Licenses are designed to make sure that you
have the freedom to distribute copies of free software (and charge for
them if you wish), that you receive source code or can get it if you
want it, that you can change the software or use pieces of it in new
free programs, and that you know you can do these things.
To protect your rights, we need to prevent others from denying you
these rights or asking you to surrender the rights. Therefore, you have
certain responsibilities if you distribute copies of the software, or if
you modify it: responsibilities to respect the freedom of others.
For example, if you distribute copies of such a program, whether
gratis or for a fee, you must pass on to the recipients the same
freedoms that you received. You must make sure that they, too, receive
or can get the source code. And you must show them these terms so they
know their rights.
Developers that use the GNU GPL protect your rights with two steps:
(1) assert copyright on the software, and (2) offer you this License
giving you legal permission to copy, distribute and/or modify it.
For the developers' and authors' protection, the GPL clearly explains
that there is no warranty for this free software. For both users' and
authors' sake, the GPL requires that modified versions be marked as
changed, so that their problems will not be attributed erroneously to
authors of previous versions.
Some devices are designed to deny users access to install or run
modified versions of the software inside them, although the manufacturer
can do so. This is fundamentally incompatible with the aim of
protecting users' freedom to change the software. The systematic
pattern of such abuse occurs in the area of products for individuals to
use, which is precisely where it is most unacceptable. Therefore, we
have designed this version of the GPL to prohibit the practice for those
products. If such problems arise substantially in other domains, we
stand ready to extend this provision to those domains in future versions
of the GPL, as needed to protect the freedom of users.
Finally, every program is threatened constantly by software patents.
States should not allow patents to restrict development and use of
software on general-purpose computers, but in those that do, we wish to
avoid the special danger that patents applied to a free program could
make it effectively proprietary. To prevent this, the GPL assures that
patents cannot be used to render the program non-free.
The precise terms and conditions for copying, distribution and
modification follow.
TERMS AND CONDITIONS
0. Definitions.
"This License" refers to version 3 of the GNU General Public License.
"Copyright" also means copyright-like laws that apply to other kinds of
works, such as semiconductor masks.
"The Program" refers to any copyrightable work licensed under this
License. Each licensee is addressed as "you". "Licensees" and
"recipients" may be individuals or organizations.
To "modify" a work means to copy from or adapt all or part of the work
in a fashion requiring copyright permission, other than the making of an
exact copy. The resulting work is called a "modified version" of the
earlier work or a work "based on" the earlier work.
A "covered work" means either the unmodified Program or a work based
on the Program.
To "propagate" a work means to do anything with it that, without
permission, would make you directly or secondarily liable for
infringement under applicable copyright law, except executing it on a
computer or modifying a private copy. Propagation includes copying,
distribution (with or without modification), making available to the
public, and in some countries other activities as well.
To "convey" a work means any kind of propagation that enables other
parties to make or receive copies. Mere interaction with a user through
a computer network, with no transfer of a copy, is not conveying.
An interactive user interface displays "Appropriate Legal Notices"
to the extent that it includes a convenient and prominently visible
feature that (1) displays an appropriate copyright notice, and (2)
tells the user that there is no warranty for the work (except to the
extent that warranties are provided), that licensees may convey the
work under this License, and how to view a copy of this License. If
the interface presents a list of user commands or options, such as a
menu, a prominent item in the list meets this criterion.
1. Source Code.
The "source code" for a work means the preferred form of the work
for making modifications to it. "Object code" means any non-source
form of a work.
A "Standard Interface" means an interface that either is an official
standard defined by a recognized standards body, or, in the case of
interfaces specified for a particular programming language, one that
is widely used among developers working in that language.
The "System Libraries" of an executable work include anything, other
than the work as a whole, that (a) is included in the normal form of
packaging a Major Component, but which is not part of that Major
Component, and (b) serves only to enable use of the work with that
Major Component, or to implement a Standard Interface for which an
implementation is available to the public in source code form. A
"Major Component", in this context, means a major essential component
(kernel, window system, and so on) of the specific operating system
(if any) on which the executable work runs, or a compiler used to
produce the work, or an object code interpreter used to run it.
The "Corresponding Source" for a work in object code form means all
the source code needed to generate, install, and (for an executable
work) run the object code and to modify the work, including scripts to
control those activities. However, it does not include the work's
System Libraries, or general-purpose tools or generally available free
programs which are used unmodified in performing those activities but
which are not part of the work. For example, Corresponding Source
includes interface definition files associated with source files for
the work, and the source code for shared libraries and dynamically
linked subprograms that the work is specifically designed to require,
such as by intimate data communication or control flow between those
subprograms and other parts of the work.
The Corresponding Source need not include anything that users
can regenerate automatically from other parts of the Corresponding
Source.
The Corresponding Source for a work in source code form is that
same work.
2. Basic Permissions.
All rights granted under this License are granted for the term of
copyright on the Program, and are irrevocable provided the stated
conditions are met. This License explicitly affirms your unlimited
permission to run the unmodified Program. The output from running a
covered work is covered by this License only if the output, given its
content, constitutes a covered work. This License acknowledges your
rights of fair use or other equivalent, as provided by copyright law.
You may make, run and propagate covered works that you do not
convey, without conditions so long as your license otherwise remains
in force. You may convey covered works to others for the sole purpose
of having them make modifications exclusively for you, or provide you
with facilities for running those works, provided that you comply with
the terms of this License in conveying all material for which you do
not control copyright. Those thus making or running the covered works
for you must do so exclusively on your behalf, under your direction
and control, on terms that prohibit them from making any copies of
your copyrighted material outside their relationship with you.
Conveying under any other circumstances is permitted solely under
the conditions stated below. Sublicensing is not allowed; section 10
makes it unnecessary.
3. Protecting Users' Legal Rights From Anti-Circumvention Law.
No covered work shall be deemed part of an effective technological
measure under any applicable law fulfilling obligations under article
11 of the WIPO copyright treaty adopted on 20 December 1996, or
similar laws prohibiting or restricting circumvention of such
measures.
When you convey a covered work, you waive any legal power to forbid
circumvention of technological measures to the extent such circumvention
is effected by exercising rights under this License with respect to
the covered work, and you disclaim any intention to limit operation or
modification of the work as a means of enforcing, against the work's
users, your or third parties' legal rights to forbid circumvention of
technological measures.
4. Conveying Verbatim Copies.
You may convey verbatim copies of the Program's source code as you
receive it, in any medium, provided that you conspicuously and
appropriately publish on each copy an appropriate copyright notice;
keep intact all notices stating that this License and any
non-permissive terms added in accord with section 7 apply to the code;
keep intact all notices of the absence of any warranty; and give all
recipients a copy of this License along with the Program.
You may charge any price or no price for each copy that you convey,
and you may offer support or warranty protection for a fee.
5. Conveying Modified Source Versions.
You may convey a work based on the Program, or the modifications to
produce it from the Program, in the form of source code under the
terms of section 4, provided that you also meet all of these conditions:
a) The work must carry prominent notices stating that you modified
it, and giving a relevant date.
b) The work must carry prominent notices stating that it is
released under this License and any conditions added under section
7. This requirement modifies the requirement in section 4 to
"keep intact all notices".
c) You must license the entire work, as a whole, under this
License to anyone who comes into possession of a copy. This
License will therefore apply, along with any applicable section 7
additional terms, to the whole of the work, and all its parts,
regardless of how they are packaged. This License gives no
permission to license the work in any other way, but it does not
invalidate such permission if you have separately received it.
d) If the work has interactive user interfaces, each must display
Appropriate Legal Notices; however, if the Program has interactive
interfaces that do not display Appropriate Legal Notices, your
work need not make them do so.
A compilation of a covered work with other separate and independent
works, which are not by their nature extensions of the covered work,
and which are not combined with it such as to form a larger program,
in or on a volume of a storage or distribution medium, is called an
"aggregate" if the compilation and its resulting copyright are not
used to limit the access or legal rights of the compilation's users
beyond what the individual works permit. Inclusion of a covered work
in an aggregate does not cause this License to apply to the other
parts of the aggregate.
6. Conveying Non-Source Forms.
You may convey a covered work in object code form under the terms
of sections 4 and 5, provided that you also convey the
machine-readable Corresponding Source under the terms of this License,
in one of these ways:
a) Convey the object code in, or embodied in, a physical product
(including a physical distribution medium), accompanied by the
Corresponding Source fixed on a durable physical medium
customarily used for software interchange.
b) Convey the object code in, or embodied in, a physical product
(including a physical distribution medium), accompanied by a
written offer, valid for at least three years and valid for as
long as you offer spare parts or customer support for that product
model, to give anyone who possesses the object code either (1) a
copy of the Corresponding Source for all the software in the
product that is covered by this License, on a durable physical
medium customarily used for software interchange, for a price no
more than your reasonable cost of physically performing this
conveying of source, or (2) access to copy the
Corresponding Source from a network server at no charge.
c) Convey individual copies of the object code with a copy of the
written offer to provide the Corresponding Source. This
alternative is allowed only occasionally and noncommercially, and
only if you received the object code with such an offer, in accord
with subsection 6b.
d) Convey the object code by offering access from a designated
place (gratis or for a charge), and offer equivalent access to the
Corresponding Source in the same way through the same place at no
further charge. You need not require recipients to copy the
Corresponding Source along with the object code. If the place to
copy the object code is a network server, the Corresponding Source
may be on a different server (operated by you or a third party)
that supports equivalent copying facilities, provided you maintain
clear directions next to the object code saying where to find the
Corresponding Source. Regardless of what server hosts the
Corresponding Source, you remain obligated to ensure that it is
available for as long as needed to satisfy these requirements.
e) Convey the object code using peer-to-peer transmission, provided
you inform other peers where the object code and Corresponding
Source of the work are being offered to the general public at no
charge under subsection 6d.
A separable portion of the object code, whose source code is excluded
from the Corresponding Source as a System Library, need not be
included in conveying the object code work.
A "User Product" is either (1) a "consumer product", which means any
tangible personal property which is normally used for personal, family,
or household purposes, or (2) anything designed or sold for incorporation
into a dwelling. In determining whether a product is a consumer product,
doubtful cases shall be resolved in favor of coverage. For a particular
product received by a particular user, "normally used" refers to a
typical or common use of that class of product, regardless of the status
of the particular user or of the way in which the particular user
actually uses, or expects or is expected to use, the product. A product
is a consumer product regardless of whether the product has substantial
commercial, industrial or non-consumer uses, unless such uses represent
the only significant mode of use of the product.
"Installation Information" for a User Product means any methods,
procedures, authorization keys, or other information required to install
and execute modified versions of a covered work in that User Product from
a modified version of its Corresponding Source. The information must
suffice to ensure that the continued functioning of the modified object
code is in no case prevented or interfered with solely because
modification has been made.
If you convey an object code work under this section in, or with, or
specifically for use in, a User Product, and the conveying occurs as
part of a transaction in which the right of possession and use of the
User Product is transferred to the recipient in perpetuity or for a
fixed term (regardless of how the transaction is characterized), the
Corresponding Source conveyed under this section must be accompanied
by the Installation Information. But this requirement does not apply
if neither you nor any third party retains the ability to install
modified object code on the User Product (for example, the work has
been installed in ROM).
The requirement to provide Installation Information does not include a
requirement to continue to provide support service, warranty, or updates
for a work that has been modified or installed by the recipient, or for
the User Product in which it has been modified or installed. Access to a
network may be denied when the modification itself materially and
adversely affects the operation of the network or violates the rules and
protocols for communication across the network.
Corresponding Source conveyed, and Installation Information provided,
in accord with this section must be in a format that is publicly
documented (and with an implementation available to the public in
source code form), and must require no special password or key for
unpacking, reading or copying.
7. Additional Terms.
"Additional permissions" are terms that supplement the terms of this
License by making exceptions from one or more of its conditions.
Additional permissions that are applicable to the entire Program shall
be treated as though they were included in this License, to the extent
that they are valid under applicable law. If additional permissions
apply only to part of the Program, that part may be used separately
under those permissions, but the entire Program remains governed by
this License without regard to the additional permissions.
When you convey a copy of a covered work, you may at your option
remove any additional permissions from that copy, or from any part of
it. (Additional permissions may be written to require their own
removal in certain cases when you modify the work.) You may place
additional permissions on material, added by you to a covered work,
for which you have or can give appropriate copyright permission.
Notwithstanding any other provision of this License, for material you
add to a covered work, you may (if authorized by the copyright holders of
that material) supplement the terms of this License with terms:
a) Disclaiming warranty or limiting liability differently from the
terms of sections 15 and 16 of this License; or
b) Requiring preservation of specified reasonable legal notices or
author attributions in that material or in the Appropriate Legal
Notices displayed by works containing it; or
c) Prohibiting misrepresentation of the origin of that material, or
requiring that modified versions of such material be marked in
reasonable ways as different from the original version; or
d) Limiting the use for publicity purposes of names of licensors or
authors of the material; or
e) Declining to grant rights under trademark law for use of some
trade names, trademarks, or service marks; or
f) Requiring indemnification of licensors and authors of that
material by anyone who conveys the material (or modified versions of
it) with contractual assumptions of liability to the recipient, for
any liability that these contractual assumptions directly impose on
those licensors and authors.
All other non-permissive additional terms are considered "further
restrictions" within the meaning of section 10. If the Program as you
received it, or any part of it, contains a notice stating that it is
governed by this License along with a term that is a further
restriction, you may remove that term. If a license document contains
a further restriction but permits relicensing or conveying under this
License, you may add to a covered work material governed by the terms
of that license document, provided that the further restriction does
not survive such relicensing or conveying.
If you add terms to a covered work in accord with this section, you
must place, in the relevant source files, a statement of the
additional terms that apply to those files, or a notice indicating
where to find the applicable terms.
Additional terms, permissive or non-permissive, may be stated in the
form of a separately written license, or stated as exceptions;
the above requirements apply either way.
8. Termination.
You may not propagate or modify a covered work except as expressly
provided under this License. Any attempt otherwise to propagate or
modify it is void, and will automatically terminate your rights under
this License (including any patent licenses granted under the third
paragraph of section 11).
However, if you cease all violation of this License, then your
license from a particular copyright holder is reinstated (a)
provisionally, unless and until the copyright holder explicitly and
finally terminates your license, and (b) permanently, if the copyright
holder fails to notify you of the violation by some reasonable means
prior to 60 days after the cessation.
Moreover, your license from a particular copyright holder is
reinstated permanently if the copyright holder notifies you of the
violation by some reasonable means, this is the first time you have
received notice of violation of this License (for any work) from that
copyright holder, and you cure the violation prior to 30 days after
your receipt of the notice.
Termination of your rights under this section does not terminate the
licenses of parties who have received copies or rights from you under
this License. If your rights have been terminated and not permanently
reinstated, you do not qualify to receive new licenses for the same
material under section 10.
9. Acceptance Not Required for Having Copies.
You are not required to accept this License in order to receive or
run a copy of the Program. Ancillary propagation of a covered work
occurring solely as a consequence of using peer-to-peer transmission
to receive a copy likewise does not require acceptance. However,
nothing other than this License grants you permission to propagate or
modify any covered work. These actions infringe copyright if you do
not accept this License. Therefore, by modifying or propagating a
covered work, you indicate your acceptance of this License to do so.
10. Automatic Licensing of Downstream Recipients.
Each time you convey a covered work, the recipient automatically
receives a license from the original licensors, to run, modify and
propagate that work, subject to this License. You are not responsible
for enforcing compliance by third parties with this License.
An "entity transaction" is a transaction transferring control of an
organization, or substantially all assets of one, or subdividing an
organization, or merging organizations. If propagation of a covered
work results from an entity transaction, each party to that
transaction who receives a copy of the work also receives whatever
licenses to the work the party's predecessor in interest had or could
give under the previous paragraph, plus a right to possession of the
Corresponding Source of the work from the predecessor in interest, if
the predecessor has it or can get it with reasonable efforts.
You may not impose any further restrictions on the exercise of the
rights granted or affirmed under this License. For example, you may
not impose a license fee, royalty, or other charge for exercise of
rights granted under this License, and you may not initiate litigation
(including a cross-claim or counterclaim in a lawsuit) alleging that
any patent claim is infringed by making, using, selling, offering for
sale, or importing the Program or any portion of it.
11. Patents.
A "contributor" is a copyright holder who authorizes use under this
License of the Program or a work on which the Program is based. The
work thus licensed is called the contributor's "contributor version".
A contributor's "essential patent claims" are all patent claims
owned or controlled by the contributor, whether already acquired or
hereafter acquired, that would be infringed by some manner, permitted
by this License, of making, using, or selling its contributor version,
but do not include claims that would be infringed only as a
consequence of further modification of the contributor version. For
purposes of this definition, "control" includes the right to grant
patent sublicenses in a manner consistent with the requirements of
this License.
Each contributor grants you a non-exclusive, worldwide, royalty-free
patent license under the contributor's essential patent claims, to
make, use, sell, offer for sale, import and otherwise run, modify and
propagate the contents of its contributor version.
In the following three paragraphs, a "patent license" is any express
agreement or commitment, however denominated, not to enforce a patent
(such as an express permission to practice a patent or covenant not to
sue for patent infringement). To "grant" such a patent license to a
party means to make such an agreement or commitment not to enforce a
patent against the party.
If you convey a covered work, knowingly relying on a patent license,
and the Corresponding Source of the work is not available for anyone
to copy, free of charge and under the terms of this License, through a
publicly available network server or other readily accessible means,
then you must either (1) cause the Corresponding Source to be so
available, or (2) arrange to deprive yourself of the benefit of the
patent license for this particular work, or (3) arrange, in a manner
consistent with the requirements of this License, to extend the patent
license to downstream recipients. "Knowingly relying" means you have
actual knowledge that, but for the patent license, your conveying the
covered work in a country, or your recipient's use of the covered work
in a country, would infringe one or more identifiable patents in that
country that you have reason to believe are valid.
If, pursuant to or in connection with a single transaction or
arrangement, you convey, or propagate by procuring conveyance of, a
covered work, and grant a patent license to some of the parties
receiving the covered work authorizing them to use, propagate, modify
or convey a specific copy of the covered work, then the patent license
you grant is automatically extended to all recipients of the covered
work and works based on it.
A patent license is "discriminatory" if it does not include within
the scope of its coverage, prohibits the exercise of, or is
conditioned on the non-exercise of one or more of the rights that are
specifically granted under this License. You may not convey a covered
work if you are a party to an arrangement with a third party that is
in the business of distributing software, under which you make payment
to the third party based on the extent of your activity of conveying
the work, and under which the third party grants, to any of the
parties who would receive the covered work from you, a discriminatory
patent license (a) in connection with copies of the covered work
conveyed by you (or copies made from those copies), or (b) primarily
for and in connection with specific products or compilations that
contain the covered work, unless you entered into that arrangement,
or that patent license was granted, prior to 28 March 2007.
Nothing in this License shall be construed as excluding or limiting
any implied license or other defenses to infringement that may
otherwise be available to you under applicable patent law.
12. No Surrender of Others' Freedom.
If conditions are imposed on you (whether by court order, agreement or
otherwise) that contradict the conditions of this License, they do not
excuse you from the conditions of this License. If you cannot convey a
covered work so as to satisfy simultaneously your obligations under this
License and any other pertinent obligations, then as a consequence you may
not convey it at all. For example, if you agree to terms that obligate you
to collect a royalty for further conveying from those to whom you convey
the Program, the only way you could satisfy both those terms and this
License would be to refrain entirely from conveying the Program.
13. Use with the GNU Affero General Public License.
Notwithstanding any other provision of this License, you have
permission to link or combine any covered work with a work licensed
under version 3 of the GNU Affero General Public License into a single
combined work, and to convey the resulting work. The terms of this
License will continue to apply to the part which is the covered work,
but the special requirements of the GNU Affero General Public License,
section 13, concerning interaction through a network will apply to the
combination as such.
14. Revised Versions of this License.
The Free Software Foundation may publish revised and/or new versions of
the GNU General Public License from time to time. Such new versions will
be similar in spirit to the present version, but may differ in detail to
address new problems or concerns.
Each version is given a distinguishing version number. If the
Program specifies that a certain numbered version of the GNU General
Public License "or any later version" applies to it, you have the
option of following the terms and conditions either of that numbered
version or of any later version published by the Free Software
Foundation. If the Program does not specify a version number of the
GNU General Public License, you may choose any version ever published
by the Free Software Foundation.
If the Program specifies that a proxy can decide which future
versions of the GNU General Public License can be used, that proxy's
public statement of acceptance of a version permanently authorizes you
to choose that version for the Program.
Later license versions may give you additional or different
permissions. However, no additional obligations are imposed on any
author or copyright holder as a result of your choosing to follow a
later version.
15. Disclaimer of Warranty.
THERE IS NO WARRANTY FOR THE PROGRAM, TO THE EXTENT PERMITTED BY
APPLICABLE LAW. EXCEPT WHEN OTHERWISE STATED IN WRITING THE COPYRIGHT
HOLDERS AND/OR OTHER PARTIES PROVIDE THE PROGRAM "AS IS" WITHOUT WARRANTY
OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO,
THE IMPLIED WARRANTIES OF MERCHANTABILITY AND FITNESS FOR A PARTICULAR
PURPOSE. THE ENTIRE RISK AS TO THE QUALITY AND PERFORMANCE OF THE PROGRAM
IS WITH YOU. SHOULD THE PROGRAM PROVE DEFECTIVE, YOU ASSUME THE COST OF
ALL NECESSARY SERVICING, REPAIR OR CORRECTION.
16. Limitation of Liability.
IN NO EVENT UNLESS REQUIRED BY APPLICABLE LAW OR AGREED TO IN WRITING
WILL ANY COPYRIGHT HOLDER, OR ANY OTHER PARTY WHO MODIFIES AND/OR CONVEYS
THE PROGRAM AS PERMITTED ABOVE, BE LIABLE TO YOU FOR DAMAGES, INCLUDING ANY
GENERAL, SPECIAL, INCIDENTAL OR CONSEQUENTIAL DAMAGES ARISING OUT OF THE
USE OR INABILITY TO USE THE PROGRAM (INCLUDING BUT NOT LIMITED TO LOSS OF
DATA OR DATA BEING RENDERED INACCURATE OR LOSSES SUSTAINED BY YOU OR THIRD
PARTIES OR A FAILURE OF THE PROGRAM TO OPERATE WITH ANY OTHER PROGRAMS),
EVEN IF SUCH HOLDER OR OTHER PARTY HAS BEEN ADVISED OF THE POSSIBILITY OF
SUCH DAMAGES.
17. Interpretation of Sections 15 and 16.
If the disclaimer of warranty and limitation of liability provided
above cannot be given local legal effect according to their terms,
reviewing courts shall apply local law that most closely approximates
an absolute waiver of all civil liability in connection with the
Program, unless a warranty or assumption of liability accompanies a
copy of the Program in return for a fee.
END OF TERMS AND CONDITIONS